## F4
MSPGCL-Chandrapur U # 3-7
MTR Petition Formats - Generation
| Form 4: Summary of Capital Expenditure and Capitalisation | [16 empty] | (Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-24 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MTR Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MTR Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MTR Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h )+ (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 131.0561 | 131.0561 |  | 127.604 | 127.604 |  | 31.16 | 560.1931 | 591.3531 | 591.3531 | 3042.2372 | 2211.6905 | 814.964 | 879.1599 | 211.02
2 | Capitalisation | 199.17 | 117.3226 | -81.8474 | 149.45 | 110.7942 | -38.6558 | 920.43 | 31.16 | 607.2179 | 638.3779 | -282.0521 | 2974.7857 | 2260.8135 | 789.964 | 879.1599 | 211.02
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 199.17 | 117.3226 | -81.8474 | 149.45 | 110.7942 | -38.6558 | 920.43 | 31.16 | 607.2179 | 638.3779 | -282.0521 | 2974.7857 | 2260.8135 | 789.964 | 879.1599 | 211.02
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Chandrapur U # 3-7
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | DPR | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 1.06 | 0.44763 |  | 0.61237 |  |  | 0.61237
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 11.8 | 0 |  | 11.8 |  |  | 11.8
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 12.3 | 10.0166 |  | 2.2834 |  |  | 2.2834
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 7.52 | 3.8602 |  | 3.6598 |  |  | 3.6598
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 43.2 | 56.1594 |  | -12.9594 |  |  | -12.9594
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 23.4 | 12.9173 |  | 10.4827 |  |  | 10.4827
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 27.6 | 11.3681 |  | 16.2319 |  |  | 16.2319
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 1.43 | 1.8769 |  | -0.44693 |  |  | -0.44693
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 3.5 | 4.2488 |  | -0.74883 |  |  | -0.74883
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 2 | 2.0468 |  | -0.046828 |  |  | -0.046828
1.11 | Reducing the pressure drop across ESP | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 2.913 | 1.6187 |  | 1.2943 |  |  | 1.2943
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 15 | 14.8516 |  | 0.14838 |  |  | 0.14838
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 4.604 | 0.089776 |  | 4.5142 |  |  | 4.5142
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 10.5 | 0 |  | 10.5 |  |  | 10.5
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 4.91 | 3.5436 |  | 1.3664 |  |  | 1.3664
0 | IDC | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 |  | 2010-11-25 |  | - | - |  | - | 10.09 | 0 |  | 10.09 |  |  | 10.09
2 | Input source Measurement | DPR | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 1.0398 | 0.707 |  | 0.3328 |  |  | 0.3328
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 3.138 | 0 |  | 3.138 |  |  | 3.138
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 3.0657 | 1.7643 |  | 1.3014 |  |  | 1.3014
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 0.0211 | 0 |  | 0.0211 |  |  | 0.0211
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 0.4954 | 0.29784 |  | 0.19756 |  |  | 0.19756
2.6 | Belt weighers (28 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 3.3196 | 0 |  | 3.3196 |  |  | 3.3196
2.7 | In motion weigh bridge (10 Nos). | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 4.5396 | 0.19084 |  | 4.3488 |  |  | 4.3488
2.8 | Bunker level transmitters (50 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 2.5285 | 0 |  | 2.5285 |  |  | 2.5285
2.9 | Flap Gate sensors (120 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 0.1225 | 0 |  | 0.1225 |  |  | 0.1225
2.10 | PLC (20 Nos) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 0.5333 | 0 |  | 0.5333 |  |  | 0.5333
2.11 | Cables (20,000 meters estimated) | Scheme | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 1.0216 | 0 |  | 1.0216 |  |  | 1.0216
0 | IDC | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 |  | 2011-07-06 |  | - | - |  | - | 1.165 | 0 |  | 1.165 |  |  | 1.165
3 | ESP Restoration/Refurbishment | DPR | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | Scheme | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 11.7 | 8.6202 |  | 3.0798 |  |  | 3.0798
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | Scheme | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 15.6 | 6.5553 |  | 9.0447 |  |  | 9.0447
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | Scheme | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 16.02 | 5.1899 |  | 10.8301 |  |  | 10.8301
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | Scheme | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 0.95 | 0.92199 |  | 0.028006 |  |  | 0.028006
0 | IDC | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 |  | 2011-07-07 |  | - | - |  | - | 9.72 | 0.03865 |  | 9.6814 |  |  | 9.6814
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | DPR | MERC/CAPEX/20112012/01908 | 2011-11-03 |  | 2011-11-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | Scheme | MERC/CAPEX/20112012/01908 | 2011-11-03 |  | 2011-11-03 |  | - | - |  | - | 26.1 | 0 |  | 26.1 |  |  | 26.1
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | Scheme | MERC/CAPEX/20112012/01908 | 2011-11-03 |  | 2011-11-03 |  | - | - |  | - | 26.1 | 0 |  | 26.1 |  |  | 26.1
0 | IDC | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 |  | 2011-11-03 |  | - | - |  | - | 5.5 | 0 |  | 5.5 |  |  | 5.5
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | DPR | MERC/CAPEX/20112012/02443 | 2012-01-03 |  | 2012-01-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | Scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 |  | 2012-01-03 |  | - | - |  | - | 229.4 | 0 |  | 229.4 |  |  | 229.4
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | DPR | MERC/CAPEX/20122013/00818 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | Scheme | MERC/CAPEX/20122013/00818 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 16.77 | 5.4267 |  | 11.3433 |  |  | 11.3433
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | DPR | MERC/CAPEX/20122013/00827 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | Construction for U#5 | Scheme | MERC/CAPEX/20122013/00827 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 11.2318 | 19.3782 |  | -8.1464 |  |  | -8.1464
7.2 | Construction for U#6 | Scheme | MERC/CAPEX/20122013/00827 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 14.968 | 23.1899 |  | -8.2219 |  |  | -8.2219
0 | IDC | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 |  | 2012-07-10 |  | - | - |  | - | 3.0802 | 0 |  | 3.0802 |  |  | 3.0802
8 | Upgradation of IDCT Unit 5 | DPR | MERC/CAPEX/20122013/00914 | 2012-07-18 |  | 2012-07-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Cooling Tower IDCT for Unit-5A | Scheme | MERC/CAPEX/20122013/00914 | 2012-07-18 |  | 2012-07-18 |  | - | - |  | - | 8.5 | 0 |  | 8.5 |  |  | 8.5
8.2 | Cooling Tower IDCT for Unit-5B | Scheme | MERC/CAPEX/20122013/00914 | 2012-07-18 |  | 2012-07-18 |  | - | - |  | - | 8.5 | 0 |  | 8.5 |  |  | 8.5
0 | IDC | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 |  | 2012-07-18 |  | - | - |  | - | 1.2 | 0 |  | 1.2 |  |  | 1.2
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | DPR | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 101.8526 | 0 |  | 101.8526 |  |  | 101.8526
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 5.9838 | 0 |  | 5.9838 |  |  | 5.9838
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | DPR | MERC/CAPEX/20122013/02104 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
10.1 | Complete series replacement in U-5 & 6 | Scheme | MERC/CAPEX/20122013/02104 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 7.12 | 1.408 |  | 5.712 |  |  | 5.712
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | Scheme | MERC/CAPEX/20122013/02104 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 3.03 | 2.4824 |  | 0.54762 |  |  | 0.54762
10.3 | Replacement ash line worn out pipes | Scheme | MERC/CAPEX/20122013/02104 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 3.6 | 4.4211 |  | -0.82109 |  |  | -0.82109
0 | IDC | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 |  | 2013-01-07 |  | - | - |  | - | 1.5 | 0 |  | 1.5 |  |  | 1.5
11 | Fully Integrated Security Surveillance System | DPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
11.1 | Long range cameras | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 12.3 | 0 |  | 12.3 |  |  | 12.3
11.2 | Laser fence sensors/buried cable | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 6.1 | 0 |  | 6.1 |  |  | 6.1
11.3 | PTZ/fixed cameras | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 8.075 | 0 |  | 8.075 |  |  | 8.075
11.4 | Command & control /video wall | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 16 | 0 |  | 16 |  |  | 16
11.5 | Communication | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 0.4595 | 0 |  | 0.4595 |  |  | 0.4595
11.6 | RFID | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 0.83 | 0 |  | 0.83 |  |  | 0.83
11.7 | LPR | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 0.6 | 0 |  | 0.6 |  |  | 0.6
11.8 | Electricals/networking | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 2.8674 | 0 |  | 2.8674 |  |  | 2.8674
11.9 | Infrastructure | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 3.896 | 0 |  | 3.896 |  |  | 3.896
0 | IDC | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 |  | 2013-04-18 |  | - | - |  | - | 3.07 | 0 |  | 3.07 |  |  | 3.07
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | DPR | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
12.1 | AFGC U 5,7 | Scheme | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 2.08 | 2.037 |  | 0.043043 |  |  | 0.043043
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | Scheme | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 7.1339 | 0 |  | 7.1339 |  |  | 7.1339
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 0.87 | 0 |  | 0.87 |  |  | 0.87
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | DPR | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 32.76 | 11.6609 |  | 21.0991 |  |  | 21.0991
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 3.88 | 3.5012 |  | 0.37878 |  |  | 0.37878
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 9.81 | 4.9253 |  | 4.8847 |  |  | 4.8847
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 4.76 | 2.7668 |  | 1.9932 |  |  | 1.9932
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 13.41 | 6.3206 |  | 7.0894 |  |  | 7.0894
13.6 | Work Cost for Replacement of above Assemblies. | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 5.05 | 0 |  | 5.05 |  |  | 5.05
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 |  | 2014-01-08 |  | - | - |  | - | 6.9 | 0 |  | 6.9 |  |  | 6.9
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | DPR | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 |  | 2013-10-01 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | Scheme | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 |  | 2013-10-01 |  | - | - |  | - | 48.0394 | 48.0394 |  | 0 |  |  | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | Scheme | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 |  | 2013-10-01 |  | - | - |  | - | 35.7843 | 35.7843 |  | 0 |  |  | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | DPR | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 |  | 2013-10-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | Scheme | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 |  | 2013-10-18 |  | - | - |  | - | 8.8554 | 0 |  | 8.8554 |  |  | 8.8554
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | Scheme | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 |  | 2013-10-18 |  | - | - |  | - | 2.1445 | 0 |  | 2.1445 |  |  | 2.1445
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 |  | 2013-10-18 |  | - | - |  | - | 0.1701 | 0 |  | 0.1701 |  |  | 0.1701
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | DPR | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | Scheme | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 5.5023 | 4.2319 |  | 1.2704 |  |  | 1.2704
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | Scheme | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 5.5023 | 4.5024 |  | 0.9999 |  |  | 0.9999
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 |  | 2014-06-02 |  | - | - |  | - | 0.74 | 0 |  | 0.74 |  |  | 0.74
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | DPR | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | Scheme | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 13.5092 | 5.3885 |  | 8.1207 |  |  | 8.1207
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | Scheme | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 4.551 | 2.347 |  | 2.204 |  |  | 2.204
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 1.25 | 0 |  | 1.25 |  |  | 1.25
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | DPR | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 4.4388 | 1.6219 |  | 2.8169 |  |  | 2.8169
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 2.2757 | 2.2757 |  | 0 |  |  | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 4.4665 | 2.2258 |  | 2.2407 |  |  | 2.2407
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0.7335 | 0 |  | 0.7335 |  |  | 0.7335
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | DPR | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 |  | 2014-09-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | Scheme | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 |  | 2014-09-11 |  | - | - |  | - | 4.87 | 2.8937 |  | 1.9763 |  |  | 1.9763
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | Scheme | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 |  | 2014-09-11 |  | - | - |  | - | 7.0937 | 6.1698 |  | 0.9239 |  |  | 0.9239
0 | IDC | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 |  | 2014-09-11 |  | - | - |  | - | 1.2 | 0 |  | 1.2 |  |  | 1.2
20 | 210/500 MW CHP performance improvement | DPR | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
20.1 | Provision of over band suspended magnets for CHP-C. | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 1.077 | 0.90834 |  | 0.16866 |  |  | 0.16866
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 5.759 | 2.8943 |  | 2.8647 |  |  | 2.8647
20.3 | Bulldozer BD-155 | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 5.12 | 7.9707 |  | -2.8507 |  |  | -2.8507
20.4 | Modification of wagon tippler CHP-A | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 3.897 | 4.4884 |  | -0.59144 |  |  | -0.59144
0 | IDC | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 |  | 2015-09-09 |  | - | - |  | - | 0.45 | 0 |  | 0.45 |  |  | 0.45
21 | Improvement in Electrical Systems | DPR | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | Scheme | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 2.71 | 3.7131 |  | -1.0031 |  |  | -1.0031
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | Scheme | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 0.55 | 0.53016 |  | 0.019835 |  |  | 0.019835
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | Scheme | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 3.12 | 3.5539 |  | -0.43392 |  |  | -0.43392
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | Scheme | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 2.34 | 3.3241 |  | -0.98414 |  |  | -0.98414
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | Scheme | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 1.03 | 1.1916 |  | -0.16158 |  |  | -0.16158
0 | IDC | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 |  | 2016-05-10 |  | - | - |  | - | 0.75 | 0 |  | 0.75 |  |  | 0.75
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | DPR | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | Scheme | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 4.61 | 3.9122 |  | 0.69782 |  |  | 0.69782
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | Scheme | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 4.61 | 0 |  | 4.61 |  |  | 4.61
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | Scheme | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 2.98 | 1.3773 |  | 1.6027 |  |  | 1.6027
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | Scheme | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 5.37 | 4.5728 |  | 0.79719 |  |  | 0.79719
0 | IDC | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 |  | 2016-08-02 |  | - | - |  | - | 0.6 | 0 |  | 0.6 |  |  | 0.6
23 | Performance Improvement & Life enhancement of 500MW CHP-B | DPR | MERC/CAPEX/20162017/01067 | 2016-11-28 |  | 2016-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | Scheme | MERC/CAPEX/20162017/01067 | 2016-11-28 |  | 2016-11-28 |  | - | - |  | - | 5.76 | 5.295 |  | 0.46505 |  |  | 0.46505
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | Scheme | MERC/CAPEX/20162017/01067 | 2016-11-28 |  | 2016-11-28 |  | - | - |  | - | 2.19 | 2.3148 |  | -0.12475 |  |  | -0.12475
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | Scheme | MERC/CAPEX/20162017/01067 | 2016-11-28 |  | 2016-11-28 |  | - | - |  | - | 10.33 | 11.7941 |  | -1.4641 |  |  | -1.4641
0 | IDC | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 |  | 2016-11-28 |  | - | - |  | - | 0.5 | 0 |  | 0.5 |  |  | 0.5
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | DPR | MERC/CAPEX/20162017/01475 | 2017-02-06 |  | 2017-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | Scheme | MERC/CAPEX/20162017/01475 | 2017-02-06 |  | 2017-02-06 |  | - | - |  | - | 3.25 | 3.8744 |  | -0.62442 |  |  | -0.62442
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | Scheme | MERC/CAPEX/20162017/01475 | 2017-02-06 |  | 2017-02-06 |  | - | - |  | - | 3.46 | 3.5523 |  | -0.09228 |  |  | -0.09228
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | Scheme | MERC/CAPEX/20162017/01475 | 2017-02-06 |  | 2017-02-06 |  | - | - |  | - | 6.19 | 4.5767 |  | 1.6133 |  |  | 1.6133
0 | IDC | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 |  | 2017-02-06 |  | - | - |  | - | 0.8 | 0 |  | 0.8 |  |  | 0.8
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | DPR | MERC/CAPEX/20162017/01269 | 2017-01-02 |  | 2017-01-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | Scheme | MERC/CAPEX/20162017/01269 | 2017-01-02 |  | 2017-01-02 |  | - | - |  | - | 14.686 | 12.4004 |  | 2.2856 |  |  | 2.2856
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | DPR | MERC/CAPEX/20172018/4171 | 2017-09-08 |  | 2017-09-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | Scheme | MERC/CAPEX/20172018/4171 | 2017-09-08 |  | 2017-09-08 |  | - | - |  | - | 196.26 | 256.8153 |  | -60.5553 |  |  | -60.5553
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | DPR | MERC/CAPEX/20172018/4071 | 2017-08-18 |  | 2017-08-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | Scheme | MERC/CAPEX/20172018/4071 | 2017-08-18 |  | 2017-08-18 |  | - | - |  | - | 18.25 | 8.283 |  | 9.967 |  |  | 9.967
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | Scheme | MERC/CAPEX/20172018/4071 | 2017-08-18 |  | 2017-08-18 |  | - | - |  | - | 6.72 | 6.0757 |  | 0.6443 |  |  | 0.6443
0 | IDC | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 |  | 2017-08-18 |  | - | - |  | - | 0.3 | 0 |  | 0.3 |  |  | 0.3
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | DPR | MERC/CAPEX/20172018/4686 | 2017-11-15 |  | 2017-11-15 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | Scheme | MERC/CAPEX/20172018/4686 | 2017-11-15 |  | 2017-11-15 |  | - | - |  | - | 10.36 | 11.5758 |  | -1.2158 |  |  | -1.2158
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | Scheme | MERC/CAPEX/20172018/4686 | 2017-11-15 |  | 2017-11-15 |  | - | - |  | - | 0.63 | 0 |  | 0.63 |  |  | 0.63
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | Scheme | MERC/CAPEX/20172018/4686 | 2017-11-15 |  | 2017-11-15 |  | - | - |  | - | 0.536 | 0.51656 |  | 0.019438 |  |  | 0.019438
0 | IDC | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 |  | 2017-11-15 |  | - | - |  | - | 0.93 | 0 |  | 0.93 |  |  | 0.93
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | DPR | MERC/CAPEX/20172018/0272 | 2018-02-23 |  | 2018-02-23 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-02-23 |  | 2018-02-23 |  | - | - |  | - | 2.01 | 2.115 |  | -0.10502 |  |  | -0.10502
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-02-23 |  | 2018-02-23 |  | - | - |  | - | 3.34 | 1.9274 |  | 1.4126 |  |  | 1.4126
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-02-23 |  | 2018-02-23 |  | - | - |  | - | 9.02 | 8.8302 |  | 0.1898 |  |  | 0.1898
0 | IDC | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 |  | 2018-02-23 |  | - | - |  | - | 1.12 | 0 |  | 1.12 |  |  | 1.12
30 | Renovation & Beautification of Colony at Chandrapur STPS | DPR | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 82.6 | 82.25 |  | 0.35 |  |  | 0.35
30.2 | Colony Internal Roads at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 7.08 | 6.3802 |  | 0.6998 |  |  | 0.6998
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 4.72 | 4.1941 |  | 0.52593 |  |  | 0.52593
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 15.34 | 5.247 |  | 10.093 |  |  | 10.093
0 | IDC | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 7.83 | 10.9403 |  | -3.1103 |  |  | -3.1103
31 | Fully Integrated Security Surveillance System | DPR | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 24.03 | 0 |  | 24.03 |  |  | 24.03
31.2 | FIRE ALARM SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 4.33 | 0 |  | 4.33 |  |  | 4.33
31.3 | ACCESS CONTROL SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 0.48 | 0 |  | 0.48 |  |  | 0.48
31.4 | EPABX | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 1.93 | 0 |  | 1.93 |  |  | 1.93
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 1.76 | 0 |  | 1.76 |  |  | 1.76
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 1.25 | 0 |  | 1.25 |  |  | 1.25
31.7 | NETWORKING | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 9.35 | 0 |  | 9.35 |  |  | 9.35
31.8 | MESSAGE DISPLAY SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 0.31 | 0 |  | 0.31 |  |  | 0.31
31.9 | IP PA SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 2.74 | 0 |  | 2.74 |  |  | 2.74
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 7.63 | 0 |  | 7.63 |  |  | 7.63
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 18.67 | 0 |  | 18.67 |  |  | 18.67
31.12 | ADDITIONAL CIVIL WORK | Scheme | MERC/CAPEX/2018-19/066 | 2019-03-05 |  | 2019-03-05 |  | - | - |  | - | 3.93 | 0 |  | 3.93 |  |  | 3.93
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | DPR | MERC/CAPEX/20182019/1240 | 2018-09-20 |  | 2018-09-20 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | Scheme | MERC/CAPEX/20182019/1240 | 2018-09-20 |  | 2018-09-20 |  | - | - |  | - | 32.56 | 29.2032 |  | 3.3568 |  |  | 3.3568
32.2 | Automation of Control Room of CHP-B Using PLC System | Scheme | MERC/CAPEX/20182019/1240 | 2018-09-20 |  | 2018-09-20 |  | - | - |  | - | 4.91 | 0 |  | 4.91 |  |  | 4.91
0 | IDC | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 |  | 2018-09-20 |  | - | - |  | - | 1.16 | 0 |  | 1.16 |  |  | 1.16
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | DPR | MERC/CAPEX/2019-2020/362 | 2019-07-11 |  | 2019-07-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | Scheme | MERC/CAPEX/2019-2020/362 | 2019-07-11 |  | 2019-07-11 |  | - | - |  | - | 14.2003 | 1.4649 |  | 12.7354 |  |  | 12.7354
0 | IDC | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 |  | 2019-07-11 |  | - | - |  | - | 1.02 | 0 |  | 1.02 |  |  | 1.02
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | DPR | MERC/CAPEX/2019-2020/129 | 2019-05-03 |  | 2019-05-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | Scheme | MERC/CAPEX/2019-2020/129 | 2019-05-03 |  | 2019-05-03 |  | - | - |  | - | 40.3591 | 42.1896 |  | -1.8305 |  |  | -1.8305
0 | IDC | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 |  | 2019-05-03 |  | - | - |  | - | 1.11 | 0 |  | 1.11 |  |  | 1.11
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | DPR | MERC/CAPEX/2019-2020/1214 | 2019-12-23 |  | 2019-12-23 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | Scheme | MERC/CAPEX/2019-2020/1214 | 2019-12-23 |  | 2019-12-23 |  | - | - |  | - | 21.66 | 22.8548 |  | -1.1948 |  |  | -1.1948
0 | IDC | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 |  | 2019-12-23 |  | - | - |  | - | 0.39 | 0 |  | 0.39 |  |  | 0.39
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | DPR | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 |  | 2020-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 |  | 2020-09-30 |  | - | - |  | - | 18.32 | 16.77 |  | 1.55 |  |  | 1.55
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 |  | 2020-09-30 |  | - | - |  | - | 0.24 | 0 |  | 0.24 |  |  | 0.24
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | DPR | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 |  | 2020-12-14 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 |  | 2020-12-14 |  | - | - |  | - | 602.58 | 0 |  | 602.58 |  |  | 602.58
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 |  | 2020-12-14 |  | - | - |  | - | 53.67 | 0 |  | 53.67 |  |  | 53.67
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | DPR | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 |  | 2015-01-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | Scheme | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 |  | 2015-01-29 |  | - | - |  | - | 9.4 | 9.3999 |  | 0.0001392 |  |  | 0.0001392
0 | IDC | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 |  | 2015-01-29 |  | - | - |  | - | 0.6 | 0 |  | 0.6 |  |  | 0.6
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | DPR | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 |  | 2021-05-19 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 |  | 2021-05-19 |  | - | - |  | - | 21.02 | 9.9521 |  | 11.0679 |  |  | 11.0679
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 |  | 2021-05-19 |  | - | - |  | - | 0.51 | 0 |  | 0.51 |  |  | 0.51
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | DPR | MERC/CAP/DPR/10/07/1149 | 2007-05-30 |  | 2007-05-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 1.1 | CSTPS U-1,2&4 | Scheme | MERC/CAP/DPR/10/07/1149 | 2007-05-30 |  | 2007-05-30 |  | - | - |  | - | 9.6 | 4.9831 |  | 4.6169 |  |  | 4.6169
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | DPR | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 4.1 | Chandrapur TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 10.36 | 0 |  | 10.36 |  |  | 10.36
0 | IDC | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 |  | 2013-07-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 5.706 | 0.90661 |  | 4.7994 |  |  | 4.7994
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 |  | 2014-11-25 |  | - | - |  | - | 11.25 | 5.7542 |  | 5.4958 |  |  | 5.4958
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 1.3258 | 0 |  | 1.3258 |  |  | 1.3258
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 7.1 | Chandrapur STPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 7.0966 | 0 |  | 7.0966 |  |  | 7.0966
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 2.9 | 0.26772 |  | 2.6323 |  |  | 2.6323
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 1.25 | 2.1847 |  | -0.93465 |  |  | -0.93465
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10.1 | CSTPS Chandrapur | Scheme | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 9.0742 | 9.6123 |  | -0.53805 |  |  | -0.53805
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | DPR | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 1.73 | 1.696 |  | 0.034034 |  |  | 0.034034
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 9.4 | 8.9105 |  | 0.4895 |  |  | 0.4895
0 | IDC | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 2.9127 | 2.8883 |  | 0.02438 |  |  | 0.02438
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0.84252 | 0.84252 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | DPR | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | Scheme | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 6.2 | 6.0121 |  | 0.1879 |  |  | 0.1879
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | Scheme | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 4.39 | 4.3294 |  | 0.060636 |  |  | 0.060636
0 | IDC | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 |  | 2021-06-10 |  | - | - |  | - | 0.3 | 0 |  | 0.3 |  |  | 0.3
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/0321 | 2022-07-18 |  | 2022-07-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2022-2023/0321 | 2022-07-18 |  | 2022-07-18 |  | - | - |  | - | 6.08 | 3.607 |  | 2.473 |  |  | 2.473
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2022-2023/0321 | 2022-07-18 |  | 2022-07-18 |  | - | - |  | - | 5.28 | 2.709 |  | 2.571 |  |  | 2.571
41.3 | Generator Protection Scheme U-7 | Scheme | MERC/CAPEX/2022-2023/0321 | 2022-07-18 |  | 2022-07-18 |  | - | - |  | - | 1.98 | 1.7287 |  | 0.2513 |  |  | 0.2513
0 | IDC | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 |  | 2022-07-18 |  | - | - |  | - | 0.72 | 0 |  | 0.72 |  |  | 0.72
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | DPR | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 207.46 | 0 |  | 207.46 |  |  | 207.46
0 | IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 |  | 2022-09-29 |  | - | - |  | - | 11.98 | 0 |  | 11.98 |  |  | 11.98
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | DPR | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 109.4 | 0 |  | 109.4 |  |  | 109.4
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 5.94 | 0 |  | 5.94 |  |  | 5.94
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/0409 | 2022-09-02 |  | 2022-09-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | Scheme | MERC/CAPEX/2022-2023/0409 | 2022-09-02 |  | 2022-09-02 |  | - | - |  | - | 32.568 | 0 |  | 32.568 |  |  | 32.568
0 | IDC | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 |  | 2022-09-02 |  | - | - |  | - | 0.7 | 0 |  | 0.7 |  |  | 0.7
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 101.8102 | 40.1338 |  | 61.6764 |  |  | 61.6764
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 1.708 | 0 |  | 1.708 |  |  | 1.708
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 4.2692 | 0 |  | 4.2692 |  |  | 4.2692
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 25.6575 | 0 |  | 25.6575 |  |  | 25.6575
0 | IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 |  | 2023-09-05 |  | - | - |  | - | 11.61 | 0 |  | 11.61 |  |  | 11.61
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 |  | 2024-05-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | DPR | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 5.66 | 0 |  | 5.66 |  |  | 5.66
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 8.17 | 0 |  | 8.17 |  |  | 8.17
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 4.12 | 0 |  | 4.12 |  |  | 4.12
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 3.72 | 0 |  | 3.72 |  |  | 3.72
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 3.45 | 0 |  | 3.45 |  |  | 3.45
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 4.6 | 0 |  | 4.6 |  |  | 4.6
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 8.14 | 0 |  | 8.14 |  |  | 8.14
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 4.18 | 0 |  | 4.18 |  |  | 4.18
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 |  | 2023-10-31 |  | - | - |  | - | 0.97 | 0 |  | 0.97 |  |  | 0.97
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 18 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 18.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | DPR | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 80.15 | 0 |  | 80.15 |  |  | 80.15
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 1.2 | 0 |  | 1.2 |  |  | 1.2
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 7.19 | 0 |  | 7.19 |  |  | 7.19
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0.8 | 0 |  | 0.8 |  |  | 0.8
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 2.97 | 2.9194 |  | 0.050603 |  |  | 0.050603
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 10.48 | 0 |  | 10.48 |  |  | 10.48
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 3.66 | 0 |  | 3.66 |  |  | 3.66
0 | IDC | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0.68 | 0 |  | 0.68 |  |  | 0.68
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | DPR | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 |  | 2024-08-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | DPR | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 9.58 | 0 |  | 9.58 |  |  | 9.58
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 2.95 | 0 |  | 2.95 |  |  | 2.95
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 7.95 | 0 |  | 7.95 |  |  | 7.95
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 17.46 | 0 |  | 17.46 |  |  | 17.46
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 |  | 2024-08-08 |  | - | - |  | - | 0.46 | 0 |  | 0.46 |  |  | 0.46
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | DPR | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 |  | 2024-09-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | Scheme | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 |  | 2024-09-09 |  | - | - |  | - | 17.61 | 0 |  | 17.61 |  |  | 17.61
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | Scheme | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 |  | 2024-09-09 |  | - | - |  | - | 14.65 | 0 |  | 14.65 |  |  | 14.65
0 | IDC | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 |  | 2024-09-09 |  | - | - |  | - | 0.29 | 0 |  | 0.29 |  |  | 0.29
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected |  |  |  |  | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
[50 empty] | N.A. | DPR | Not Initiated
| A) DPR Schemes | [48 empty] | N.A. | Scheme | WIP
| (i) In Principally Approved By MERC | [48 empty] | N.A. | IDC | Partially Capitalised
1 | Boiler & Turbine Improvement | DPR | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 181.827 | 181.827 |  |  | 2010-11-25 | [8 empty] | 0 | [19 empty] | 0 | [11 empty] | Non-DPR | Capitalised
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 1.06 | 1.06 |  |  | 2010-11-25 |  |  |  |  | 0.44763 | 0 | 0 | 0 | 0.44763 | 0 | 0 | 0 | [12 empty] | 0.44763 | 0 | 0 | 0 | 0.44763 | 0 | 0 | 0 | [7 empty] | Cancelled |  | Cancelled
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 11.8 | 11.8 |  |  | 2010-11-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Cancelled |  | To be cancelled
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 12.3 | 12.3 |  |  | 2010-11-25 |  |  |  |  | 2.243 | 1.7453 | 0.98157 | 5.0468 | 10.0166 |  | 0 | 0 | [9 empty] | 100% |  |  | 0.48 | 3.5082 | 0.98157 | 5.0468 | 10.0166 |  | 0 | 0 | [7 empty] | Capitalised |  | N.A.
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 7.52 | 7.52 |  |  | 2010-11-25 |  |  |  |  | 3.8602 | 0 | 0 | 0 | 3.8602 | 0 | 0 | 0 | [5 empty] | 100% | [6 empty] | 3.8602 | 0 | 0 | 0 | 3.8602 | 0 | 0 | 0 | [7 empty] | Capitalised |  | To be confirmed
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 43.2 | 43.2 |  |  | 2010-11-25 |  |  |  |  | 56.1594 | 0 | 0 | 0 | 56.1594 | 0 | 0 | 0 | [5 empty] | 100% | [6 empty] | 56.1594 | 0 | 0 | 0 | 56.1594 | 0 | 0 | 0 | [7 empty] | Capitalised
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 23.4 | 23.4 |  |  | 2010-11-25 |  |  |  |  | 12.9173 | 0 | 0 | 0 | 12.9173 | 0 | 0 | 0 | [5 empty] | 100% | [6 empty] | 12.9173 | 0 | 0 | 0 | 12.9173 | 0 | 0 | 0 | [7 empty] | Capitalised
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 27.6 | 27.6 |  |  | 2010-11-25 |  |  |  |  | 11.3681 | 0 | 0 | 0 | 11.3681 | 0 | 0 | 0 | [5 empty] | 100% | [6 empty] | 11.3681 | 0 | 0 | 0 | 11.3681 | 0 | 0 | 0 | [7 empty] | Capitalised
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 1.43 | 1.43 |  |  | 2010-11-25 |  |  |  |  | 1.8769 | 0 | 0 | 0 | 1.8769 | 0 | 0 | 0 | [5 empty] | 100% | [6 empty] | 1.8769 | 0 | 0 | 0 | 1.8769 | 0 | 0 | 0 | [7 empty] | Capitalised
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 3.5 | 3.5 |  |  | 2010-11-25 |  |  |  |  | 0 | 2.3482 | 0 | 1.5723 | 3.9205 | 0.32828 | 0 | 0 | [8 empty] | 100% |  |  |  | 0 | 0 | 2.3482 | 1.5723 | 3.9205 | 0.32828 | 0 | 0 | [7 empty] | Capitalised
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 2 | 2 |  |  | 2010-11-25 |  |  |  |  | 0 | 0 | 2.0468 | 0 | 2.0468 | 0 | 0 | 0 | [7 empty] | 100% |  |  |  |  | 0 | 0 | 2.0468 | 0 | 2.0468 | 0 | 0 | 0 | [7 empty] | Capitalised
1.11 | Reducing the pressure drop across ESP | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 0 | 0 |  |  | 2010-11-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Cancelled
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 2.913 | 2.913 |  |  | 2010-11-25 |  |  |  |  | 1.5327 | 0.086077 | 0 | 0 | 1.6187 | 0 | 0 | 0 | [5 empty] | 90% | 95% | 100% |  |  |  |  | 1.0515 | 0.48117 | 0.086077 | 0 | 1.6187 | 0 | 0 | 0 | [7 empty] | Capitalised
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 15 | 15 |  |  | 2010-11-25 |  |  |  |  | 12.4669 | 0 | 2.1568 | 0.228 | 14.8516 | 3.9e-08 | 0 | 0 | [7 empty] | 100% |  |  |  |  | 12.4669 | 0 | 0.39452 | 1.9902 | 14.8516 | 3.9e-08 | 0 | 0 | [7 empty] | Capitalised
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 4.604 | 4.604 |  |  | 2010-11-25 |  |  |  |  | 0.089776 | 0 | 0 | 0 | 0.089776 | 0 | 0 | 0 | [12 empty] | 0.089776 | 0 | 0 | 0 | 0.089776 | 0 | 0 | 0 | [7 empty] | Cancelled
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 10.5 | 10.5 |  |  | 2010-11-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Cancelled
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | Scheme | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 4.91 | 4.91 |  |  | 2010-11-25 |  |  |  |  | 1.2188 | 0 | 0 | 2.3249 | 3.5436 | 0 | 0 | 0 | [5 empty] | 40% |  |  | 100% |  |  |  | 1.2188 | 0 | 0 | 2.3249 | 3.5436 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20102011/01755 | 2010-11-03 | 2010-11-25 | 10.09 | 10.09 |  |  | 2010-11-25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Input source Measurement | DPR | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 20.9901 | 20.9901 |  |  | 2011-07-06 | [8 empty] | 0 | [19 empty] | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 1.0398 | 1.0398 |  |  | 2011-07-06 |  |  |  |  | 0.707 |  |  |  | 0.707 | [15 empty] | 0.707 |  |  |  | 0.707 | [10 empty] | Capitalised
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 3.138 | 3.138 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 3.0657 | 3.0657 |  |  | 2011-07-06 |  |  |  |  | 1.7643 |  |  |  | 1.7643 | [15 empty] | 1.7643 |  |  |  | 1.7643 | [10 empty] | Capitalised
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 0.0211 | 0.0211 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 0.4954 | 0.4954 |  |  | 2011-07-06 |  |  |  |  | 0.29784 |  |  |  | 0.29784 | [15 empty] | 0.29784 |  |  |  | 0.29784 | [10 empty] | Capitalised
2.6 | Belt weighers (28 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 3.3196 | 3.3196 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
2.7 | In motion weigh bridge (10 Nos). | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 4.5396 | 4.5396 |  |  | 2011-07-06 |  |  |  |  | 0.19084 |  |  |  | 0.19084 | [15 empty] | 0.19084 |  |  |  | 0.19084 | [10 empty] | Cancelled
2.8 | Bunker level transmitters (50 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 2.5285 | 2.5285 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
2.9 | Flap Gate sensors (120 Nos.) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 0.1225 | 0.1225 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
2.10 | PLC (20 Nos) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 0.5333 | 0.5333 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
2.11 | Cables (20,000 meters estimated) | Scheme | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 1.0216 | 1.0216 |  |  | 2011-07-06 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | To be cancelled
| IDC | IDC | MERC/CAPEX/20112012/00925 | 2011-04-26 | 2011-07-06 | 1.165 | 1.165 |  |  | 2011-07-06 | [8 empty] | 0 | [19 empty] | 0
3 | ESP Restoration/Refurbishment | DPR | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 53.99 | 53.99 |  |  | 2011-07-07 | [8 empty] | 0 | [19 empty] | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | Scheme | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 11.7 | 11.7 |  |  | 2011-07-07 |  |  |  |  | 3.3841 | 1.7132 | 0 | 0 | 5.0972 | 0.64944 | 2.8735 | 0 | [12 empty] | 0 | 5.0972 | 5.4e-05 | 0 | 5.0973 | 0.64939 | 2.8735 | 0 | [7 empty] | Capitalised
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | Scheme | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 15.6 | 15.6 |  |  | 2011-07-07 |  |  |  |  | 4.5099 | 0.41802 | 0 | 0.12178 | 5.0497 | 1.1781 | 0.32741 | 0 | 6 | [11 empty] | 4.5099 | 0.41802 | 0 | 0 | 4.9279 | 1.2999 | 0.32741 | 0 | 6 | [6 empty] | Partially Capitalised
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | Scheme | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 16.02 | 16.02 |  |  | 2011-07-07 |  |  |  |  | 4.5201 | 0 | 0 | 0 | 4.5201 | 0.66977 |  |  | 8 | [11 empty] | 4.4155 | 0 | 0 | 0 | 4.4155 | 0.66977 |  |  | 8 | [6 empty] | Partially Capitalised
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | Scheme | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 0.95 | 0.95 |  |  | 2011-07-07 |  |  |  |  | 0.92199 | 0 | 0 | 0 | 0.92199 | 0 | 0 | 0 | [12 empty] | 0.92199 | 0 | 0 | 0 | 0.92199 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20112012/00939 | 2011-06-15 | 2011-07-07 | 9.72 | 9.72 |  |  | 2011-07-07 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.03865 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0.03865 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | DPR | MERC/CAPEX/20112012/01908 | 2011-08-03 | 2011-11-03 | 57.7 | 57.7 |  |  | 2011-11-03 | [8 empty] | 0 | [19 empty] | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | Scheme | MERC/CAPEX/20112012/01908 | 2011-08-03 | 2011-11-03 | 26.1 | 26.1 |  |  | 2011-11-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26.1 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26.1 | [6 empty] | WIP
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | Scheme | MERC/CAPEX/20112012/01908 | 2011-08-03 | 2011-11-03 | 26.1 | 26.1 |  |  | 2011-11-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 26.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 26.1 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/20112012/01908 | 2011-08-03 | 2011-11-03 | 5.5 | 5.5 |  |  | 2011-11-03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | DPR | MERC/CAPEX/20112012/02443 | 2011-08-23 | 2012-01-03 | 229.4 | 229.4 |  |  | 2012-01-03 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | Scheme | MERC/CAPEX/20112012/02443 | 2011-08-23 | 2012-01-03 | 229.4 | 229.4 |  |  | 2012-01-03 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | DPR | MERC/CAPEX/20122013/00818 | 2011-11-25 | 2012-07-10 | 16.77 | 16.77 |  |  | 2012-07-10 | [8 empty] | 0 | [19 empty] | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | Scheme | MERC/CAPEX/20122013/00818 | 2011-11-25 | 2012-07-10 | 16.77 | 16.77 |  |  | 2012-07-10 |  |  |  |  | 0 | 0 | 0 | 5.4267 | 5.4267 |  | 0 | 0 | 11.3433 | [11 empty] | 0 | 0 | 0 | 4.0159 | 4.0159 |  | 0 | 0 | 12.7541 | [6 empty] | Partially Capitalised
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | DPR | MERC/CAPEX/20122013/00827 | 2011-11-23 | 2012-07-10 | 29.5098 | 29.28 |  |  | 2012-07-10 | [8 empty] | 0 | [19 empty] | 0
7.1 | Construction for U#5 | Scheme | MERC/CAPEX/20122013/00827 | 2011-11-23 | 2012-07-10 | 11.2318 | 11.2318 |  |  | 2012-07-10 |  |  |  |  | 19.3782 | 0 | 0 | 0 | 19.3782 | 0 | 0 | 0 | [12 empty] | 19.3782 |  |  |  | 19.3782 | [9 empty] | Fully Approved | Capitalised
7.2 | Construction for U#6 | Scheme | MERC/CAPEX/20122013/00827 | 2011-11-23 | 2012-07-10 | 14.968 | 14.968 |  |  | 2012-07-10 |  |  |  |  | 19.4149 | 3.775 | 0 | 0 | 23.1899 | 0 | 0 | 0 | [12 empty] | 19.4149 | 0 | 3.775 | 0 | 23.1899 | 0 | 0 | 0 | [6 empty] | Cost Overrun of Rs. 4.45 Cr disallowed in FY 2018-19 | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/00827 | 2011-11-23 | 2012-07-10 | 3.31 | 3.0802 |  |  | 2012-07-10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | DPR | MERC/CAPEX/20122013/00914 | 2011-12-30 | 2012-07-18 | 18.2 | 18.2 |  |  | 2012-07-18 | [8 empty] | 0 | [19 empty] | 0
8.1 | Cooling Tower IDCT for Unit-5A | Scheme | MERC/CAPEX/20122013/00914 | 2011-12-30 | 2012-07-18 | 8.5 | 8.5 |  |  | 2012-07-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
8.2 | Cooling Tower IDCT for Unit-5B | Scheme | MERC/CAPEX/20122013/00914 | 2011-12-30 | 2012-07-18 | 8.5 | 8.5 |  |  | 2012-07-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/CAPEX/20122013/00914 | 2011-12-30 | 2012-07-18 | 1.2 | 1.2 |  |  | 2012-07-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | DPR | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 107.8364 | 107.8364 |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | Scheme | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 101.8526 | 101.8526 |  |  | 2013-07-09 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2012-06-14 | 2013-07-09 | 5.9838 | 5.9838 |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | DPR | MERC/CAPEX/20122013/02104 | 2012-09-17 | 2013-01-07 | 15.25 | 15.25 |  |  | 2013-01-07 | [8 empty] | 0 | [19 empty] | 0
10.1 | Complete series replacement in U-5 & 6 | Scheme | MERC/CAPEX/20122013/02104 | 2012-09-17 | 2013-01-07 | 7.12 | 7.12 |  |  | 2013-01-07 |  |  |  |  | 1.408 |  |  |  | 1.408 | [15 empty] | 1.408 |  |  |  | 1.408 | [10 empty] | Cancelled
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | Scheme | MERC/CAPEX/20122013/02104 | 2012-09-17 | 2013-01-07 | 3.03 | 3.03 |  |  | 2013-01-07 |  |  |  |  | 2.1444 |  |  |  | 2.1444 | 0.16888 | 0.16907 | [13 empty] | 2.1444 |  |  |  | 2.1444 | 0.16888 | 0.16907 | [8 empty] | Capitalised
10.3 | Replacement ash line worn out pipes | Scheme | MERC/CAPEX/20122013/02104 | 2012-09-17 | 2013-01-07 | 3.6 | 3.6 |  |  | 2013-01-07 |  |  |  |  | 4.4211 |  |  |  | 4.4211 | [15 empty] | 4.4211 |  |  |  | 4.4211 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20122013/02104 | 2012-09-17 | 2013-01-07 | 1.5 | 1.5 |  |  | 2013-01-07 | [8 empty] | 0 | [19 empty] | 0
11 | Fully Integrated Security Surveillance System | DPR | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 54.1979 | 54.1979 |  |  | 2013-04-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
11.1 | Long range cameras | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 12.3 | 12.3 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.2 | Laser fence sensors/buried cable | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 6.1 | 6.1 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.3 | PTZ/fixed cameras | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 8.075 | 8.075 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.4 | Command & control /video wall | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 16 | 16 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.5 | Communication | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 0.4595 | 0.4595 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.6 | RFID | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 0.83 | 0.83 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.7 | LPR | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 0.6 | 0.6 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.8 | Electricals/networking | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 2.8674 | 2.8674 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
11.9 | Infrastructure | Scheme | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 3.896 | 3.896 |  |  | 2013-04-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2012-09-26 | 2013-04-18 | 3.07 | 3.07 |  |  | 2013-04-18 | [8 empty] | 0 | [19 empty] | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | DPR | MERC/TECH 1/CAPEX/20132014/01366 | 2013-06-13 | 2013-10-04 | 10.0839 | 10.0839 |  |  | 2013-10-04 | [8 empty] | 0 | [19 empty] | 0
12.1 | AFGC U 5,7 | Scheme | MERC/TECH 1/CAPEX/20132014/01366 | 2013-06-13 | 2013-10-04 | 2.08 | 2.08 |  |  | 2013-10-04 |  |  |  |  | 2.037 |  |  |  | 2.037 | [15 empty] | 2.037 |  |  |  | 2.037 | [10 empty] | Capitalised
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | Scheme | MERC/TECH 1/CAPEX/20132014/01366 | 2013-06-13 | 2013-10-04 | 7.1339 | 7.1339 |  |  | 2013-10-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [5 empty] | Proposal stg | Not Initiated
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-06-13 | 2013-10-04 | 0.87 | 0.87 |  |  | 2013-10-04 | [8 empty] | 0 | [19 empty] | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | DPR | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 76.57 | 76.57 |  |  | 2014-01-08 | [8 empty] | 0 | [19 empty] | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 32.76 | 32.76 |  |  | 2014-01-08 |  |  |  |  | 11.6609 | 0 | 0 | 0 | 11.6609 | 0 | 0 | 0 | [12 empty] | 11.6609 | 0 | 0 | 0 | 11.6609 | 0 | 0 | 0 | [7 empty] | Capitalised
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 3.88 | 3.88 |  |  | 2014-01-08 |  |  |  |  | 3.5012 | 0 | 0 | 0 | 3.5012 | 0 | 0 | 0 | [12 empty] | 3.5012 | 0 | 0 | 0 | 3.5012 | 0 | 0 | 0 | [7 empty] | Capitalised
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 9.81 | 9.81 |  |  | 2014-01-08 |  |  |  |  | 3.9521 | 0.97317 | 0 | 0 | 4.9253 | 0 | 0 | 0 | [12 empty] | 0 | 4.9253 | 0 | 0 | 4.9253 | 0 | 0 | 0 | [7 empty] | Capitalised
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 4.76 | 4.76 |  |  | 2014-01-08 |  |  |  |  | 1.7334 | 1.0334 | 0 | 0 | 2.7668 | 0 | 0 | 0 | [12 empty] | 0 | 2.7668 | 0 | 0 | 2.7668 | 0 | 0 | 0 | [7 empty] | Capitalised
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 13.41 | 13.41 |  |  | 2014-01-08 |  |  |  |  | 0 | 6.3206 | 0 | 0 | 6.3206 | 0 | 0 | 0 | [12 empty] | 0 | 6.3206 | 0 | 0 | 6.3206 | 0 | 0 | 0 | [7 empty] | Capitalised
13.6 | Work Cost for Replacement of above Assemblies. | Scheme | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 5.05 | 5.05 |  |  | 2014-01-08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2013-07-04 | 2014-01-08 | 6.9 | 6.9 |  |  | 2014-01-08 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | DPR | MERC/TECH 1/CAPEX/20132014/01334 | 2013-07-24 | 2013-10-01 | 83.8237 | 83.8237 |  |  | 2013-10-01 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Capitalised
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | Scheme | MERC/TECH 1/CAPEX/20132014/01334 | 2013-07-24 | 2013-10-01 | 48.0394 | 48.0394 |  |  | 2013-10-01 |  |  |  |  | 48.0394 |  |  |  | 48.0394 | [15 empty] | 48.0394 |  |  |  | 48.0394 | [10 empty] | Capitalised
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | Scheme | MERC/TECH 1/CAPEX/20132014/01334 | 2013-07-24 | 2013-10-01 | 35.7843 | 35.7843 |  |  | 2013-10-01 |  |  |  |  | 35.7843 |  |  |  | 35.7843 | [15 empty] | 35.7843 |  |  |  | 35.7843 | [10 empty] | Capitalised
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | DPR | MERC/TECH 1/CAPEX/20132014/01431 | 2013-08-20 | 2013-10-18 | 11.17 | 11.17 |  |  | 2013-10-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | Scheme | MERC/TECH 1/CAPEX/20132014/01431 | 2013-08-20 | 2013-10-18 | 8.8554 | 8.8554 |  |  | 2013-10-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | Scheme | MERC/TECH 1/CAPEX/20132014/01431 | 2013-08-20 | 2013-10-18 | 2.1445 | 2.1445 |  |  | 2013-10-18 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-08-20 | 2013-10-18 | 0.1701 | 0.1701 |  |  | 2013-10-18 | [8 empty] | 0 | [19 empty] | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | DPR | MERC/TECH 1/CAPEX/20142015/00432 | 2014-04-19 | 2014-06-02 | 11.7446 | 11.7446 |  |  | 2014-06-02 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Capitalised
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | Scheme | MERC/TECH 1/CAPEX/20142015/00432 | 2014-04-19 | 2014-06-02 | 5.5023 | 5.5023 |  |  | 2014-06-02 |  |  |  |  | 4.2319 |  |  |  | 4.2319 | [15 empty] | 4.2319 |  |  |  | 4.2319 | [10 empty] | Capitalised
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | Scheme | MERC/TECH 1/CAPEX/20142015/00432 | 2014-04-19 | 2014-06-02 | 5.5023 | 5.5023 |  |  | 2014-06-02 |  |  |  |  | 4.5024 |  |  |  | 4.5024 | [15 empty] | 4.5024 |  |  |  | 4.5024 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-04-19 | 2014-06-02 | 0.74 | 0.74 |  |  | 2014-06-02 | [8 empty] | 0 | [19 empty] | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | DPR | MERC/TECH 1/CAPEX/20142015/0010 | 2014-06-20 | 2014-10-16 | 19.3102 | 19.3102 |  |  | 2014-10-16 | [8 empty] | 0 | [19 empty] | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | Scheme | MERC/TECH 1/CAPEX/20142015/0010 | 2014-06-20 | 2014-10-16 | 13.5092 | 13.5092 |  |  | 2014-10-16 |  |  |  |  | 0 | 0 | 0 | 1.3517 | 1.3517 | 4.0368 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 1.3517 | 1.3517 | 4.0368 | 0 | 0 | [7 empty] | Capitalised
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | Scheme | MERC/TECH 1/CAPEX/20142015/0010 | 2014-06-20 | 2014-10-16 | 4.551 | 4.551 |  |  | 2014-10-16 |  |  |  | Benefits cannot be quantified as Pumps are procured as Insurance spares for replacemet in case of emergency reducing down time of auxiliary / unit. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. | 0 | 0 | 0 | 0 | 0 | 2.347 |  | 3.5 | 1.4 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 2.347 |  | 3.5 | 1.4 | [6 empty] | Partially Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-06-20 | 2014-10-16 | 1.25 | 1.25 |  |  | 2014-10-16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | DPR | MERC/TECH 1/CAPEX/20142015/01220 | 2014-09-10 | 2014-11-25 | 11.9128 | 11.9145 |  |  | 2014-11-25 | [8 empty] | 0 | [19 empty] | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-09-10 | 2014-11-25 | 4.4388 | 4.4388 |  |  | 2014-11-25 |  |  |  |  | 1.6219 | 0 | 0 | 0 | 1.6219 | 0 | 0 | 0 | [12 empty] | 1.6219 | 0 | 0 | 0 | 1.6219 | 0 | 0 | 0 | [7 empty] | Capitalised
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-09-10 | 2014-11-25 | 2.274 | 2.2757 |  |  | 2014-11-25 |  |  |  |  | 1.2441 | 1.0315 | 0 | 0 | 2.2757 | 0 | 0 | 0 | [12 empty] | 1.2441 | 0 | 0 | 1.0315 | 2.2757 | 0 | 0 | 0 | [7 empty] | Capitalised
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | Scheme | MERC/TECH 1/CAPEX/20142015/01220 | 2014-09-10 | 2014-11-25 | 4.4665 | 4.4665 |  |  | 2014-11-25 |  |  |  |  | 2.2258 | 0 | 0 | 0 | 2.2258 | 0 | 0 | 0 | [12 empty] | 2.2258 | 0 | 0 | 0 | 2.2258 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-09-10 | 2014-11-25 | 0.7335 | 0.7335 |  |  | 2014-11-25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | DPR | MERC/TECH 1/CAPEX/20142015/00950 | 2014-07-31 | 2014-09-11 | 13.1637 | 13.1637 |  |  | 2014-09-11 | [8 empty] | 0 | [19 empty] | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | Scheme | MERC/TECH 1/CAPEX/20142015/00950 | 2014-07-31 | 2014-09-11 | 4.87 | 4.87 |  |  | 2014-09-11 |  |  |  |  | 2.8937 |  |  |  | 2.8937 | [15 empty] | 2.8937 |  |  |  | 2.8937 | [10 empty] | Capitalised
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | Scheme | MERC/TECH 1/CAPEX/20142015/00950 | 2014-07-31 | 2014-09-11 | 7.0937 | 7.0937 |  |  | 2014-09-11 |  |  |  |  | 6.1698 |  |  |  | 6.1698 | [15 empty] | 6.1698 |  |  |  | 6.1698 | [10 empty] | Capitalised
| IDC | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-07-31 | 2014-09-11 | 1.2 | 1.2 |  |  | 2014-09-11 | [8 empty] | 0 | [19 empty] | 0
20 | 210/500 MW CHP performance improvement | DPR | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 16.303 | 16.303 |  |  | 2015-09-09 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Capitalised
20.1 | Provision of over band suspended magnets for CHP-C. | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 1.077 | 1.077 |  |  | 2015-09-09 |  |  |  |  | 0.90834 |  |  |  | 0.90834 | [15 empty] | 0.90834 |  |  |  | 0.90834 | [10 empty] | Capitalised
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 5.759 | 5.759 |  |  | 2015-09-09 |  |  |  |  | 2.8943 |  |  |  | 2.8943 | [15 empty] | 2.8943 |  |  |  | 2.8943 | [10 empty] | Capitalised
20.3 | Bulldozer BD-155 | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 5.12 | 5.12 |  |  | 2015-09-09 |  |  |  |  | 7.9707 |  |  |  | 7.9707 | [15 empty] | 7.9707 |  |  |  | 7.9707 | [10 empty] | Capitalised
20.4 | Modification of wagon tippler CHP-A | Scheme | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 3.897 | 3.897 |  |  | 2015-09-09 |  |  |  |  | 4.4884 |  |  |  | 4.4884 | [15 empty] | 4.4884 |  |  |  | 4.4884 | [10 empty] | Capitalised
| IDC | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-08-31 | 2015-09-09 | 0.45 | 0.45 |  |  | 2015-09-09 | [8 empty] | 0 | [19 empty] | 0
21 | Improvement in Electrical Systems | DPR | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 10.5 | 10.5 |  |  | 2016-05-10 | [8 empty] | 0 | [19 empty] | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | Scheme | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 2.71 | 2.71 |  |  | 2016-05-10 |  |  |  |  | 3.6387 | 0 | 0 | 0.07434 | 3.7131 | 0 | 0 | 0 | [12 empty] | 0 | 3.6387 | 0 | 0.07434 | 3.7131 | 0 | 0 | 0 | [7 empty] | Capitalised
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | Scheme | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 0.55 | 0.55 |  |  | 2016-05-10 |  |  |  |  | 0.53016 | 0 | 0 | 0 | 0.53016 | 0 | 0 | 0 | [12 empty] | 0.53016 | 0 | 0 | 0 | 0.53016 | 0 | 0 | 0 | [7 empty] | Capitalised
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | Scheme | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 3.12 | 3.12 |  |  | 2016-05-10 |  |  |  |  | 3.5539 | 0 | 0 | 0 | 3.5539 | 0 | 0 | 0 | [12 empty] | 3.5539 | 0 | 0 | 0 | 3.5539 | 0 | 0 | 0 | [7 empty] | Capitalised
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | Scheme | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 2.34 | 2.34 |  |  | 2016-05-10 |  |  |  |  | 2.6948 | 0.14843 | 0 | 0.2865 | 3.1298 | 0.19438 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 3.1298 | 3.1298 | 0.19438 | 0 | 0 | [7 empty] | Capitalised
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | Scheme | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 1.03 | 1.03 |  |  | 2016-05-10 |  |  |  |  | 1.1916 | 0 | 0 | 0 | 1.1916 | 0 | 0 | 0 | [12 empty] | 1.1916 | 0 | 0 | 0 | 1.1916 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/00192 | 2015-07-17 | 2016-05-10 | 0.75 | 0.75 |  |  | 2016-05-10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | DPR | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 18.17 | 18.17 |  |  | 2016-08-02 | [8 empty] | 0 | [19 empty] | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | Scheme | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 4.61 | 4.61 |  |  | 2016-08-02 |  |  |  | As the scheme is not related to generation, the cost benefit may not be analysed. However, by implementing the scheme, following benefits is achieved. 1. Stack emission of Unit#3 is reduced. 2. As the two rows of ESP fields are new, availability, reliability of total ESP fields is increased. 3. Repetation of field inspection reduced as replaced by new one as compared to old fields.. | 0 | 0 | 0 | 3.8049 | 3.8049 | 0.10731 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 3.8049 | 3.8049 | 0.10731 | 0 | 0 | [7 empty] | Capitalised
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | Scheme | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 4.61 | 4.61 | [6 empty] | As the scheme is not related to generation, the cost benefit may not be analysed. However, by implementing the scheme, following benefits will be achieved. 1. Stack emission of Unit#4 will reduced. 2. As the two rows of ESP fields are new, availability, reliability of total ESP fields will increased. 3. Repetation of field inspection will reduced as replaced by new one as compared to old fields.. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.61 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4.61 | [5 empty] | Proposal stg | Not Initiated
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | Scheme | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 2.98 | 2.98 |  |  | 2016-08-02 |  |  |  |  | 1.3773 | 0 | 0 | 0 | 1.3773 | 0 | 0 | 0 | [12 empty] | 1.3773 | 0 | 0 | 0 | 1.3773 | 0 | 0 | 0 | [7 empty] | Capitalised
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | Scheme | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 5.37 | 5.37 |  |  | 2016-08-02 |  |  |  |  | 0 | 0 | 4.4976 | 0 | 4.4976 | 0.07524 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 4.5728 |  | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20152016/00420 | 2015-07-29 | 2016-08-02 | 0.6 | 0.6 |  |  | 2016-08-02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | DPR | MERC/CAPEX/20162017/01067 | 2015-12-04 | 2016-11-28 | 18.78 | 18.78 |  |  | 2016-11-28 | [8 empty] | 0 | [19 empty] | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | Scheme | MERC/CAPEX/20162017/01067 | 2015-12-04 | 2016-11-28 | 5.76 | 5.76 |  |  | 2016-11-28 |  |  |  |  | 5.295 | 0 | 0 | 0 | 5.295 | 0 | 0 | 0 | [12 empty] | 5.295 | 0 | 0 | 0 | 5.295 | 0 | 0 | 0 | [7 empty] | Capitalised
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | Scheme | MERC/CAPEX/20162017/01067 | 2015-12-04 | 2016-11-28 | 2.19 | 2.19 |  |  | 2016-11-28 |  |  |  |  | 2.3128 | 0.0019456 | 0 | 0 | 2.3148 | 0 | 0 | 0 | [12 empty] | 0 | 2.3148 | 0 | 0 | 2.3148 | 0 | 0 | 0 | [7 empty] | Capitalised
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | Scheme | MERC/CAPEX/20162017/01067 | 2015-12-04 | 2016-11-28 | 10.33 | 10.33 |  |  | 2016-11-28 |  |  |  |  | 0 | 11.2985 | 0.3658 | 0.1298 | 11.7941 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 11.7941 | 11.7941 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/01067 | 2015-12-04 | 2016-11-28 | 0.5 | 0.5 |  |  | 2016-11-28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | DPR | MERC/CAPEX/20162017/01475 | 2016-05-20 | 2017-02-06 | 13.7 | 13.7 |  |  | 2017-02-06 | [8 empty] | 0 | [19 empty] | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | Scheme | MERC/CAPEX/20162017/01475 | 2016-05-20 | 2017-02-06 | 3.25 | 3.25 |  |  | 2017-02-06 |  |  |  |  | 2.88 | 0.67228 | 0 | 0.32214 | 3.8744 | 0 | 0 | 0 | [12 empty] | 0 | 3.5523 | 0 | 0.32214 | 3.8744 | 0 | 0 | 0 | [7 empty] | Capitalised
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | Scheme | MERC/CAPEX/20162017/01475 | 2016-05-20 | 2017-02-06 | 3.46 | 3.46 |  |  | 2017-02-06 |  |  |  |  | 3.4443 | 0.10794 | 0 | 0 | 3.5523 | 0 | 0 | 0 | [12 empty] | 0 | 3.5523 | 0 | 0 | 3.5523 | 0 | 0 | 0 | [7 empty] | Capitalised
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | Scheme | MERC/CAPEX/20162017/01475 | 2016-05-20 | 2017-02-06 | 6.19 | 6.19 |  |  | 2017-02-06 |  |  |  |  | 4.5767 | 0 | 0 | 0 | 4.5767 | 0 | 0 | 0 | [12 empty] | 4.5767 | 0 | 0 | 0 | 4.5767 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/01475 | 2016-05-20 | 2017-02-06 | 0.8 | 0.8 |  |  | 2017-02-06 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | DPR | MERC/CAPEX/20162017/01269 | 2016-08-26 | 2017-01-02 | 5.736 | 14.686 |  |  | 2017-01-02 | [8 empty] | 0 | [19 empty] | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | Scheme | MERC/CAPEX/20162017/01269 | 2016-08-26 | 2017-01-02 | 5.736 | 14.686 |  |  | 2017-01-02 |  |  |  |  | 4.365 | 5.0886 | 0 | 2.7132 | 12.1667 |  | 0.23363 | 2.29 | [12 empty] | 0 | 0 | 5.854 | 3.564 | 9.418 | 2.5941 | 0.3883 | 2.29 | [7 empty] | Partially Capitalised
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | DPR | MERC/CAPEX/20172018/4171 | 2017-01-10 | 2017-09-08 | 196.26 | 196.26 |  |  | 2017-09-08 | [8 empty] | 0 | [19 empty] | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | Scheme | MERC/CAPEX/20172018/4171 | 2017-01-10 | 2017-09-08 | 196.26 | 196.26 |  |  | 2017-09-08 |  |  |  |  | 2.3195 | 0 | 0 | 252.2656 | 254.5851 | 1.8582 | 0.37193 | 0 | [12 empty] | 0 | 0 | 0 | 254.5851 | 254.5851 | 1.8582 | 0.37193 | 0 | [7 empty] | Capitalised
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | DPR | MERC/CAPEX/20172018/4071 | 2017-03-31 | 2017-08-18 | 26.72 | 25.27 |  |  | 2017-08-18 | [8 empty] | 0 | [19 empty] | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | Scheme | MERC/CAPEX/20172018/4071 | 2017-03-31 | 2017-08-18 | 19.7 | 18.25 |  |  | 2017-08-18 |  |  |  |  | 8.283 | 0 | 0 | 0 | 8.283 | 0 | 0 | 0 | [12 empty] | 8.283 | 0 | 0 | 0 | 8.283 | 0 | 0 | 0 | [7 empty] | Capitalised
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | Scheme | MERC/CAPEX/20172018/4071 | 2017-03-31 | 2017-08-18 | 6.72 | 6.72 |  |  | 2017-08-18 |  |  |  |  | 0 | 0 | 0 | 6.0757 | 6.0757 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 6.0757 | 6.0757 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4071 | 2017-03-31 | 2017-08-18 | 0.3 | 0.3 |  |  | 2017-08-18 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | DPR | MERC/CAPEX/20172018/4686 | 2017-08-29 | 2017-11-15 | 12.456 | 12.456 |  |  | 2017-11-15 | [8 empty] | 0 | [19 empty] | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | Scheme | MERC/CAPEX/20172018/4686 | 2017-08-29 | 2017-11-15 | 10.36 | 10.36 |  |  | 2017-11-15 |  |  |  |  | 11.4814 | 0.0944 | 0 | 0 | 11.5758 | 0 | 0 | 0 | [12 empty] | 5.428 | 6.1478 | 0 | 0 | 11.5758 | 0 | 0 | 0 | [7 empty] | Capitalised
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | Scheme | MERC/CAPEX/20172018/4686 | 2017-08-29 | 2017-11-15 | 0.63 | 0.63 |  |  | 2017-11-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | WIP
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | Scheme | MERC/CAPEX/20172018/4686 | 2017-08-29 | 2017-11-15 | 0.536 | 0.536 |  |  | 2017-11-15 |  |  |  |  | 0.46988 | 0.046681 | 0 | 0 | 0.51656 | 0 | 0 | 0 | [12 empty] | 0 | 0.51656 | 0 | 0 | 0.51656 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4686 | 2017-08-29 | 2017-11-15 | 0.93 | 0.93 |  |  | 2017-11-15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | DPR | MERC/CAPEX/20172018/0272 | 2018-01-30 | 2018-02-23 | 15.49 | 15.49 |  |  | 2018-02-23 | [8 empty] | 0 | [19 empty] | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-01-30 | 2018-02-23 | 2.01 | 2.01 |  |  | 2018-02-23 |  |  |  |  | 0 | 0 | 0 | 2.115 | 2.115 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 2.115 | 2.115 | 0 | 0 | 0 | [7 empty] | Capitalised
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-01-30 | 2018-02-23 | 3.34 | 3.34 |  |  | 2018-02-23 |  |  |  |  | 0 | 0 | 0 | 1.9274 | 1.9274 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 1.9274 | 1.9274 | 0 |  | 0 | [7 empty] | Capitalised
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20172018/0272 | 2018-01-30 | 2018-02-23 | 9.02 | 9.02 |  |  | 2018-02-23 |  |  |  |  | 0 | 8.8302 | 0 | 0 | 8.8302 | 0 | 0 | 0 | [12 empty] | 0 | 8.8302 | 0 | 0 | 8.8302 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/0272 | 2018-01-30 | 2018-02-23 | 1.12 | 1.12 |  |  | 2018-02-23 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | DPR | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 128.02 | 117.57 |  |  | 2018-05-18 | [8 empty] | 0 | [19 empty] | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 82.6 | 82.6 |  |  | 2018-05-18 |  |  |  | 1) Increased the structural life of the buildings 2) Maintenance cost of the work is reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. | 0 | 16.099 | 32.3767 | 33.2573 | 81.733 | -4.8009 | 5.3179 | 0.35 | [12 empty] | 0 | 0 | 34.3378 | 39.9811 | 74.3189 | 3.2833 | 4.6478 | 0.35 | [7 empty] | Capitalised
30.2 | Colony Internal Roads at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 7.08 | 7.08 |  |  | 2018-05-18 |  |  |  | 1) Available good riding surface for traffic movement 2)Smooth traffic movememnt is achieved. 3) maintenance cost of road is reduced. 4) No need to carry out same work again and again 5) Possibility of accidents is reduced by providing the road furniture. 6) The above scheme is not related to the generation and it related to provide the services to the employees. | 0 | 0 | 0.59821 | 7.1999 | 7.7981 | -1.4528 | 0.034842 | 0.6998 | [12 empty] | 0 | 0 | 0 | 5.837 | 5.837 | 0.5084 | 0.034842 | 0.6998 | [7 empty] | Capitalised
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 9.44 | 4.72 |  |  | 2018-05-18 |  |  |  | 1) Creates a healty atmosphere in colony 2) Same place utilised for gardening and entertainment 3) Maintains the good enviornment in colony 4) The above scheme is not related to the generation and it related to provide the services to the employees | 0 | 0 | 0 | 0 | 0 | 0 | 4.1941 | 0.52593 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4.1941 | 0.52593 | [7 empty] | WIP
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | Scheme | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 18.88 | 15.34 |  |  | 2018-05-18 |  |  |  | 1) The said scheme is not related to the generation and it related to provide the services to the employees. | 0.12349 | 0.27255 | 0.093497 | 0 | 0.48954 | 1.1378 | 3.6196 | 2.1 | 7.993 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1.6273 | 3.0375 | 2.1 | 8.5751 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/20182019/0644 | 2018-02-15 | 2018-05-18 | 10.02 | 7.83 |  |  | 2018-05-18 | [5 empty] | 0 | 0 | 0 | 0 | 5.4274 | 5.513 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 5.4274 | 5.513 | 0
31 | Fully Integrated Security Surveillance System | DPR | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 76.4286 | 76.41 |  |  | 2019-03-05 | [8 empty] | 0 | [19 empty] | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 24.0248 | 24.03 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.03 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.03 | [5 empty] | Proposal stg | WIP
31.2 | FIRE ALARM SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 4.3306 | 4.33 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.33 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.33 | [5 empty] | Proposal stg | WIP
31.3 | ACCESS CONTROL SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 0.4838 | 0.48 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | [5 empty] | Proposal stg | WIP
31.4 | EPABX | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 1.9234 | 1.93 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.93 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.93 | [5 empty] | Proposal stg | WIP
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 1.7582 | 1.76 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | [5 empty] | Proposal stg | WIP
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 1.2508 | 1.25 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | [5 empty] | Proposal stg | WIP
31.7 | NETWORKING | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 9.3574 | 9.35 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | [5 empty] | Proposal stg | WIP
31.8 | MESSAGE DISPLAY SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 0.3186 | 0.31 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31 | [5 empty] | Proposal stg | WIP
31.9 | IP PA SYSTEM | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 2.7494 | 2.74 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.74 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.74 | [5 empty] | Proposal stg | WIP
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 7.6346 | 7.63 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.63 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.63 | [5 empty] | Proposal stg | WIP
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 18.6676 | 18.67 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.67 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.67 | [5 empty] | Proposal stg | WIP
31.12 | ADDITIONAL CIVIL WORK | Scheme | MERC/CAPEX/2018-19/066 | 2018-06-06 | 2019-03-05 | 3.9294 | 3.93 |  |  | 2019-03-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | [5 empty] | Proposal stg | WIP
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | DPR | MERC/CAPEX/20182019/1240 | 2018-07-10 | 2018-09-20 | 38.64 | 38.63 |  |  | 2018-09-20 | [8 empty] | 0 | [19 empty] | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | Scheme | MERC/CAPEX/20182019/1240 | 2018-07-10 | 2018-09-20 | 32.56 | 32.56 |  |  | 2018-09-20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 29.2133 | -0.010019 | 3.3568 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1.7134 | 30.8466 | [6 empty] | Proposal stg | WIP
32.2 | Automation of Control Room of CHP-B Using PLC System | Scheme | MERC/CAPEX/20182019/1240 | 2018-07-10 | 2018-09-20 | 4.92 | 4.91 |  |  | 2018-09-20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |  |  |  |  | Proposal stg | WIP
| IDC | IDC | MERC/CAPEX/20182019/1240 | 2018-07-10 | 2018-09-20 | 1.16 | 1.16 |  |  | 2018-09-20 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | DPR | MERC/CAPEX/2019-2020/362 | 2018-12-17 | 2019-07-11 | 15.8738 | 15.2203 |  |  | 2019-07-11 | [8 empty] | 0 | [19 empty] | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | Scheme | MERC/CAPEX/2019-2020/362 | 2018-12-17 | 2019-07-11 | 14.2003 | 14.2003 |  |  | 2019-07-11 |  |  |  | As the scheme is not related to generation, the cost benefit may not be analysed. However, by implementing the scheme, following benefits will be achieved. 1. Shunting time will be reduce and will result in reduction in rake detention time. 2. Reduction in damurrages charges. 3. Derailments due to poor rail structure will be reduced. 4. Reduction in maintenance cost. |  | 0 | 0 | 0 | 0 | 0 | 1.4649 | 15.4351 | [13 empty] | 0 | 0 | 0 | 0 | 0 |  | 16.9 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2019-2020/362 | 2018-12-17 | 2019-07-11 | 1.6736 | 1.02 |  |  | 2019-07-11 | [8 empty] | 0 | [19 empty] | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | DPR | MERC/CAPEX/2019-2020/129 | 2019-04-03 | 2019-05-03 | 41.4691 | 41.4691 |  |  | 2019-05-03 | [8 empty] | 0 | [19 empty] | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | Scheme | MERC/CAPEX/2019-2020/129 | 2019-04-03 | 2019-05-03 | 40.3591 | 40.3591 |  |  | 2019-05-03 |  |  |  |  | 0 | 0 | 0 | 1.0992 | 1.0992 | 41.0903 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0.826 | 0.826 | 41.3636 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/129 | 2019-04-03 | 2019-05-03 | 1.11 | 1.11 |  |  | 2019-05-03 | [8 empty] | 0 | [19 empty] | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | DPR | MERC/CAPEX/2019-2020/1214 | 2019-08-09 | 2019-12-23 | 22.05 | 22.05 |  |  | 2019-12-23 | [8 empty] | 0 | [19 empty] | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | Scheme | MERC/CAPEX/2019-2020/1214 | 2019-08-09 | 2019-12-23 | 21.66 | 21.66 |  |  | 2019-12-23 | [5 empty] | 0 | 0 | 22.8548 | 22.8548 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 22.8548 | 22.8548 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/1214 | 2019-08-09 | 2019-12-23 | 0.39 | 0.39 |  |  | 2019-12-23 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | DPR | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2019-10-14 | 2020-09-30 | 18.56 | 18.56 |  |  | 2020-09-30 | [8 empty] | 0 | [19 empty] | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2019-10-14 | 2020-09-30 | 18.32 | 18.32 |  |  | 2020-09-30 | [5 empty] | 0 | 0 | 8.8348 | 8.8348 | 7.3896 | 0.54562 | 1.55 | [15 empty] | 8.8348 | 8.8348 | 7.3896 |  | 1.0956 | 1 |  |  |  |  | -3.5476 |  | Partially Capitalised
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2019-10-14 | 2020-09-30 | 0.24 | 0.24 |  |  | 2020-09-30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | DPR | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2019-12-09 | 2020-12-14 | 656.25 | 656.25 |  |  | 2020-12-14 | [8 empty] | 0 | [19 empty] | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2019-12-09 | 2020-12-14 | 602.58 | 602.58 |  |  | 2020-12-14 | [5 empty] | 0 | 0 | 0 | 0 |  |  | 179.49 | 658.11 | 358.97 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 179.49 | 658.11 | 358.97 | [5 empty] | To be confirmed
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2019-12-09 | 2020-12-14 | 53.67 | 53.67 |  |  | 2020-12-14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | DPR | MERC/TECH1/CAPEX/20142015/01526 |  | 2015-01-29 | 10 | 10 |  |  | 2015-01-29 | [8 empty] | 0 | [19 empty] | 0
| Replacement of ECO and LTSH coils to Unit-4 Chandrapur | Scheme | MERC/TECH1/CAPEX/20142015/01526 |  | 2015-01-29 | 9.4 | 9.4 |  |  | 2015-01-29 | [8 empty] | 0 |  | 9.3999 | [17 empty] | 0 |  | 9.3999 | [8 empty] | Capitalised |  |  |  | Capitalised | 9.3999 | 9.3999 | 0 | 0 | 0.0001392
| IDC | IDC | MERC/TECH1/CAPEX/20142015/01526 |  | 2015-01-29 | 0.6 | 0.6 |  |  | 2015-01-29 | [8 empty] | 0 | [19 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | DPR | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2020-03-02 | 2021-05-19 | 21.53 | 21.53 |  |  | 2021-05-19 | [8 empty] | 0 | [19 empty] | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2020-03-02 | 2021-05-19 | 21.02 | 21.02 |  |  | 2021-05-19 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9.9521 | 0 | [15 empty] | 0 | 0 | 0 | 9.9521 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2020-03-02 | 2021-05-19 | 0.51 | 0.51 |  |  | 2021-05-19 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | DPR | MERC/CAP/DPR/10/07/1149 | 2007-05-21 | 2007-05-30 | 9.6 | 9.6 |  |  | 2007-05-30 | [8 empty] | 0 | [19 empty] | 0
HO DPR 1.1 | CSTPS U-1,2&4 | Scheme | MERC/CAP/DPR/10/07/1149 | 2007-05-21 | 2007-05-30 | 9.6 | 9.6 |  |  | 2007-05-30 |  |  |  |  | 4.9831 |  |  |  | 4.9831 | [8 empty] | 100% | [6 empty] | 4.9831 |  |  |  | 4.9831 | [10 empty] | Capitalised
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | DPR | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 | 10.36 | 10.36 |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0
HO DPR 4.1 | Chandrapur TPS | Scheme | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 | 10.36 | 10.36 |  |  | 2013-07-09 |  |  |  |  | 0 |  |  |  | 0 | [15 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
| IDC | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-04-18 | 2013-07-09 |  |  |  |  | 2013-07-09 | [8 empty] | 0 | [19 empty] | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | DPR | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 16.956 | 16.956 |  |  | 2014-11-25 | [8 empty] | 0 | [19 empty] | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 5.706 | 5.706 |  |  | 2014-11-25 |  |  |  |  | 0.83245 | 0.074168 | 0 | 0 | 0.90661 | 0 | 0 | 0 | [12 empty] | 0.83245 | 0.074168 | 0 | 0 | 0.90661 | 0 | 0 | 0 | [7 empty] | Capitalised
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | Scheme | MERC/TECH 1/CAPEX/20142015/01218 | 2014-10-01 | 2014-11-25 | 11.25 | 11.25 |  |  | 2014-11-25 |  |  |  |  | 0 | 0 | 2.8715 | 2.8827 | 5.7542 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 2.6685 | 3.0857 | 5.7542 | 0 | 0 | 0 | [7 empty] | Capitalised
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 1.3258 | 1.3258 |  |  | 2016-08-03 | [8 empty] | 0 | [19 empty] | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 1.3258 | 1.3258 |  |  | 2016-08-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Cancelled
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 7.0966 | 7.0966 |  |  | 2016-09-30 | [8 empty] | 0 | [19 empty] | 0
HO DPR 7.1 | Chandrapur STPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 7.0966 | 7.0966 |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 7.0966 | [11 empty] | 0 |  |  |  | 0 |  |  |  | 7.0966 | [5 empty] | Proposal stage | Not Initiated
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 4.15 | 4.15 |  |  | 2017-11-13 | [8 empty] | 0 | [19 empty] | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 2.9 | 2.9 |  |  | 2017-11-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.26772 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0.26772 | [9 empty] | Capitalised
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.25 | 1.25 |  |  | 2017-11-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2.1847 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 2.1847 | [9 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 |  |  |  |  | 2017-11-13 | [8 empty] | 0 | [19 empty] | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 9.0742 | 9.0742 |  |  | 2018-02-06 | [8 empty] | 0 | [19 empty] | 0
HO DPR 10.1 | CSTPS Chandrapur | Scheme | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 9.0742 | 9.0742 |  |  | 2018-02-06 |  |  |  |  | 0 | 1.1422 | 2.1163 | 4.4786 | 7.737 | 1.214 | 0.66117 | 0 | [12 empty] | 0 | 0 | 2.1919 | 3.937 | 6.1289 | 2.8222 | 0.66117 | 0 | [7 empty] | Capitalised
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | DPR | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 | 11.13 | 11.13 |  |  | 2019-08-26 | [8 empty] | 0 | [19 empty] | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 | 1.73 | 1.73 |  |  | 2019-08-26 |  |  |  | • Boiler efficiency will be improved. • APH performance will be improved. • Dry flue gas losses will be reduced. • Improved Heat Rate. • Availability and Reliability of unit will be increased | 0 | 0 | 1.696 | 0 | 1.696 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 1.696 | 1.696 | 0 | 0 | 0 | [7 empty] | Capitalised
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 | 9.4 | 9.4 |  |  | 2019-08-26 |  |  |  |  | 0 | 4.4553 | 4.4553 | 0 | 8.9105 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 4.4553 | 4.4553 | 8.9105 | 0 | 0 | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 |  |  |  |  | 2019-08-26 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 3.7552 | 3.7552 |  |  | 2020-10-27 | [8 empty] | 0 | [19 empty] | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 2.9127 | 2.9127 |  |  | 2020-10-27 | [5 empty] | 0 | 0 | 0 | 0 | 2.8883 |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 2.8883 |  | 0 | [7 empty] | Capitalised
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 0.84252 | 0.84252 |  |  | 2020-10-27 | [5 empty] | 0 | 0 | 0 | 0 | 0.84252 |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0.84252 |  | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 0 | 0 |  |  | 2020-10-27 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | DPR | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-01-06 | 2021-06-10 | 10.89 | 10.89 |  |  | 2021-06-10 | [8 empty] | 0 | [19 empty] | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | Scheme | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-01-06 | 2021-06-10 | 6.2 | 6.2 |  |  | 2021-06-10 | [5 empty] | 0 | 0 | 0 | 0 | 6.0121 | 0 | 0 | [16 empty] | 0 | 6.0121 | 0 | 0 | [7 empty] | Capitalised
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | Scheme | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-01-06 | 2021-06-10 | 4.39 | 4.39 |  |  | 2021-06-10 |  |  |  | 1) Improvement in condenser vacuum. 2) Improvement in gross heat rate. 3) Increase in system availability & performance improvement. 4) Increase in heat transfer due to exposure of extra area of hot water to air. 5) L/G ration maintained. |  | 0 | 0 | 0 | 0 | 4.3294 |  | 0 | [16 empty] | 0 | 4.3294 |  | 0 | [7 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-01-06 | 2021-06-10 | 0.3 | 0.3 |  |  | 2021-06-10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/0321 | 2021-01-07 | 2022-07-18 | 14.06 | 14.06 |  |  | 2022-07-18 | [8 empty] | 0 | [19 empty] | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2022-2023/0321 | 2021-01-07 | 2022-07-18 | 6.08 | 6.08 |  |  | 2022-07-18 |  |  |  | a) Revenue Savings : The unit is saved under varying system disturbances b) Fast & efficient response to supply changeover, Safety during transfer c) Increase in efficiency & Life Expectance of Drives and Driven Equipments d) Better event analysis and trouble-shooting capabilities. (Payback period is estimated as Apprx. 3.4 years) |  | 0 | 0 | 0 | 0 | 0 | 3.607 | 2.47 | [16 empty] | 0 | 0 | 3.607 | 2.47 | [6 empty] | Proposal stg | Partially Capitalised
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2022-2023/0321 | 2021-01-07 | 2022-07-18 | 5.28 | 5.28 |  |  | 2022-07-18 |  |  |  | a) System improvement and reliability of critical 220V DC & 24V DC supply schemes. b) Tangible cost saving in terms of reduction in Power consumption and Operational costs. c) Drastic reduction in Battery maintenance. d) Comprehensive Battery System monitoring. e) Prolonged Battery life and improved performance. (Payback period is estimated as Apprx. 3.1 years) |  | 0 | 0 | 0 | 0 |  | 2.709 |  | 2.571 | [15 empty] | 0 | 0 | 2.3456 | 0.36343 | 2.571 | [5 empty] | Proposal stg | Partially Capitalised
41.3 | Generator Protection Scheme U-7 | Scheme | MERC/CAPEX/2022-2023/0321 | 2021-01-07 | 2022-07-18 | 1.98 | 1.98 |  |  | 2022-07-18 |  |  |  | a) Increase in reliability of critical generator protection system. b) Better analytical & diagnostic purpose. c) As history and events logging data is available in relay memory the system shall be very much useful for analysis, in case of unit tripping d) Reduction in repairs of faulty relays. (Payback period is estimated as Apprx. 1 year) |  | 0 | 0 | 0 | 0 | 1.7287 | 0 | 0 | 0.2513 | [15 empty] | 0 | 0 | 0 | 0 | 1.98 | [5 empty] | PO dispatch stg | WIP
| IDC | IDC | MERC/CAPEX/2022-2023/0321 | 2021-01-07 | 2022-07-18 | 0.72 | 0.72 |  |  | 2022-07-18 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | DPR | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 219.44 | 219.44 |  |  | 2022-09-29 | [8 empty] | 0 | [19 empty] | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 207.46 | 207.46 |  |  | 2022-09-29 | [8 empty] | 0 |  |  | 116.38 | 116.38 | 0 | [14 empty] | 0 |  |  | 116.38 | 116.38 | 0 |  |  |  |  | LOA issued | WIP
| IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2021-02-26 | 2022-09-29 | 11.98 | 11.98 |  |  | 2022-09-29 | [8 empty] | 0 | [19 empty] | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | DPR | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2021-03-18 | 2023-09-05 | 115.34 | 115.34 |  |  | 2023-09-05 | [8 empty] | 0 | [19 empty] | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2021-03-18 | 2023-09-05 | 109.4 | 109.4 |  |  | 2023-09-05 | [8 empty] | 0 |  |  | 19.22 | 108.94 | [15 empty] | 0 |  |  | 19.22 | 108.94 | [5 empty] | Proposal stage | Not Initiated
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2021-03-18 | 2023-09-05 | 5.94 | 5.94 |  |  | 2023-09-05 | [8 empty] | 0 | [19 empty] | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/0409 | 2021-08-12 | 2022-09-02 | 33.268 | 33.268 |  |  | 2022-09-02 | [8 empty] | 0 | [19 empty] | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | Scheme | MERC/CAPEX/2022-2023/0409 | 2021-08-12 | 2022-09-02 | 32.568 | 32.568 |  |  | 2022-09-02 |  |  |  | GTR reliability increase. |  | 0 | 0 | 0 | 0 |  |  | 39 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 39 | [6 empty] | Material received | WIP
| IDC | IDC | MERC/CAPEX/2022-2023/0409 | 2021-08-12 | 2022-09-02 | 0.7 | 0.7 |  |  | 2022-09-02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | DPR | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 145.055 | 145.055 |  |  | 2023-09-05 | [8 empty] | 0 | [19 empty] | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 101.8102 | 101.8102 |  |  | 2023-09-05 | [5 empty] | 0 | 0 | 0 | 0 |  | 40.1338 | 26.8099 | [13 empty] | 0 | 0 | 0 | 0 |  | 40.1338 | 26.8099 | [7 empty] | Partially Capitalised
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 1.708 | 1.708 |  |  | 2023-09-05 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 1.1231 | [13 empty] | 0 | 0 | 0 | 0 | 0 |  | 1.1231 | [7 empty] | WIP
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 4.2692 | 4.2692 |  |  | 2023-09-05 | [8 empty] | 0 |  |  | 2.8072 | [16 empty] | 0 |  |  | 2.8072 | [7 empty] | WIP
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | Scheme | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 25.6575 | 25.6575 |  |  | 2023-09-05 | [8 empty] | 0 |  | 0 | 16.8707 | [16 empty] | 0 |  | 0 | 16.8707 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2021-09-03 | 2023-09-05 | 11.61 | 11.61 |  |  | 2023-09-05 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2022-11-16 | 2024-05-17 | 37.3162 | 37.32 |  |  | 2024-05-17 | [8 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0 | [7 empty] | PO dispatch stg
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2022-11-16 | 2024-05-17 | 35.944 |  |  |  | 2024-05-17 |  |  |  | • Reliability and availability of system will be improved. • Increase in energy efficiency due to improved material and manufacturing methods, Thus lower internal losses and additional energy savings. • Lesser maintenance and monitoring costs. • Emergency tendering cost in case of failure of existing BCW motor will be minimised |  |  |  |  | 0 |  | 0 |  | 35.944 | [15 empty] | 0 |  | 0 |  | 35.944 | [6 empty] | WIP
| IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2022-11-16 | 2024-05-17 | 1.3722 |  |  |  | - | [8 empty] | 0 |  | 0 | 0 | [10 empty] | 0 | 0 |  |  |  |  | 0 |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | DPR | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 43.01 | 43.01 |  |  | 2023-10-31 | [8 empty] | 0 | [19 empty] | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 5.66 | 5.66 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 5.66 | [16 empty] | 0 |  |  | 5.66
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 8.17 | 8.17 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 8.17 | [16 empty] | 0 |  |  | 8.17
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 4.12 | 4.12 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 4.12 | [16 empty] | 0 |  |  | 4.12
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 3.72 | 3.72 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 3.72 | [16 empty] | 0 |  |  | 3.72
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 3.45 | 3.45 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 3.45 | [16 empty] | 0 |  |  | 3.45
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 4.6 | 4.6 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 4.6 | [16 empty] | 0 |  |  | 4.6
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 8.14 | 8.14 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 8.14 | [16 empty] | 0 |  |  | 8.14
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 4.18 | 4.18 |  |  | 2023-10-31 | [8 empty] | 0 |  |  | 4.18 | [16 empty] | 0 |  |  | 4.18
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-08-31 | 2023-10-31 | 0.97 | 0.97 |  |  | 2023-10-31 | [8 empty] | 0 | [19 empty] | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 |  |  | 2022-02-12 | [8 empty] | 0 | [19 empty] | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 |  |  | 2022-02-12 | [8 empty] | 0 |  |  |  | 27.12 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 27.12
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 |  |  | 2022-02-12 | [8 empty] | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 |  |  | 2023-11-02 | [8 empty] | 0 | [19 empty] | 0
HO DPR 18.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 |  |  | 2023-11-02 | [8 empty] | 0 |  |  |  | 22.003 | 44.006 | [14 empty] | 0 |  |  |  |  | 66.009
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 |  |  | 2023-11-02 | [8 empty] | 0 | [19 empty] | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | DPR | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 104.24 | 81.35 | [11 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0 | [10 empty] | 0 |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 102.92 | 80.15 | [11 empty] | 0 |  | 0 |  | 40.075 | 40.075 | [14 empty] | 0 |  | 0 |  | 40.075 | 40.075 | [6 empty] | 80.15 | 0 | #REF! | 0 | 22.77
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 1.32 | 1.2 | [11 empty] | 0 |  | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | #REF! | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 25.78 | 25.78 | [11 empty] | 0 | [19 empty] | 0 | [14 empty] | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 7.19 | 7.19 | [11 empty] | 0 |  |  |  |  | 7.19 | [14 empty] | 0 |  |  |  |  | 7.19 | [6 empty] | 7.19 |  | #REF! | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 0.8 | 0.8 | [11 empty] | 0 |  |  |  |  | 0.8 | [14 empty] | 0 |  |  |  |  | 0.8 | [6 empty] | 0.8 |  | #REF! | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 2.97 | 2.97 | [11 empty] | 0 |  | 2.9194 | [17 empty] | 0 |  | 2.9194 |  |  | 0 | [6 empty] | 2.9194 |  | #REF! | 0 | 0.050603
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 10.48 | 10.48 | [6 empty] | 1. Cost effective and more efficient 2. Reduces lifts down time and failure. 3. Improved reliability and safety and lower maintenance cost 4. Enhanced appearance and intangible benefits: |  |  |  |  | 0 |  |  |  |  | 10.48 | [14 empty] | 0 |  |  |  |  | 10.48 | [6 empty] | 10.48 |  | #REF! | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | Scheme | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 3.66 | 3.66 | [6 empty] | 1. Cost effective and more efficient 2. Reduces lifts down time and failure. 3. Improved reliability and safety and lower maintenance cost 4. Enhanced appearance and intangible benefits: |  |  |  |  | 0 |  |  |  |  | 3.66 | [14 empty] | 0 |  |  |  |  | 3.66 | [6 empty] | 3.66 |  | #REF! | 0 | 0
| IDC | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 0.68 | 0.68 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | 0 |  | #REF! | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | DPR | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 127.95 | [7 empty] | 1) Water losses will be reduced by providing and laying new pipeline. 2) Irrigation water royalty will be reduced 3) Generation cost will be reduced 4) Scarcity of the water at one day reservoir will be minimised |  |  |  |  | 0 | [19 empty] | 0 | [12 empty] | 0 |  | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 119.12 | [12 empty] | 0 |  |  |  |  | 78.3255 | [14 empty] | 0 |  |  |  |  | 78.3255 | [6 empty] | 78.3255 | 0 | #REF! | -78.3255 | 40.7945
0 | IDC | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-01-31 | 2024-08-06 | 8.83 | [12 empty] | 0 |  | 0 | 0 | [16 empty] | 0 |  |  | 0 | [8 empty] | 0 | 0 | #REF! | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | DPR | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 32.43 | [12 empty] | 0 | [19 empty] | 0 | [14 empty] | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 4.43 | [12 empty] | 0 |  |  |  | 4.43 | [15 empty] | 0 |  |  |  | 4.43 | [7 empty] | 4.43 |  | #REF! | -4.43 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 4.54 | [12 empty] | 0 |  |  |  | 4.54 | [15 empty] | 0 |  |  |  | 4.54 | [7 empty] | 4.54 |  | #REF! | -4.54 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 5.25 | [12 empty] | 0 |  |  |  | 5.25 | [15 empty] | 0 |  |  |  | 5.25 | [7 empty] | 5.25 |  | #REF! | -5.25 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 4.61 | [12 empty] | 0 |  |  |  | 4.61 | [15 empty] | 0 |  |  |  | 4.61 | [7 empty] | 4.61 |  | #REF! | -4.61 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 3.83 | [12 empty] | 0 |  |  |  | 3.83 | [15 empty] | 0 |  |  |  | 3.83 | [7 empty] | 3.83 |  | #REF! | -3.83 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 3.83 | [12 empty] | 0 |  |  |  | 3.83 | [15 empty] | 0 |  |  |  | 3.83 | [7 empty] | 3.83 |  | #REF! | -3.83 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | Scheme | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 5.31 | [12 empty] | 0 |  |  |  | 5.31 | [15 empty] | 0 |  |  |  | 5.31 | [7 empty] | 5.31 |  | #REF! | -5.31 | 0
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-04-12 | 2024-08-02 | 0.63 | [12 empty] | 0 | [19 empty] | 0 | [11 empty] | 0 |  | #REF! | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | DPR | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 38.4 | 38.4 | [11 empty] | 0 | [19 empty] | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 9.58 | 9.58 | [11 empty] | 0 |  |  |  | 9.58 | [15 empty] | 0 |  |  |  | 9.58
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 2.95 | 2.95 | [11 empty] | 0 |  |  |  | 2.95 | [15 empty] | 0 |  |  |  | 2.95
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 7.95 | 7.95 | [11 empty] | 0 |  |  |  | 7.95 | [15 empty] | 0 |  |  |  | 7.95
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | Scheme | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 17.46 | 17.46 | [11 empty] | 0 |  |  | 17.46 | [16 empty] | 0 |  |  | 17.46 | 0
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-04-12 | 2024-08-08 | 0.46 | 0.46 | [11 empty] | 0 | [19 empty] | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | DPR | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 |  | 2024-09-09 | 32.55 | 32.55 | [11 empty] | 0 | [19 empty] | 0
| Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | Scheme | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 |  | 2024-09-09 | 17.61 | 17.61 | [11 empty] | 0 |  |  |  |  | 17.61 | [14 empty] | 0 |  |  |  |  | 17.61
| Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | Scheme | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 |  | 2024-09-09 | 14.65 | 14.65 | [11 empty] | 0 |  |  |  |  | 14.65 | [14 empty] | 0 |  |  |  |  | 14.65
| IDC | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 |  | 2024-09-09 | 0.29 | 0.29 | [11 empty] | 0 |  |  |  |  | 0.29 | [14 empty] | 0 |  |  |  |  | 0.29
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0 | [13 empty] | #REF! | #REF!
[19 empty] | 0 | [19 empty] | 0 | [12 empty] | #REF! | #REF! | #REF!
| (ii) Submitted to MERC, Yet To Receive Approval | [17 empty] | 0 | [19 empty] | 0 | [13 empty] | #REF! | #REF!
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | DPR | Yet To Receive Approval |  |  | 34.89 | [12 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Scheme | Yet To Receive Approval |  |  | 13.8 | [12 empty] | 0 |  |  |  |  | 13.8 | [14 empty] | 0 |  |  |  |  | 13.8 | [6 empty] | #REF! | #REF! | 0 | Plant & Machinery | N | Relliabiility
| Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Scheme | Yet To Receive Approval |  |  | 10.19 | [12 empty] | 0 |  |  |  |  | 10.19 | [14 empty] | 0 |  |  |  |  | 10.19 | [6 empty] | #REF! | #REF! | 0 | Plant & Machinery | N | Fire fighting
| Quick Response Vehicle (Multipurpose Fire Tender) | Scheme | Yet To Receive Approval |  |  | 2.55 | [12 empty] | 0 |  |  |  |  | 2.55 | [14 empty] | 0 |  |  |  |  | 2.55 | [6 empty] | #REF! | #REF! | 0 | Plant & Machinery | N | Fire fighting
| High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Scheme | Yet To Receive Approval |  |  | 8.35 | [12 empty] | 0 |  |  |  |  | 8.35 | [14 empty] | 0 |  |  |  |  | 8.35 | [6 empty] | #REF! | #REF! | 0 | Plant & Machinery | N | Fire fighting
| IDC | IDC | Yet To Receive Approval |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0 | Plant & Machinery | N
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | DPR | Yet To Receive Approval |  |  | 23.21 | [12 empty] | 0 | [19 empty] | 0 | [12 empty] | 0 | 0
| Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Scheme | Yet To Receive Approval |  |  | 5.1599 | [7 empty] | a) Ease of maintenance, b) Improved availability and Reliability of the system c) Increased protection to motors and equipment’s. d) The latest breakers being technologically superior to old designed breakers will be more user friendly. e) Reduction in outage hours on account of failure. f) Reduction in maintenance. g) Overall improvement in performance of plant. |  |  |  |  | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [6 empty] | #REF! | #REF! | -1.8401
| Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Scheme | Yet To Receive Approval |  |  | 16.4283 | [12 empty] | 0 |  |  |  |  | 17 | [14 empty] | 0 |  |  |  |  | 17 | [6 empty] | #REF! | #REF! | -0.5717
| IDC | IDC | Yet To Receive Approval |  |  | 1.62 | [12 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | DPR | Yet To Receive Approval |  |  | 31.37 | [12 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Scheme | Yet To Receive Approval |  |  | 11.9 | [12 empty] | 0 |  |  |  | 11.9 | [15 empty] | 0 |  |  |  | 11.9
| Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | IDC | Yet To Receive Approval |  |  | 18.49 | [12 empty] | 0 |  |  |  | 18.49 | [15 empty] | 0 |  |  |  | 18.49
| IDC |  | Yet To Receive Approval |  |  | 0.98 | [12 empty] | 0 | [19 empty] | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | DPR | Yet To Receive Approval |  |  | 26.27 | [12 empty] | 0 | [19 empty] | 0
| Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Scheme | Yet To Receive Approval |  |  | 16.5 | [12 empty] | 0 |  |  |  | 16.5 | [15 empty] | 0 |  |  |  | 16.5
| Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Scheme | Yet To Receive Approval |  |  | 3.05 | [12 empty] | 0 |  |  |  | 3.05 | [15 empty] | 0 |  |  |  | 3.05
| Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Scheme | Yet To Receive Approval |  |  | 2.21 | [12 empty] | 0 |  |  |  | 2.21 | [15 empty] | 0 |  |  |  | 2.21
| Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Scheme | Yet To Receive Approval |  |  | 1.39 | [7 empty] | Improvement of @ 10 Kcal/Kwh in GTHR expected due to improvement in HP / LP Heater efficiency |  |  |  |  | 0 |  |  |  | 1.39 | [15 empty] | 0 |  |  |  | 1.39
| Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Scheme | Yet To Receive Approval |  |  | 1.95 | [12 empty] | 0 |  |  |  | 1.95 | [15 empty] | 0 |  |  |  | 1.95
| IDC | IDC | Yet To Receive Approval |  |  | 1.17 | [12 empty] | 0 | [19 empty] | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | DPR | Yet To Receive Approval |  |  | 30.36 | [12 empty] | 0 | [19 empty] | 0
| Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Scheme | Yet To Receive Approval |  |  | 4.15 | [7 empty] | a) Availability of ESP Fields shall be enhanced. b) Reduction in stack emission levels. c) Improvement in ambient air quality. Maintaining MPCB environmental norms d) Facilitating adherence to statutory environmental norms and parameters. e) Reduction in failure of electronic cards and components. |  |  |  |  | 0 |  |  |  | 4.15 | [15 empty] | 0 |  |  |  | 4.15
| Scheme-2: Supply and installation of DAVR at U-5,6,7 | Scheme | Yet To Receive Approval |  |  | 6.07 | [7 empty] | a) Reliability of the critical excitation system. b) Improvement in efficiency of the critical excitation system. c) Fine precision control of the critical excitation system. d) Accurate analysis and trouble shooting of the system. e) Better monitoring and supervision of the critical excitation system. (Payback period is estimated as 3 years) |  |  |  |  | 0 |  |  |  | 6.07 | [15 empty] | 0 |  |  |  | 6.07
| Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Scheme | Yet To Receive Approval |  |  | 9.01 | [7 empty] | a) Increase in reliability of critical HT switchgear protection system. b) Better analytical & diagnostic purpose. c) As history and events logging data is available in relay memory the system shall be very much useful for analysis, in case of feeder tripping. d) Reduction in repairs of faulty relays. (Payback period is estimated as 2 years) |  |  |  |  | 0 |  |  |  | 9.01 | [15 empty] | 0 |  |  |  | 9.01
| Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Scheme | Yet To Receive Approval |  |  | 9.86 | [7 empty] | a) Precise light weight mechanical movement. b) Wide Operating temperature range suitable for toughest industrial environments. c) Anti jamming pulsation action via dither signal from electronic positioner (RK/LK) . d) Easy to remove from actuator and re-install when unit is not in service. e) Reliable electro-hydraulic mechanism for holding the actuator at its last position in case of loss of hydraulic pressure or electric power. (Payback period is estimated as 1.5 years) |  |  |  |  | 0 |  |  |  | 9.86 | [15 empty] | 0 |  |  |  | 9.86
| IDC | IDC | Yet To Receive Approval |  |  | 1.26 | [12 empty] | 0 | [19 empty] | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | DPR | Yet To Receive Approval |  |  | 26.87 | [12 empty] | 0 | [19 empty] | 0
| Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Scheme | Yet To Receive Approval |  |  | 24.96 | [12 empty] | 0 |  |  |  | 24.96 | [15 empty] | 0 |  |  |  | 24.96
| IDC | IDC | Yet To Receive Approval |  |  | 1.91 | [12 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
[19 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
[19 empty] | 0 | [19 empty] | 0 | [12 empty] | #REF! | #REF! | #REF!
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A. |  | #REF! | #REF! | #REF!
[19 empty] | 0 | [19 empty] | 0 | [12 empty] | #REF! | #REF! | #REF!
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | DPR |  |  |  |  | 118.75 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | Scheme |  |  |  |  | 118.75 | [11 empty] | 0 |  |  |  |  | 118.75 | [14 empty] | 0 |  |  |  |  | 118.75 | [6 empty] | #REF! | #REF! | -118.75 | Plant & Machinery | N | Fire fighting
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | DPR |  |  |  |  | 31.56 | [11 empty] | 0 | [19 empty] | 0
| DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | Scheme |  |  |  |  | 31.56 | [11 empty] | 0 |  |  |  |  | 31.56 | [14 empty] | 0 |  |  |  |  | 31.56 | [9 empty] | Plant & Machinery | N | Fire fighting
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | DPR |  |  |  |  | 35 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | Scheme |  |  |  |  | 35 | [11 empty] | 0 |  |  |  |  | 35 | [14 empty] | 0 |  |  |  |  | 35 | [6 empty] | #REF! | #REF! | -35 | Plant & Machinery | N | CHP
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | DPR |  |  |  |  | 41.24 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | Scheme |  |  |  |  | 5.42 | [11 empty] | 0 |  |  |  | 5.42 | [15 empty] | 0 |  |  |  | 5.42 | [7 empty] | #REF! | #REF! | -5.42 | Plant & Machinery | N | Civil
| Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | Scheme |  |  |  |  | 35.82 | [11 empty] | 0 |  |  |  | 35.82 | [15 empty] | 0 |  |  |  | 35.82 | [7 empty] | #REF! | #REF! | -35.82 | Plant & Machinery | N | Civil
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | DPR |  |  |  |  | 33.47 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | Scheme |  |  |  |  | 33.47 | [11 empty] | 0 |  |  |  | 5 | 28.47 | [14 empty] | 0 |  |  |  | 5 | 28.47 | [6 empty] | #REF! | #REF! | -33.47 | Plant & Machinery | N | Civil
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | DPR |  |  |  |  | 71.5 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | Scheme |  |  |  |  | 71.5 | [11 empty] | 0 |  |  |  | 15.5 | 56 | [14 empty] | 0 |  |  |  | 15.5 | 56 | [6 empty] | #REF! | #REF! | -71.5 | Plant & Machinery | N | Civil
| Boiler Maintenance-I | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | DPR for Coal mill improvement | DPR |  |  |  |  | 54.74 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | Scheme |  |  |  |  | 18.74 | [6 empty] | •Coal mill availability will be increased. •Coal reject from coal mill will be reduced. •Coal powder fineness will be increased. •Combustion efficiency will be improved. •More than 70% of -200 mesh & less than 1% of +50 mesh •Unburnt fly ash and in bottom ash will be reduced. •Huge Generation loss and specific oil consumptions on account of non-availability of coal mill will be reduced. •Auxiliary power consumption will be saved, as repeated changeover of mill will be reduced. •Increase in loadability of unit. •Maintenance cost of coal mill will be reduced. •Reduce coal mill down time. •Boiler efficiency will be improved. •Availability and Reliability of unit will be increased. |  |  |  |  | 0 |  |  |  | 18.74 | [15 empty] | 0 |  |  |  | 18.74 | [7 empty] | #REF! | #REF! | -18.74 | Plant & Machinery | N | Loadability
| Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | Scheme |  |  |  |  | 36 | [6 empty] | Improve availability of Coal feeders in rainy seasons . Reduce down time of Coal feeders. |  |  |  |  | 0 |  |  |  | 12 | 12 | 12 | [13 empty] | 0 |  |  |  | 12 | 12 | 12 | [5 empty] | #REF! | #REF! | -24 | Plant & Machinery | N | Loadability
2 | DPR for APH basket, HRH coil and Valves | DPR |  |  |  |  | 28.94 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | Scheme |  |  |  |  | 4.94 | [6 empty] | • Boiler efficiency will be improved. • APH performance will be improved. • Dry flue gas losses will be reduced. • Improved Heat Rate. • Availability and Reliability of unit will be increased |  |  |  |  | 0 |  |  |  | 4.94 | [15 empty] | 0 |  |  |  | 4.94 | [7 empty] | #REF! | #REF! | -4.94 | Plant & Machinery | N | Loadability
| Procurement & replacement of complete HRH coils assembly in U#4 | Scheme |  |  |  |  | 24 | [6 empty] | 1.Reduce BTL 2.Boiler efficiency will be improved. 3.Availability and Reliability of unit will be increased |  |  |  |  | 0 |  |  |  |  | 24 | [14 empty] | 0 |  |  |  |  | 24 | [6 empty] | #REF! | #REF! | -24 | Plant & Machinery | N | Loadability
3 | DPR for ESP internal and CRH coil | DPR |  |  |  |  | 45 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Replacement of complete internals of ESP U#3&4 | Scheme |  |  |  |  | 20 | [6 empty] | • Reduction in stack loss • Increase in life of equipment • Achievement in statutory requirement as per MPCB norms |  |  |  |  | 0 |  |  |  |  | 20 | [14 empty] | 0 |  |  |  |  | 20 | [6 empty] | #REF! | #REF! | -20 | Plant & Machinery | N | Loadability
| Procurement & replacement of CRH coil assemblies in U#3 | Scheme |  |  |  |  | 25 | [6 empty] | 1.Reduce BTL 2.Boiler efficiency will be improved. 3.Availability and Reliability of unit will be increased" |  |  |  |  | 0 |  |  |  |  | 25 | [14 empty] | 0 |  |  |  |  | 25 | [6 empty] | #REF! | #REF! | -25 | Plant & Machinery | N | Loadability
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | Scheme |  |  |  |  | 30 | [6 empty] | 1.Reduce BTL 2.Boiler efficiency will be improved. 3.Availability and Reliability of unit will be increased" |  |  |  |  | 0 |  |  |  |  | 30 | [14 empty] | 0 |  |  |  |  | 30 | [6 empty] | #REF! | #REF! | -30 | Plant & Machinery | N | Loadability
| Turbine Maintenance-I | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | DPR |  |  |  |  | 35 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Condenser vaccuum system improvement | Scheme |  |  |  |  | 16 | [6 empty] | 1. The steam required in the ejector will be eliminated. 2. Improvement in the heat rate gain. 3. Overall cycle efficiency will improve. 4. The rated condenser vacuum can be maintained at rated load 5. Vacuum build up fast during rolling reduces time required for set synchronization |  |  |  |  | 0 |  |  |  | 16 | [15 empty] | 0 |  |  |  | 16 | [7 empty] | #REF! | #REF! | -16 | Plant & Machinery | N | Loadability
| Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | Scheme |  |  |  |  | 19 | [6 empty] | 1. Increase in pump efficiency. 2. Readily availability of spare assembly for urgent replacement during emergent situations. 3. Generation Loss due to unpredicted failure/tripping of BFP shall be reduced. 4. Boiler Feed Pump availability will be maintained. 5. Reliability of operation of Units on low loads will be improved. |  |  |  |  | 0 |  |  |  | 19 | [15 empty] | 0 |  |  |  | 19 | [7 empty] | #REF! | #REF! | -19 | Plant & Machinery | N | Relliabiility
2 | WTP-I improvement schemes | DPR |  |  |  |  | 26 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | Scheme |  |  |  |  | 6 | [6 empty] | 1. Reduction auxiliary consumption. 2. No drop in capacity & loss of efficiency. 3. Less floor area for installation and decrease in noise level. 4. Maintenance time is very low in comparison with reciprocating compressor 5. Reduction in lubricating oil consumption. 6. Reduction in inventory. 7. Improvement in availability of compressor for instrumentation purpose |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [6 empty] | #REF! | #REF! | -6 | Plant & Machinery | N
| Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | Scheme |  |  |  |  | 10 | [6 empty] | 1. Refurbishment of existing Hydrogen compressors will keep the plant in healthy condition. 2. In house production of hydrogen cylinder will increase. 3. Breakdown occurrences will get reduce so breakdown time will minimize. 4. Unforeseen emergency due to non-availability of hydrogen cylinders will get minimized 5. Dependency on externally purchase H2 cylinder will reduce |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [6 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
| Replacement of Circulating water pumps in Unit 3 & 4 | Scheme |  |  |  |  | 10 | [6 empty] | 1. Improvement in condenser vacuum 2. Improvement in gross heat rate. 3. Increase in life of equipment’s. 4. Increase in system availability & performance improvement. 5. To retain and sustain the performance of cooling tower. 6. Reduction in auxiliary power consumption. 7. Reduction in breakdown. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [6 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
3 | Procurment of HP valves, CEP Cartridge, GS pump | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of HP valves for Unit 3 & 4 | Scheme |  |  |  |  | 15 | [6 empty] | 1. Increase reability & availability of system. 2. Perfect isolation and easy operation during running of plant. 3. Prevention of heat loss due leakage & passing of valve will be prevented 4. Improved heat rate of system 5. Increase life of system 6. Reduction in frequent maintenance of valves. |  |  |  |  | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [6 empty] | #REF! | #REF! | -15 | Plant & Machinery | N
| Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | Scheme |  |  |  |  | 5 | [6 empty] | 1. Increase pump efficiency. 2. Improvement in reliability & availability of system 3. Increase in life of equipment’s. 4. Increase in system performance improvement. 5. Reduction in auxiliary power consumption. 6. Reduction in breakdown |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [6 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
| Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | Scheme |  |  |  |  | 5 | [6 empty] | 1. Improved efficiency of pump. 2. Improved reliability and availability of GS water system 3. Increase in life of equipment’s. 4. Increase in performance improvement and efficiency of pumps. 5. Reduction in auxiliary power consumption. 6. Reduction in breakdown. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [6 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
| Electrical maintenance -I | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | DPR |  |  |  |  | 47.3 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Colony electrical renovation | Scheme |  |  |  |  | 47.3 | [6 empty] | Existing electrical wiring provided for colny are old type and installed since commissioning. By replacing the same with copper wire, 1) corrosion, sparking, discontinuation of supply and short circuit problems can be avoided. 2) Safety of residents and equipment will improve. |  |  |  |  | 0 |  |  |  | 7.3 | 10 | 10 | 10 | 10 | [11 empty] | 0 |  |  |  | 7.3 | 10 | 10 | 10 | 10 |  |  |  | #REF! | #REF! | -17.3 | Plant & Machinery | N
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | DPR |  |  |  |  | 25.68 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Electrification and illumination of perimeter wall CSTPS, Chandapur | Scheme |  |  |  |  | 12.52 | [6 empty] | As per IB Recommendation, it is proposed to provide Electrification and illumination to perimeter wall of CSTPS, Chandrapur |  |  |  |  | 0 |  |  |  | 12.52 | [15 empty] | 0 |  |  |  | 12.52 | [7 empty] | #REF! | #REF! | -12.52 | Plant & Machinery | N
| Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | Scheme |  |  |  |  | 12.35 | [6 empty] | 1) Proper electric power distribution will take place. 2) ease of maintenance 3) supply isolation during fault will be easier. 4) Due to replacement, rating of distribution boards will be increased. 5) flashover will be avoided. 6) reptiles and birds will not enters inside the boards. 7) fault can be isolated without secondary damages. 8) frequent failure of supply can be avoided. 9) Reliable and uninterruptable electric power supply can be provided to residential of Urjanagar colony. |  |  |  |  | 0 |  |  |  | 2 | 4.35 | 1 | 5 | [12 empty] | 0 |  |  |  | 2 | 4.35 | 1 | 5 |  |  |  |  | #REF! | #REF! | -6.35 | Plant & Machinery | N
| Replacement of Energy meter | Scheme |  |  |  |  | 0.81 | [6 empty] | Existing Energy meters are of old technology, analog type and installed since commissioning of plant. By replacing old energy meter by latest technology electronic energy meter, Following benifits will be added. 1) Accurate measurement of electrical power consumption. 2) Easy to calibrate 3) Power theft can be avoided. 4) Spares and services will be made available from manufacturers for at least next 15 to 20 years. 5) Safety of working staff and equipment will improve. 6) The system will be reliable, ease of maintenance and reduction in maintenance cost. |  |  |  |  | 0 |  |  |  | 0.81 | [15 empty] | 0 |  |  |  | 0.81 | [7 empty] | #REF! | #REF! | -0.81 | Plant & Machinery | N
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | DPR |  |  |  |  | 29 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | Scheme |  |  |  |  | 14 | [6 empty] | The life of existing battery set is exhausted and completed its useful service life. By replacing old batteries & its charger, Following benifits will be added. 1)It improve the reliability and performance of the system. 2) Secondary damages will be avoides to Turbine and Boiler side auxillaries during AC failure 3)Availability will increase and breakdown will reduce. 4)Unit availability will increase due to improved reliability of the D.C. Power Supply, resulting in Grid stability. 5) Service reliability will increase due to assured backup in case of emergency. 6) Healthy battery backup will be provided to DC auxiliaries and equipment in the event of AC failure. 7) Maintenance of battery sets and chargers will be reduced. Maintenance cost will save in the long run. 8) Availability of battery set during AC failure will reduce failure of critical auxiliaries & avoid generation loss. 9) Major Outage and generation loss can be avoided due to availability of Battery charger. 10) Spares and services will be made available from manufacturers for at least next 15 to 20 years. 11) Safety of working staff and equipment will improve. 12) The system will be reliable, ease of maintenance and reduction in maintenance cost. |  |  |  |  | 0 |  |  |  | 14 | [15 empty] | 0 |  |  |  | 14 | [7 empty] | #REF! | #REF! | -14 | Batteries | N
| Retrofitting of Breakers | Scheme |  |  |  |  | 6.8 | [6 empty] | Maintenance of existing breakers (Air Blast Circuit Breakers) due to ageing and non-availability of spares is getting dificult. To cope up with this problems and for smooth running of the plant, it is necessary to retrofit existing breaker of old type with the latest technology (SF6 Gas or Vacuum) which are having high switching rates and greater mechanical endurance where frequent ON/OFF of the motors are carried out. |  |  |  |  | 0 |  |  |  | 1.1 | 5.7 | [14 empty] | 0 |  |  |  | 1.1 | 5.7 | [6 empty] | #REF! | #REF! | -6.8 | Plant & Machinery | N
| supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | Scheme |  |  |  |  | 1.8 | [6 empty] | 1) VFD will reduce auxiliary power consumption ( APC ) and it will help to achive MERC APC parameter and to acheive Zero Disallowance. 2) Improve Reliability and availability |  |  |  |  | 0 |  |  |  |  | 1.8 | [14 empty] | 0 |  |  |  |  | 1.8 | [6 empty] | #REF! | #REF! | -1.8 | Plant & Machinery | N
| Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | Scheme |  |  |  |  | 6.4 | [11 empty] | 0 |  |  |  | 1.4 | 5 | [14 empty] | 0 |  |  |  | 1.4 | 5 | [6 empty] | #REF! | #REF! | -6.4 | Plant & Machinery | N
| TIC | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | DPR |  |  |  |  | 48.608 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | Scheme |  |  |  |  | 48.608 | [6 empty] | 1.Improved System availability 2.1% RoE for FGMO implementation. 3.Quick analysis of operational disturbance and implementation of corrective action. 4.Improved plant efficiency. |  |  |  |  | 0 |  |  |  |  | 24.304 | 24.304 | [13 empty] | 0 |  |  |  |  | 24.304 | 24.304 | [5 empty] | #REF! | #REF! | -24.304 | Plant & Machinery | N
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | DPR |  |  |  |  | 25.39 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | Scheme |  |  |  |  | 6 | [6 empty] | 1.Improved System availability 2.Quick analysis of operational disturbance and implementation of corrective action. 3.Improved plant efficiency. |  |  |  |  | 0 | [6 empty] | 3 | 3 | [11 empty] | 0 | [6 empty] | 3 | 3 |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | Scheme |  |  |  |  | 3.89 | [6 empty] | 1.Improved System availability 2.Quick analysis of operational disturbance and implementation of corrective action. 3.Improved plant efficiency. |  |  |  |  | 0 |  |  |  |  | 3.89 | [14 empty] | 0 |  |  |  |  | 3.89 | [6 empty] | #REF! | #REF! | -3.89 | Plant & Machinery | N
| Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | Scheme |  |  |  |  | 3 | [6 empty] | System Reliability , Accurate Monitoring and Control. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [6 empty] | #REF! | #REF! | -3 | Plant & Machinery | N
| Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | Scheme |  |  |  |  | 3.5 | [6 empty] | 1.Improved System availability 2.Quick analysis of operational disturbance and implementation of corrective action. 3.Improved plant efficiency. |  |  |  |  | 0 | [5 empty] | 3.5 | [13 empty] | 0 | [5 empty] | 3.5 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | Scheme |  |  |  |  | 3 | [6 empty] | 1.Improved System availability 2.Quick analysis of operational disturbance and implementation of corrective action. 3.Improved plant efficiency. |  |  |  |  | 0 | [5 empty] | 3 | [13 empty] | 0 | [5 empty] | 3 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | Scheme |  |  |  |  | 3 | [6 empty] | System Reliability , Accurate Monitoring and Control. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [6 empty] | #REF! | #REF! | -3 | Plant & Machinery | N
| Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | Scheme |  |  |  |  | 3 | [6 empty] | System Reliability , Accurate Monitoring and Control. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [6 empty] | #REF! | #REF! | -3 | Plant & Machinery | N
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | Scheme |  |  |  |  | 30 | [6 empty] | System Reliability , Accurate Monitoring and Control. |  |  |  |  | 0 | [6 empty] | 30 | [12 empty] | 0 | [6 empty] | 30 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | Scheme |  |  |  |  | 60 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | Scheme |  |  |  |  | 60 | [11 empty] | 0 | [7 empty] | 60 | [11 empty] | 0 | [7 empty] | 60 |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
5 | Rejuvenation of WTP-I | DPR |  |  |  |  | 26.4 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | Scheme |  |  |  |  | 8.2 | [11 empty] | 0 | [6 empty] | 8.2 | [12 empty] | 0 | [6 empty] | 8.2 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | Scheme |  |  |  |  | 2.45 | [11 empty] | 0 | [6 empty] | 2.45 | [12 empty] | 0 | [6 empty] | 2.45 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | Scheme |  |  |  |  | 15.75 | [11 empty] | 0 | [6 empty] | 15.75 | [12 empty] | 0 | [6 empty] | 15.75 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| CHP-A | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | DPR |  |  |  |  | 58 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | Scheme |  |  |  |  | 38 | [6 empty] | Rake movement will increase which in turn demmurages will reduced |  |  |  |  | 0 |  |  |  | 38 | [15 empty] | 0 |  |  |  | 38 | [7 empty] | #REF! | #REF! | -38 | Vehicles | N
| Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | Scheme |  |  |  |  | 15 | [6 empty] | Rake unloading time will decreases and no of unloading of rake will increases.Hence,demmurages will decreases |  |  |  |  | 0 |  |  |  | 15 | [15 empty] | 0 |  |  |  | 15 | [7 empty] | #REF! | #REF! | -15 | Plant & Machinery | N
| Installation of Dust Extraction system at Bunker and SCR buildings | Scheme |  |  |  |  | 5 | [6 empty] | Dust emmision will reduced |  |  |  |  | 0 |  |  |  | 5 | [15 empty] | 0 |  |  |  | 5 | [7 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | DPR |  |  |  |  | 33 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | Scheme |  |  |  |  | 12 | [6 empty] | Due to suddenly decrease in width of conveyor from 1200 to 1000 mm ,we have to run said conveyor on less load.Hence, coal bunkering and receipt will decreases .Also, cosumption is also decresed |  |  |  |  | 0 |  |  |  |  | 12 | [14 empty] | 0 |  |  |  |  | 12 | [6 empty] | #REF! | #REF! | -12 | Plant & Machinery | N
| Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | Scheme |  |  |  |  | 10 | [6 empty] | Coal receipt through ARW system will increase. |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [6 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
| Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | Scheme |  |  |  |  | 5.5 | [6 empty] | Coal bunkering will be increased. |  |  |  |  | 0 |  |  |  |  | 5.5 | [14 empty] | 0 |  |  |  |  | 5.5 | [6 empty] | #REF! | #REF! | -5.5 | Plant & Machinery | N
| Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | Scheme |  |  |  |  | 5.5 | [6 empty] | Coal rake unloading will be increased |  |  |  |  | 0 |  |  |  |  | 5.5 | [14 empty] | 0 |  |  |  |  | 5.5 | [6 empty] | #REF! | #REF! | -5.5 | Plant & Machinery | N
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | DPR |  |  |  |  | 32 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of 4 Numbers Bulldozers | Scheme |  |  |  |  | 12 | [6 empty] | Coal loading / bunkering /heap formation will be carried out more efficiently. Existing doxxer completed their useful life and proposed for scrapped. HSD /Lubricant consuption /maintenance cost will be decreased. |  |  |  |  | 0 | [5 empty] | 12 | [13 empty] | 0 | [5 empty] | 12 | [5 empty] | #REF! | 0 | 0 | Vehicles | N
| Procurement of 2 Numbers 800 HP Locomotives | Scheme |  |  |  |  | 9 | [6 empty] | Existiong loco completed their useful lice and proposed to scrapped. Coal rake movement will be carried out smoothly. Demmurage due to rake movment will decrease.HSD /Lubricant consuption /maintenance cost will be decreased. |  |  |  |  | 0 | [5 empty] | 9 | [13 empty] | 0 | [5 empty] | 9 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | Scheme |  |  |  |  | 5 | [6 empty] | Coal bunkering will be increased. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | Scheme |  |  |  |  | 6 | [6 empty] | Coal sampling will be carried out more efficiently. |  |  |  |  | 0 | [6 empty] | 6 | [12 empty] | 0 | [6 empty] | 6 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Boiler Maintenance -II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | DPR |  |  |  |  | 85.69 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | Scheme |  |  |  |  | 85.68 | [11 empty] | 0 |  |  |  | 28.56 | 28.56 | 28.56 | [13 empty] | 0 |  |  |  | 28.56 | 28.56 | 28.56 | [5 empty] | #REF! | #REF! | -57.12 | Plant & Machinery | N
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | DPR |  |  |  |  | 32.28 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | Scheme |  |  |  |  | 32.28 | [11 empty] | 0 |  |  |  | 32.28 | [15 empty] | 0 |  |  |  | 32.28 | [7 empty] | #REF! | #REF! | -32.28 | Plant & Machinery | N
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | Scheme |  |  |  |  | 30 | [11 empty] | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [7 empty] | #REF! | #REF! | -30 | Plant & Machinery | N
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | Scheme |  |  |  |  | 25 | [11 empty] | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [7 empty] | #REF! | #REF! | -25 | Plant & Machinery | N
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | Scheme |  |  |  |  | 25 | [11 empty] | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [7 empty] | #REF! | #REF! | -25 | Plant & Machinery | N
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | DPR |  |  |  |  | 40 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | Scheme |  |  |  |  | 40 | [11 empty] | 0 |  |  |  | 40 | [15 empty] | 0 |  |  |  | 40 | [7 empty] | #REF! | #REF! | -40 | Plant & Machinery | N
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | DPR |  |  |  |  | 40 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | Scheme |  |  |  |  | 40 | [11 empty] | 0 |  |  |  | 40 | [15 empty] | 0 |  |  |  | 40 | [7 empty] | #REF! | #REF! | -40 | Plant & Machinery | N
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | DPR |  |  |  |  | 52 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | Scheme |  |  |  |  | 52 | [11 empty] | 0 |  |  |  | 52 | [15 empty] | 0 |  |  |  | 52 | [7 empty] | #REF! | #REF! | -52 | Plant & Machinery | N
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | Scheme |  |  |  |  | 30 | [11 empty] | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [7 empty] | #REF! | #REF! | -30 | Plant & Machinery | N
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | DPR |  |  |  |  | 52.62 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | Scheme |  |  |  |  | 52.62 | [11 empty] | 0 |  |  |  | 52.62 | [15 empty] | 0 |  |  |  | 52.62 | [7 empty] | #REF! | #REF! | -52.62 | Plant & Machinery | N
| Turbine Maintenance-II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | DPR |  |  |  |  | 25.42 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | Scheme |  |  |  |  | 25.42 | [6 empty] | Achieved improvement in GTHR by @ 48 KCal/KWh & Gross Turbine Efficiency by @ 0.97%. |  |  |  |  | 0 |  |  | 25.42 | [16 empty] | 0 |  |  | 25.42 | [8 empty] | #REF! | #REF! | -25.42 | Plant & Machinery | N
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | Scheme |  |  |  |  | 25 | [6 empty] | Based on Energy Efficiency Calculations expected saving of @ Rs. 41 Lakhs per year. |  |  |  |  | 0 |  |  |  |  | 6.25 | 6.25 | 6.25 | 6.25 | [11 empty] | 0 |  |  |  |  | 6.25 | 6.25 | 6.25 | 6.25 |  |  |  | #REF! | #REF! | -6.25 | Plant & Machinery | N
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | DPR |  |  |  |  | 44.25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | Scheme |  |  |  |  | 7.2 | [6 empty] | Benefits in quantified terms cannot be calculated as spares shall be procured as Insurance spares for emergency replacement thus reducing down time of auxiliary. However, Feed water system improvement & enhancement can be ascertained. As on date, 8.5MW of APC can be saved for each day of reduction in Auxiliary outage. |  |  |  |  | 0 |  |  |  |  | 3.2 |  |  | 4 | [11 empty] | 0 |  |  |  |  | 3.2 |  |  | 4 |  |  |  | #REF! | #REF! | -3.2 | Plant & Machinery | N
| Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | Scheme |  |  |  |  | 11.2 | [11 empty] | 0 |  |  |  |  | 5.2 |  |  | 6 | [11 empty] | 0 |  |  |  |  | 5.2 |  |  | 6 |  |  |  | #REF! | #REF! | -5.2 | Plant & Machinery | N
| Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | Scheme |  |  |  |  | 15.85 | [11 empty] | 0 | [5 empty] | 15.85 | [13 empty] | 0 | [5 empty] | 15.85 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | Scheme |  |  |  |  | 8.5 | [11 empty] | 0 | [6 empty] | 8.5 | [12 empty] | 0 | [6 empty] | 8.5 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | Scheme |  |  |  |  | 1.5 | [11 empty] | 0 |  |  |  |  | 0.75 | 0.75 | [13 empty] | 0 |  |  |  |  | 0.75 | 0.75 | [5 empty] | #REF! | #REF! | -0.75 | Plant & Machinery | N
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | DPR |  |  |  |  | 36.81 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | Scheme |  |  |  |  | 24 | [6 empty] | Benefits cannot be quantified as Critical Turbine spares shall be procured as Insurance spare for replacemet in case of emergency reducing down time of unit. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. |  |  |  |  | 0 |  |  |  |  | 24 | [14 empty] | 0 |  |  |  |  | 24 | [6 empty] | #REF! | #REF! | -24 | Plant & Machinery | N
| Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | Scheme |  |  |  |  | 9.81 | [6 empty] | Quantified benefits cannot be calculated as refurbished HPT module shall be kept as insurance spare ready for replacement in case of urgency. Unit down time shall be reduced. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. |  |  |  |  | 0 |  |  |  | 9.81 | [15 empty] | 0 |  |  |  | 9.81 | [7 empty] | #REF! | #REF! | -9.81 | Plant & Machinery | N
| Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | Scheme |  |  |  |  | 3 | [6 empty] | Benefits cannot be quantified as lube oil system efficiency shall be improved. Old system is out of date & is not having any spare support from manufacturers. |  |  |  |  | 0 |  |  |  |  | 1.5 | 1.5 | [13 empty] | 0 |  |  |  |  | 1.5 | 1.5 | [5 empty] | #REF! | #REF! | -1.5 | Plant & Machinery | N
5 | Reliability improvement of Main Turbine | Scheme |  |  |  |  | 45 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | Scheme |  |  |  |  | 10 | [6 empty] | Benefits cannot be quantified as Critical Turbine spares shall be procured as Insurance spare for replacemet in case of emergency reducing down time of unit. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [7 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
| Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | Scheme |  |  |  |  | 35 | [6 empty] | Benefits cannot be quantified as module shall be procured as Common Pool Insurance spare for replacemet in case of emergency reducing down time of unit. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. |  |  |  |  | 0 |  |  |  | 35 | [15 empty] | 0 |  |  |  | 35 | [7 empty] | #REF! | #REF! | -35 | Plant & Machinery | N
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | DPR |  |  |  |  | 35 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | Scheme |  |  |  |  | 35 | [6 empty] | Benefits cannot be quantified as rotor shall be procured as Insurance spare for replacemet in case of emergency reducing down time of unit. As on date 0.94 Cr. of Fixed cost is saved for each day of reduction in unit outage. |  |  |  |  | 0 | [5 empty] | 35 | [13 empty] | 0 | [5 empty] | 35 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
7 | Energy saving in Air compressors | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | Scheme |  |  |  |  | 30 | [6 empty] | Benifits can be quantified based on Energy Efficiency Calculations. Presently no offer has yet been received. Hence cannot be ascertained. |  |  |  |  | 0 | [7 empty] | 30 | [11 empty] | 0 | [7 empty] | 30 |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | DPR |  |  |  |  | 50 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | Scheme |  |  |  |  | 50 | [6 empty] | Quantified benifits cannot be calculated directly. Indirect benofots include reliability improvement & compliance to stringent Environment norms. |  |  |  |  | 0 | [6 empty] | 25 | 25 | [11 empty] | 0 | [6 empty] | 25 | 25 |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| Electrical Maintenance-II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | DPR |  |  |  |  | 25.07 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | Scheme |  |  |  |  | 15.07 | [6 empty] | • By installing online Dissolved gas analyser, incipient transformer faults can be detected which helps to prevent further damage to GTR. • By replacing OIP Condenser Bushings by Resin Impregnated Polymer (RIP) bushing, bushing oil leakages will be vanish permanently. |  |  |  |  | 0 |  |  |  | 15.07 | [15 empty] | 0 |  |  |  | 15.07 | [7 empty] | #REF! | #REF! | -15.07 | Plant & Machinery | N
| Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | Scheme |  |  |  |  | 10 | [6 empty] | • New UAT in ready replacement form will substantially reduce the generation loss in case of failure Unit Switchgear 6A Incomer-II which is charged from Station board SF13. •Improves reliability of system due to availability of healthy ST-3. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [7 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | DPR |  |  |  |  | 44.31 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | Scheme |  |  |  |  | 44.31 | [6 empty] | a) Reduction in generation loss causes due to frequent failure of motors. b) Ease of maintenance, c) Improved availability and Reliability of the system d) Reduction in Auxiliary power consumption |  |  |  |  | 0 |  |  |  | 44.31 | [15 empty] | 0 |  |  |  | 44.31 | [7 empty] | #REF! | #REF! | -44.31 | Plant & Machinery | N
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | Scheme |  |  |  |  | 25 | [6 empty] | Reduction in Auxiliary power consumption |  |  |  |  | 0 | [7 empty] | 25 | [11 empty] | 0 | [7 empty] | 25 |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | DPR |  |  |  |  | 38 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Complete renovation of Chimney elevator of Unit-5,6,7 | Scheme |  |  |  |  | 10 | [6 empty] | 1)Chimney elaevator reliability incresed. 2)Chimney elaevator maintenance reduced. 3)Inspection, maintenance, calibration and continuous monitoring of emission probes can be done. |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | Scheme |  |  |  |  | 3 | [6 empty] | • By implementing this scheme, the Chimney aviation obstruction light system will remain healthy. • It is mandatory and statutory requirement; also, few governing bodies such as FAA and ICAO are strictly regulating the use, design, and installation of such lighting devices. |  |  |  |  | 0 |  |  |  | 3 | [15 empty] | 0 |  |  |  | 3 | [7 empty] | #REF! | #REF! | -3 | Plant & Machinery | N
| Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | Scheme |  |  |  |  | 25 | [6 empty] | Reliability of power supply to AUNDHA pump house will increase. |  |  |  |  | 0 |  |  |  |  | 25 | [14 empty] | 0 |  |  |  |  | 25 | [6 empty] | #REF! | #REF! | -25 | Plant & Machinery | N
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | DPR |  |  |  |  | 26 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | Scheme |  |  |  |  | 26 | [6 empty] | • APC of Chandrapur TPS in MUs consumed would go down. • The Power Factor would improve to around 0.95 as against 0.84 as of now. • The VFD provides soft start to the pump avoiding starting jerks caused currently. |  |  |  |  | 0 |  |  |  |  | 26 | [14 empty] | 0 |  |  |  |  | 26 | [6 empty] | #REF! | #REF! | -26 | Plant & Machinery | N
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | Scheme |  |  |  |  | 25 | [6 empty] | • APC of Chandrapur TPS in MUs consumed would go down. • The Power Factor would improve to around 0.95 as against 0.84 as of now. • The VFD provides soft start to the pump avoiding starting jerks caused currently. |  |  |  |  | 0 | [5 empty] | 25 | [13 empty] | 0 | [5 empty] | 25 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | Scheme |  |  |  |  | 25 | [6 empty] | Ensure reliability of existing HT & LT boards and also spares availabity. |  |  |  |  | 0 | [6 empty] | 25 | [12 empty] | 0 | [6 empty] | 25 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [14 empty] | Plant & Machinery | N
| Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | Scheme |  |  |  |  | 30 | [6 empty] | Generation loss due to tripping caused by LV bus duct failures will be minimised and ensure availability of UAT, SAT & ST transformers |  |  |  |  | 0 |  |  |  |  | 30 | [14 empty] | 0 |  |  |  |  | 30 | [9 empty] | Plant & Machinery | N
| Instrumentation & Control-II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | Scheme |  |  |  |  | 30 | [11 empty] | 0 |  |  |  | 30 | [15 empty] | 0 |  |  |  | 30 | [7 empty] | #REF! | #REF! | -30 | Plant & Machinery | N
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | DPR |  |  |  |  | 40 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | Scheme |  |  |  |  | 40 | [11 empty] | 0 | [5 empty] | 40 | [13 empty] | 0 | [5 empty] | 40 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | DPR |  |  |  |  | 26.1 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Supply of sub-assy for ID Fan VFD System | Scheme |  |  |  |  | 4.5 | [6 empty] | a) To ensure healthy operation of VFD Channel. b) To reduce cost of repairs of VFD cards |  |  |  |  | 0 |  |  |  |  | 4.5 | [14 empty] | 0 |  |  |  |  | 4.5 | [6 empty] | #REF! | #REF! | -4.5 | Plant & Machinery | N
| Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | Scheme |  |  |  |  | 5.5 | [6 empty] | a) Accurate measurement and continuous monitoring of power consumption and various electrical parameters of all important auxiliaries. b) Specific auxiliary consumption of individual auxiliary is possible with the help of this system which will help to diagnosis condition of auxiliary and for corrective measures accordingly, to avoid secondary damages. c) To optimize energy cost savings by efficiently operating existing equipment and reducing appropriate or premature auxiliary outage. d) Improved budgeting by providing a basis for the more accurate projection of future maintenance of HT auxiliaries. e) As per CPRI recommendation, the energy consumption of various auxiliaries is to be made online for performance monitoring through EMS. |  |  |  |  | 0 |  |  |  |  | 5.5 | [14 empty] | 0 |  |  |  |  | 5.5 | [6 empty] | #REF! | #REF! | -5.5 | Plant & Machinery | N
| Procurement of numerical motor/feeder protection relays | Scheme |  |  |  |  | 8.1 | [6 empty] | a) To ensure reliable and comprehensive electrical protection to critical Supply Boards b) To have an accurate understanding of protection or spurious trippings. |  |  |  |  | 0 |  |  |  |  | 8.1 | [14 empty] | 0 |  |  |  |  | 8.1 | [6 empty] | #REF! | #REF! | -8.1 | Plant & Machinery | N
| Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | Scheme |  |  |  |  | 2 | [6 empty] | a) Multifunction test kits can replace the need for multiple test sets, allowing for more efficient testing. b) Multifunction test kits can be compact and portable, making them easier to move around the lab. c) Multifunction test kits can have an easy-to-use interface that displays only the necessary functionality. |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [6 empty] | #REF! | #REF! | -2 | Plant & Machinery | N
| Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | Scheme |  |  |  |  | 6 | [6 empty] | a) To offer accurate control and positioning. b) energy efficient and can help machines adapt to flexible processes. c) Improved safety & low operation cost |  |  |  |  | 0 | [5 empty] | 6 | [13 empty] | 0 | [5 empty] | 6 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | DPR |  |  |  |  | 26 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | Scheme |  |  |  |  | 9 | [6 empty] | a) Manage, control, visualize, optimize and automate distribution networks from state-wide to city- wide power distribution networks. b) An integrated network model for design, planning, protection, reliability, and operations. c) Intuitive and user-friendly graphical user interface used by Operators, Planning Engineers, Reliability Analysts and Managers. d) Situational Intelligence provides efficient and reliable grid analysis and management during a rapidly changing network state. e) Standardization with the majority of industrial applications and easy integration with legacy and third-party software. (Payback period is estimated as 1 year) |  |  |  |  | 0 | [5 empty] | 9 | [13 empty] | 0 | [5 empty] | 9 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | Scheme |  |  |  |  | 7 | [6 empty] | a) The optimum time to repair or replace pumps. b) Increased reliability through condition monitoring. c) Minimised repair and replacement costs through early detection of mechanical and hydraulic faults. (Scheme is proposed for system improvement only) |  |  |  |  | 0 | [5 empty] | 7 | [13 empty] | 0 | [5 empty] | 7 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | Scheme |  |  |  |  | 4 | [6 empty] | a) Pollution monitoring b) Early warning system c) Air quality monitoring helps local governments stay up-to-date with federal, state, and local regulations related to air quality. |  |  |  |  | 0 |  |  |  |  | 4 | [14 empty] | 0 |  |  |  |  | 4 | [6 empty] | #REF! | #REF! | -4 | Plant & Machinery | N
| Procurement of I&C Testing Labouratory Instruments | Scheme |  |  |  |  | 2 | [6 empty] | a) Improved accuracy in measurements b) Optimized efficiency |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [6 empty] | #REF! | #REF! | -2 | Plant & Machinery | N
| Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | Scheme |  |  |  |  | 4 | [6 empty] | a) To offer accurate control and positioning. b) energy efficient and can help machines adapt to flexible processes. c) Improved safety & low operation cost |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| ODP-II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | DPR |  |  |  |  | 92 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Complete reconditioning of cooling tower 5A & 5B of Unit -5. | Scheme |  |  |  |  | 45 | [6 empty] | • Improvement in condenser vacuum • Improvement in gross heat rate. • Increase in life of equipment’s. • Increase in system availability & performance improvement. • To retain and sustain the performance of cooling tower. • Reduction in auxiliary power consumption. • Reduction in breakdown. |  |  |  |  | 0 |  |  |  | 15 | 15 | 15 | [13 empty] | 0 |  |  |  | 15 | 15 | 15 | [5 empty] | #REF! | #REF! | -30 | Cooling Towers and Circulating Water Systems | N
| Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | Scheme |  |  |  |  | 47 | [6 empty] | • Improvement in condenser vacuum • Improvement in gross heat rate. • Increase in life of equipment’s. • Increase in system availability & performance improvement. • To retain and sustain the performance of cooling tower. • Reduction in auxiliary power consumption. • Reduction in breakdown. |  |  |  |  | 0 |  |  |  |  | 23.5 | 23.5 | [13 empty] | 0 |  |  |  |  | 23.5 | 23.5 | [8 empty] | Cooling Towers and Circulating Water Systems | N
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | DPR |  |  |  |  | 121 | [11 empty] | 0 | [19 empty] | 0 | [14 empty] | Plant & Machinery | N
| Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | Scheme |  |  |  |  | 100 | [6 empty] | • Availability and Reliability of auxiliary / unit will get increased • The availability of spares & outage period will reduce substantially. • Variable Cost: Due to reduction in down time of auxiliary & improvement in Auxiliary Power Consumption, reduction in Variable cost of generation is expected. • Improvement in condenser vacuum • Improvement in gross heat rate. • Increase in life of equipment’s. • Increase in system availability & performance improvement. |  |  |  |  | 0 |  |  |  | 20 | 20 | 20 | 20 | 20 | [11 empty] | 0 |  |  |  | 20 | 20 | 20 | 20 | 20 |  |  |  | #REF! | #REF! | -40 | Plant & Machinery | N
| Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | Scheme |  |  |  |  | 11 | [11 empty] | 0 |  |  |  | 5.5 | 5.5 | [14 empty] | 0 |  |  |  | 5.5 | 5.5 | [6 empty] | #REF! | #REF! | -11 | Plant & Machinery | N
| Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | Scheme |  |  |  |  | 8 | [11 empty] | 0 |  |  |  | 5 | 3 | [14 empty] | 0 |  |  |  | 5 | 3 | [6 empty] | #REF! | #REF! | -8 | Plant & Machinery | N
| Complete reconditioning of Fire fightning system of Stage -I, II, III. | Scheme |  |  |  |  | 2 | [11 empty] | 0 |  |  |  | 2 | [15 empty] | 0 |  |  |  | 2 | [7 empty] | #REF! | #REF! | -2 | Plant & Machinery | N
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | DPR |  |  |  |  | 56 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | Scheme |  |  |  |  | 56 | [6 empty] | • Improvement in quality of DM water. • Achievement in at par Design parameter of DM water. • Increase in life of equipment & DM water system. • Increase in system availability & performance improvement. • User friendly system in operation & maintenance point of view. • Reduction in leakages of acidic & alkaline water so, reduce environmental hazards. • Increase in overhaul plant efficiency. • reduction in secondary damages to boiler & boiler tubes. • Environmental safety to avoid hazards due to acid / alkali. • Decrease the generation cost & also the cost of DM water. |  |  |  |  | 0 |  |  |  | 28 | 28 | [14 empty] | 0 |  |  |  | 28 | 28 | [6 empty] | #REF! | #REF! | -56 | Plant & Machinery | N
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | DPR |  |  |  |  | 58.37 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | Scheme |  |  |  |  | 20.19 | [6 empty] | 1. Ash disposal pipeline outage of U#5 will be minimized. 2. Ash disposal pipeline availability of U#5 will be increased. 3. Maintenance costs will be reduced. 4. by implementing DPR scheme; Environmetal & water pollution will be avoided. 5. Instances of ingress of leaky ash slurry into adjacent fields of farmer and may damage their standing crops will be avoided. 6. Ash Disposal Pipelines choke up will be reduced. 7. After each breakage / leakage of pipelines, flushing is required & hence Auxiliary power consumption for flushing will be reduced. 9.Water consumption will be reduced. 10. Wear and Tear of pumps due to flushing will be reduced |  |  |  |  | 0 |  |  |  | 20.19 | [15 empty] | 0 |  |  |  | 20.19 | [7 empty] | #REF! | #REF! | -20.19 | Plant & Machinery | N
| Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | Scheme |  |  |  |  | 38.18 | [6 empty] | 1. Ash disposal pipeline outage of U#5 & 6will be minimized. 2. Ash disposal pipeline availability will be increased. 3. Maintenance costs will be reduced. 4. Leaky ash may flow in the river through nallahs and may cause water pollution, by implementing DPR scheme; such water pollution will be avoided. 5. Instances of ingress of leaky ash slurry into adjacent fields of farmer and may damage their standing crops will be avoided. 6. Ash Disposal Pipelines choke up will be reduced. 7. Environmental pollution will be avoided. 8. After each breakage / leakage of pipelines, flushing is required & hence Auxiliary power consumption for flushing will be reduced. 9. Water consumption will be reduced. 10. Wear and Tear of pumps due to flushing will be reduced |  |  |  |  | 0 |  |  |  | 18.81 | 19.37 | [14 empty] | 0 |  |  |  | 18.81 | 19.37 | [6 empty] | #REF! | #REF! | -38.18 | Plant & Machinery | N
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | DPR |  |  |  |  | 27.55 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | Scheme |  |  |  |  | 27.55 | [6 empty] | • Existing lines are @ 14-17KM long and disposing the bottom ash in ash bund. The ash bund capacity will be exhausted soon. Hence the capacity of ash bund will be increased by diverting the bottom ash daily @2000MT to the underground mines of Durgapur Rayatwari Colliery (DRC No. 4&5) from unit 5,6&7. • At present in each unit individual lines are kept running for disposing the ash in ash bund. After implementation of this scheme only one series will be kept running, this will save in the auxiliary consumption. • The length of lines will be reduced from 16 KM to 6 KM only, this will reduce the wear & tear of pumps & pipes. • Due to shorten distance series will be run of 3 pumps as the existing series is running on four pumps in series. This will also save the one pump and reduce the consumption of spares. • Yearly requirement of ash pipelines will be reduced. • By implementation of this scheme the MoEFCC norms can be achieved. To minimize air pollution by conveying & storing ash in form of slurry. • The ash management will work more efficiently; hence power generation will enhance. |  |  |  |  | 0 |  |  |  | 17.55 | 10 | [14 empty] | 0 |  |  |  | 17.55 | 10 | [6 empty] | #REF! | #REF! | -27.55 | Plant & Machinery | N
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | DPR |  |  |  |  | 81.06 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | Scheme |  |  |  |  | 81.06 | [6 empty] | 1. Ash disposal pipeline outage will be minimized. 2. Ash disposal pipeline availability will be increased. 3. Maintenance costs will be reduced. 4. Instances of bottom ash ground unloading will be reduced. 5. Generation loss on account of ash slurry disposal pipelines non-availability will be minimized. 6. Water pollution due to the increase of leakage ash in the river through nallahs will be avoided. 7. Ash Disposal Pipelines choke up will be reduced. 8. Environmental pollution will be avoided. 9. After each breakage / leakage of pipelines, flushing is required & hence Auxiliary power consumption for flushing will be reduced. 10. Water consumption will be reduced. 11. Wear and Tear of pumps due to flushing will be reduced. |  |  |  |  | 0 |  |  |  |  | 18.81 | 19.75 | 20.73 | 21.77 | [11 empty] | 0 |  |  |  |  | 18.81 | 19.75 | 20.73 | 21.77 |  |  |  | #REF! | #REF! | -18.81 | Plant & Machinery | N
| WTP-II | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | DPR |  |  |  |  | 95.65 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | Scheme |  |  |  |  | 16 | [11 empty] | 0 | [5 empty] | 16 | [13 empty] | 0 | [5 empty] | 16 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | Scheme |  |  |  |  | 85.5299 | [11 empty] | 0 | [6 empty] | 85.5299 | [12 empty] | 0 | [6 empty] | 85.5299 |  |  |  |  | #REF! | 0 | 0 | Cooling Towers and Circulating Water Systems | N
| CHP-B | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | DPR |  |  |  |  | 38 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | Scheme |  |  |  |  | 16 | [11 empty] | 0 |  |  |  | 16 | [15 empty] | 0 |  |  |  | 16 | [7 empty] | #REF! | #REF! | -16 | Plant & Machinery | N
| Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | Scheme |  |  |  |  | 7 | [11 empty] | 0 |  |  |  | 7 | [15 empty] | 0 |  |  |  | 7 | [7 empty] | #REF! | #REF! | -7 | Plant & Machinery | N
| Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | Scheme |  |  |  |  | 5 | [11 empty] | 0 |  |  |  | 5 | [15 empty] | 0 |  |  |  | 5 | [7 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | DPR |  |  |  |  | 75 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | Scheme |  |  |  |  | 39 | [11 empty] | 0 |  |  |  | 39 | [15 empty] | 0 |  |  |  | 39 | [7 empty] | #REF! | #REF! | -39 | Plant & Machinery | N
| Scheme-2 Automation of Control Room of CHPA/B | Scheme |  |  |  |  | 15 | [11 empty] | 0 |  |  |  | 15 | [15 empty] | 0 |  |  |  | 15 | [7 empty] | #REF! | #REF! | -15 | Plant & Machinery | N
| Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | Scheme |  |  |  |  | 11 | [11 empty] | 0 |  |  |  | 11 | [15 empty] | 0 |  |  |  | 11 | [7 empty] | #REF! | #REF! | -11 | Plant & Machinery | N
| Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | Scheme |  |  |  |  | 10 | [11 empty] | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [7 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | DPR |  |  |  |  | 29 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | Scheme |  |  |  |  | 9 | [11 empty] | 0 |  |  |  | 9 | [15 empty] | 0 |  |  |  | 9 | [7 empty] | #REF! | #REF! | -9 | Plant & Machinery | N
| Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | Scheme |  |  |  |  | 20 | [11 empty] | 0 |  |  |  | 20 | [15 empty] | 0 |  |  |  | 20 | [7 empty] | #REF! | #REF! | -20 | Plant & Machinery | N
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | DPR |  |  |  |  | 29 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | Scheme |  |  |  |  | 8 | [11 empty] | 0 |  |  |  | 8 | [15 empty] | 0 |  |  |  | 8 | [7 empty] | #REF! | #REF! | -8 | Plant & Machinery | N
| Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | Scheme |  |  |  |  | 4 | [11 empty] | 0 |  |  |  | 4 | [15 empty] | 0 |  |  |  | 4 | [7 empty] | #REF! | #REF! | -4 | Plant & Machinery | N
| Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | Scheme |  |  |  |  | 8 | [11 empty] | 0 |  |  |  | 5 |  | 3 | [13 empty] | 0 |  |  |  | 5 |  | 3 | [5 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
| Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | Scheme |  |  |  |  | 4 | [11 empty] | 0 |  |  |  | 4 | [15 empty] | 0 |  |  |  | 4 | [7 empty] | #REF! | #REF! | -4 | Plant & Machinery | N
| Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | Scheme |  |  |  |  | 5 | [11 empty] | 0 |  |  |  | 5 | [15 empty] | 0 |  |  |  | 5 | [7 empty] | #REF! | #REF! | -5 | Plant & Machinery | N
5 | Modification & upgradation in Railway Track network of CSTPS | DPR |  |  |  |  | 29 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | Scheme |  |  |  |  | 14 | [11 empty] | 0 |  |  |  |  | 14 | [14 empty] | 0 |  |  |  |  | 14 | [6 empty] | #REF! | #REF! | -14 | Plant & Machinery | N
| Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | Scheme |  |  |  |  | 15 | [11 empty] | 0 |  |  |  |  | 15 | [14 empty] | 0 |  |  |  |  | 15 | [6 empty] | #REF! | #REF! | -15 | Plant & Machinery | N
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | DPR |  |  |  |  | 100 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | Scheme |  |  |  |  | 100 | [11 empty] | 0 | [5 empty] | 100 | [13 empty] | 0 | [5 empty] | 100 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| CHP-C | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0
| Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | Scheme |  |  |  |  | 25 | [11 empty] | 0 |  |  |  | 25 | [15 empty] | 0
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | DPR |  |  |  |  | 15 | [11 empty] | 0 | [19 empty] | 0
| Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | Scheme |  |  |  |  | 15 | [11 empty] | 0 | [5 empty] | 15 | [13 empty] | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | DPR |  |  |  |  | 6 | [11 empty] | 0 | [19 empty] | 0
| Reliability & availability improvement by replacement of set of internals for Paddle feeders | Scheme |  |  |  |  | 6 | [11 empty] | 0 |  |  |  | 6 | [15 empty] | 0
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | DPR |  |  |  |  | 10 | [11 empty] | 0 | [19 empty] | 0
| Reliability & availability improvement by replacement of transfer chutes at CHP-C | Scheme |  |  |  |  | 10 | [11 empty] | 0 | [5 empty] | 10 | [13 empty] | 0
| Civil U#3 to U#7 | [17 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | DPR |  |  |  |  | 37.57 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | Scheme |  |  |  |  | 37.57 | [6 empty] | As the schme is not related to generation, the cost benifit may not be analysed. However, by implemeting the scheme, following benifits will be achieved. 1. Land pollution due to contamination of reject coal with soil shall be restricted. 2. Contamination of nallah water and subsequent contamination of Erai river due to reject coal shall be avoided. 3. It shall facilitate smooth movement of transportation of coal reject. 4. Water logging of area during monsoon will be avoided. |  |  |  |  | 0 |  |  |  | 10 | 27.57 | [14 empty] | 0 |  |  |  | 10 | 27.57 | [6 empty] | #REF! | #REF! | -37.57 | Plant & Machinery | N
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | DPR |  |  |  |  | 47.15 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | Scheme |  |  |  |  | 47.15 | [6 empty] | As the schme is not related to generation, the cost benifit may not be analysed. However, by implemeting the scheme, following benifits will be achieved. 1. Smooth CHP operation in stacker area shall be ensured. 2. Regular maintenance cost will be reduced. 3. Accident chances shall be reduced. 4. Contamination of stacked coal with soil shall be restricted and therefore, the CV of coal can be retained. 5. Capacity of stacker shall be increased. |  |  |  |  | 0 |  |  |  | 15 | 32.15 | [14 empty] | 0 |  |  |  | 15 | 32.15 | [6 empty] | #REF! | #REF! | -47.15 | Plant & Machinery | N
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | DPR |  |  |  |  | 27.05 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | Scheme |  |  |  |  | 27.05 | [6 empty] | As the schme is not related to generation, the cost benifit may not be analysed. However, by implemeting the scheme, following benifits will be achieved. 1. Fugitive emission in CHP area will be reduced. 2. Maintenance cost of the road will be minimized. 3. The drain water will be circulated efficiently. 4. Accidents / Casualties will be avoided /minimized. 5. Facilitation of smooth movement to coal trucks to CHP stack yards and thereby will reduce the chanced of generation loss. 6. Aesthetic appearance of plant premise is improved. |  |  |  |  | 0 |  |  |  | 15 | 12.05 | [14 empty] | 0 |  |  |  | 15 | 12.05 | [6 empty] | #REF! | #REF! | -27.05 | Plant & Machinery | N
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | DPR |  |  |  |  | 30 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | Scheme |  |  |  |  | 30 | [6 empty] | The scheme is not related to generation & therefore quantified benefits may not be feasible to evaluate. However, the benefits of scheme are as under. 1) Roof leakages in buildings will be restricted. 2) Unsafe condition of building structure due to roof leakages shall be avoided. 3) Working environment shall become healthy. 4) Due to restriction of roof leakages machineries / electric panels / records available in building will become safe during monsoon. |  |  |  |  | 0 |  |  |  | 15 | 15 | [14 empty] | 0 |  |  |  | 15 | 15 | [6 empty] | #REF! | #REF! | -30 | Plant & Machinery | N
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | DPR |  |  |  |  | 40 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | Scheme |  |  |  |  | 30 | [6 empty] | The scheme is not related to generation & therefore quantified benefits may not be feasible to evaluate. However, the benefits of scheme are as under. 1) Life of structures / buildings will be increased. 2) Chances of accident in future due to failure of structure will be nullified. 3) Chances of generation loss due to failure of structure in near futere will be minimised. 4) Healthy atmosphere among working staff shall be achieved. |  |  |  |  | 0 |  |  |  | 15 | 15 | [14 empty] | 0 |  |  |  | 15 | 15 | [6 empty] | #REF! | #REF! | -30 | Plant & Machinery | N
| Structural strengthening of CHP-A buildings | Scheme |  |  |  |  | 10 | [6 empty] | The scheme is not related to generation & therefore quantified benefits may not be feasible to evaluate. However, the benefits of scheme are as under. 1) Life of structures / buildings will be increased. 2) Chances of accident in future due to failure of structure will be nullified. 3) Chances of generation loss due to failure of structure in near futere will be minimised. 4) Healthy atmosphere among working staff shall be achieved. |  |  |  |  | 0 |  |  |  | 6 | 4 | [14 empty] | 0 |  |  |  | 6 | 4 | [6 empty] | #REF! | #REF! | -10 | Plant & Machinery | N
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | DPR |  |  |  |  | 67.9 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | Scheme |  |  |  |  | 3.78 | [6 empty] | 1) It creates more water presuure. The elevated position of water storage tanks allows it to deliver water with more pressure. 2)It will eliminates the expenses and insatllation of pumps. 3) The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 3.78 | [15 empty] | 0 |  |  |  | 3.78 | [7 empty] | #REF! | #REF! | -3.78 | Plant & Machinery | N
| ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | Scheme |  |  |  |  | 4.05 | [6 empty] | 1) Maintenance cost will be reduced as compared with the old pipelines 2)The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 4.05 | [15 empty] | 0 |  |  |  | 4.05 | [7 empty] | #REF! | #REF! | -4.05 | Plant & Machinery | N
| iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | Scheme |  |  |  |  | 7.01 | [6 empty] | 1) Maintenance cost will be reduced as compared with the old pipelines 2)The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 7.01 | [15 empty] | 0 |  |  |  | 7.01 | [7 empty] | #REF! | #REF! | -7.01 | Plant & Machinery | N
| iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | Scheme |  |  |  |  | 6.34 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced . 3) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 6.34 | [15 empty] | 0 |  |  |  | 6.34 | [7 empty] | #REF! | #REF! | -6.34 | Plant & Machinery | N
| v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | Scheme |  |  |  |  | 16.86 | [6 empty] | 1) Storm water drain will be prevevted flooding by diverting rainwater away from the buildings. 2)Storm water drain will prevent the soil errosion. 3) maintenance cost of road will be reduced. 4) Maintenece cost will be reduced 5) Healthy atmosphere will be created in colony. 6) The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 8.43 | 8.43 | [14 empty] | 0 |  |  |  | 8.43 | 8.43 | [6 empty] | #REF! | #REF! | -16.86 | Plant & Machinery | N
| vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | Scheme |  |  |  |  | 29.81 | [6 empty] | 1) Good riding surface will be available for traffic movement 2)Smooth traffic movememnt will be achieved. 3) maintenance cost of road will be reduced. 4) No need to carry out same work repitatively 5) Possibility of accidents will be reduced by providing the road furniture. 6) The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 14.905 | 14.905 | [14 empty] | 0 |  |  |  | 14.905 | 14.905 | [6 empty] | #REF! | #REF! | -29.81 | Plant & Machinery | N
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | DPR |  |  |  |  | 209 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | Scheme |  |  |  |  | 132 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  |  | 44 | 44 | 44 | [12 empty] | 0 |  |  |  |  | 44 | 44 | 44 |  |  |  |  | #REF! | #REF! | -44 | Buildings | N
| ii-Renovation of old and new market at CSTPS Chandrapur | Scheme |  |  |  |  | 2 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [6 empty] | #REF! | #REF! | -2 | Plant & Machinery | N
| iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | Scheme |  |  |  |  | 55 | [6 empty] | 1) Good riding surface will be available for traffic movement 2)Smooth traffic movememnt will be achieved. 3) maintenance cost of road will be reduced. 4) No need to carry out same work repitatively 5) Possibility of accidents will be reduced by providing the road furniture. 6) The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 27.5 | 27.5 | [12 empty] | 0 | [5 empty] | 27.5 | 27.5 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | Scheme |  |  |  |  | 1.5 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 1.5 | [13 empty] | 0 | [5 empty] | 1.5 | [5 empty] | #REF! | 0 | 0 | Buildings | N
| v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | Scheme |  |  |  |  | 1.5 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 1.5 | [13 empty] | 0 | [5 empty] | 1.5 | [5 empty] | #REF! | 0 | 0 | Buildings | N
| vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | Scheme |  |  |  |  | 2 | [6 empty] | 1) Structural life of the buildings will be incresed 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
| vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | Scheme |  |  |  |  | 15 | [6 empty] | 1) Good riding surface will be available for traffic movement 2)Smooth traffic movememnt will be achieved. 3) maintenance cost of road will be reduced. 4) No need to carry out same work repitatively 5) Possibility of accidents will be reduced by providing the road furniture. 6) The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 15 | [13 empty] | 0 | [5 empty] | 15 | [5 empty] | #REF! | 0 | 0 | Plant & Machinery | N
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | DPR |  |  |  |  | 76.25 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | Scheme |  |  |  |  | 60 | [6 empty] | 1) Modern amenities are one of the main advantage of new construction building 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [5 empty] | 30 | 30 | [12 empty] | 0 | [5 empty] | 30 | 30 |  |  |  |  | #REF! | 0 | 0 | Buildings | N
| ii-Construction of New Hospital Building at CSTSP Chandrapur | Scheme |  |  |  |  | 2 | [6 empty] | 1) Modern amenities are one of the main advantage of new construction building 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  |  | #REF! | 0 | 0 | Buildings | N
| iii-Construction of new Chummary Building at CSTPS Chandrapur | Scheme |  |  |  |  | 7.5 | [6 empty] | 1) Modern amenities are one of the main advantage of new construction building 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 7.5 | [12 empty] | 0 | [6 empty] | 7.5 |  |  |  |  | #REF! | 0 | 0 | Buildings | N
| iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | Scheme |  |  |  |  | 0.75 | [6 empty] | 1) Modern amenities are one of the main advantage of new construction building 2) Maintenance cost of the work will be reduced 3) No need to carry out the same work repetatively. 4) Healthy atmosphere will be created in colony. 5) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 0.75 | [12 empty] | 0 | [6 empty] | 0.75 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| v-Construction of swimming pool in colony at CSTPS Chandrapur | Scheme |  |  |  |  | 2 | [6 empty] | 1) A well desigened pool can enhance the look of residential area. 2) A can be a great place for family and friends to socialize 3) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | Scheme |  |  |  |  | 2 | [6 empty] | 1) Maintenance cost will be reduced as compared with the old pipelines 2)The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
| viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | Scheme |  |  |  |  | 2 | [6 empty] | 1) Ground water tablr will be recharged or it will be icreased 2)The scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  |  | #REF! | 0 | 0 | Buildings | N
9 | Renovation of public utility building of CSTPS, Chandrapur | DPR |  |  |  |  | 29.95 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| Renovation and interior decoration of Hirai guest house | Scheme |  |  |  |  | 7.51 | [6 empty] | 1) Advanced facilities for VIP Guest will be availalbe. 2) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 3.755 | 3.755 | [14 empty] | 0 |  |  |  | 3.755 | 3.755 | [6 empty] | #REF! | #REF! | -7.51 | Plant & Machinery | N
| Renovation and interior decoration of existing chummery guest house | Scheme |  |  |  |  | 12.22 | [6 empty] | 1) Advanced facilities for VIP Guest will be availalbe. 2) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 6.11 | 6.11 | [14 empty] | 0 |  |  |  | 6.11 | 6.11 | [6 empty] | #REF! | #REF! | -12.22 | Plant & Machinery | N
| Renovation and interior decoration of existing Erai dam guest house | Scheme |  |  |  |  | 6.65 | [6 empty] | 1) Advanced facilities for VIP Guest will be availalbe. 2) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 3.325 | 3.325 | [14 empty] | 0 |  |  |  | 3.325 | 3.325 | [6 empty] | #REF! | #REF! | -6.65 | Plant & Machinery | N
| Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | Scheme |  |  |  |  | 3.57 | [6 empty] | 1) Advanced facilities for VIP Guest will be availalbe. 2) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 |  |  |  | 1.785 | 1.785 | [14 empty] | 0 |  |  |  | 1.785 | 1.785 | [6 empty] | #REF! | #REF! | -3.57 | Buildings | N
10 | R&M/LE for Identified Thermal units of MSPGCL | DPR |  |  |  |  | 400 | [11 empty] | 0 | [19 empty] | 0 | [11 empty] | #REF! | 0 | 0
| R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | Scheme |  |  |  |  | 293 | [11 empty] | 0 |  |  |  |  | 293 | [14 empty] | 0 |  |  |  |  | 293 | [6 empty] | #REF! | #REF! | -293 | Plant & Machinery | N
| R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | Scheme |  |  |  |  | 300 | [11 empty] | 0 | [6 empty] | 300 | [12 empty] | 0 | [6 empty] | 300 |  |  |  |  | #REF! | 0 | 0 | Plant & Machinery | N
11 | CHP Improvement Schemes | DPR |  |  |  |  | 100 | [11 empty] | 0 | [19 empty] | 0
| CHP Improvement Schemes at CHP-A, B, C | Scheme |  |  |  |  | 100 | [11 empty] | 0 |  |  |  |  | 100 | [14 empty] | 0 |  |  |  |  | 100 | [9 empty] | Plant & Machinery | N
12 | Developlment & Upgradation of SAP for MSPGCL | DPR |  |  |  |  | 200 | [11 empty] | 0 | [19 empty] | 0
| Developlment & Upgradation of SAP for MSPGCL | Scheme |  |  |  |  | 200 | [11 empty] | 0 |  |  |  | 200 | [15 empty] | 0 |  |  |  | 200 | [10 empty] | Software | N
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | DPR |  |  |  |  | 42 | [11 empty] | 0 | [19 empty] | 0
| Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | Scheme |  |  |  |  | 42 | [11 empty] | 0 |  |  |  | 42 | [15 empty] | 0 |  |  |  | 42 | [10 empty] | Plant & Machinery | N
14 | Implementation of Flexible Operation Solutions (U-3,4) | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0
| Implementation of Flexible Operation Solutions (U-3,4) | Scheme |  |  |  |  | 25 | [11 empty] | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [10 empty] | Plant & Machinery | N
15 | DPR for ash utilisation cell- infrastructure development | DPR |  |  |  |  | 278.5 | [11 empty] | 0 | [19 empty] | 0
| DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | Scheme |  |  |  |  | 268 | [11 empty] | 0 |  |  |  | 200 | 68 | [14 empty] | 0 |  |  |  | 200 | 68 | [9 empty] | Other & Civil work | N
| Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | Scheme |  |  |  |  | 10 | [11 empty] | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [10 empty] | Other & Civil work | N
| Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | Scheme |  |  |  |  | 0.5 | [11 empty] | 0 |  |  |  | 0.5 | [15 empty] | 0 |  |  |  | 0.5 | [10 empty] | Other & Civil work | N
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | DPR |  |  |  |  | 25 | [11 empty] | 0 | [19 empty] | 0
| Up-gradation Schemes for CAAQM Stations & NABL Laboratory | Scheme |  |  |  |  | 25 | [11 empty] | 0 |  |  |  |  | 12.5 | 12.5 | [13 empty] | 0 |  |  |  |  | 12.5 | 12.5 | [8 empty] | Plant & Machinery | N
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | DPR |  |  |  |  | 27.6 | [11 empty] | 0 | [19 empty] | 0
| Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | Scheme |  |  |  |  | 8.9 | [11 empty] | 0 |  |  |  |  | 8.9 | [14 empty] | 0 |  |  |  |  | 8.9 | [9 empty] | Plant & Machinery | N
| Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | Scheme |  |  |  |  | 10.82 | [11 empty] | 0 |  |  |  |  | 10.82 | [14 empty] | 0 |  |  |  |  | 10.82 | [9 empty] | Plant & Machinery | N
| Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | Scheme |  |  |  |  | 7.88 | [11 empty] | 0 |  |  |  |  | 7.88 | [14 empty] | 0 |  |  |  |  | 7.88 | [9 empty] | Plant & Machinery | N
18 | Ash bund peripheral road | DPR |  |  |  |  | 120 | [11 empty] | 0 | [19 empty] | 0
| Ash bund peripheral road | Scheme |  |  |  |  | 120 | [11 empty] | 0 | [5 empty] | 60 | 60 | [12 empty] | 0 | [5 empty] | 60 | 60 | [7 empty] | Other & Civil work | N
19 | Construction of peripheral nallah | DPR |  |  |  |  | 100 | [11 empty] | 0 | [19 empty] | 0
| Construction of peripheral nallah | Scheme |  |  |  |  | 100 | [11 empty] | 0 | [5 empty] | 50 | 50 | [12 empty] | 0 | [5 empty] | 50 | 50 | [7 empty] | Other & Civil work | N
20 | Construction of concrete Roads with drains at colony | DPR |  |  |  |  | 110 | [11 empty] | 0 | [19 empty] | 0
| Construction of concrete Roads with drains at colony | Scheme |  |  |  |  | 110 | [11 empty] | 0 | [5 empty] | 55 | 55 | [12 empty] | 0 | [5 empty] | 55 | 55 | [7 empty] | Other & Civil work | N
21 | Fugitive emisson reduction techniques | DPR |  |  |  |  | 50 | [11 empty] | 0 | [19 empty] | 0
| Fugitive emisson reduction schemes | Scheme |  |  |  |  | 50 | [11 empty] | 0 | [5 empty] | 25 | 25 | [12 empty] | 0 | [5 empty] | 25 | 25 | [7 empty] | Plant & Machinery | N
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | GENERAL ASSET | Non-DPR |  |  |  |  | 20 | [8 empty] | 1.9755 | 0.75187 | 1.3456 | 4.073 | 1.3032 |  | 1.5 | 1.5 | [12 empty] | 1.9755 | 0.75187 | 1.3456 | 4.073 | 1.3032 |  | 1.5 | 1.5 |  |  |  |  | 6.0902 |  |  | #REF! | #REF! | 7.5508 | Office Equipment | E
2 | M/S GEO-MILLER arbitration amount | Non-DPR |  |  |  |  | 1.3765 | [8 empty] | 0.68824 |  |  | 0.68824 | [19 empty] | 0 | 0.68824 | [10 empty] | #REF! | #REF! | 0.68824 | Plant & Machinery | E
3 | CM Reject Handling Sys Macawber Breakey | Non-DPR |  |  |  |  | 3.1822 | [7 empty] | 3.1822 |  |  |  | 3.1822 | -3.1822 | [18 empty] | 0 | [11 empty] | #REF! | 0 | 3.1822 | Plant & Machinery | E
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | Non-DPR |  |  |  |  | 4.8622 | [11 empty] | 0 | 4.8622 | [18 empty] | 0 | 4.8622 | [10 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | Non-DPR |  |  |  |  | 4.742 | [11 empty] | 0 | 4.742 | [18 empty] | 0 | 4.742 | [10 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | Non-DPR |  |  |  |  | 4.51 | [10 empty] | 2.2543 | 2.2543 | 2.2543 | [18 empty] | 0 | 4.5085 | [10 empty] | #REF! | #REF! | 0.001456 | Plant & Machinery | E
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | Non-DPR |  |  |  |  | 3.45 | [11 empty] | 0 | 3.4451 | [18 empty] | 0 | 3.4451 | [10 empty] | #REF! | #REF! | 0.0049428 | Plant & Machinery | E
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | Non-DPR |  |  |  |  | 6.41 | [6 empty] | 1) Wall compound protects from the wild animals and thievs 2) Wall compound helps to etsblish the boundaries of a property and prevevnt diputes with neighbours 3) Wall compound creates a secured space for colony residents 4) The above scheme is not related to the generation and it related to provide the services to the employees. |  |  |  |  | 0 | 0.81084 | 1.1201 | 1.6811 | [16 empty] | 0 |  |  | 3.612 | [8 empty] | #REF! | #REF! | 2.798 | Plant & Machinery | E
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | Non-DPR |  |  |  |  | 7.95 | [10 empty] | 2.5033 | 2.5033 | 4.52 |  | 0.92678 | [16 empty] | 0 |  |  |  | 7.95 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | Non-DPR |  |  |  |  | 4.7 | [11 empty] | 0 | 0.91373 | 0.91373 | [17 empty] | 0 |  | 1.8275 | [9 empty] | #REF! | #REF! | 2.8725 | Plant & Machinery | E
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | Non-DPR |  |  |  |  | 4.6024 | [11 empty] | 0 | 2.3014 | 2.301 | [17 empty] | 0 |  | 4.6024 | [9 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | Non-DPR |  |  |  |  | 7.251 | [11 empty] | 0 |  | 7.2509 | [17 empty] | 0 |  | 7.2509 | [9 empty] | #REF! | #REF! | 6.05e-05 | Plant & Machinery | E
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | Non-DPR |  |  |  |  | 5.27 | [11 empty] | 0 |  | 2.5838 | 2.6862 | [16 empty] | 0 |  | 2.5838 | 2.6862 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | Non-DPR |  |  |  |  | 5.61 | [6 empty] | 1) Availability and Reliability of auxiliary / unit get increased. 2) The availability of spares & outage period reduce substantially. 3) Variable Cost: Due to reduction in down time of auxiliary & improvement in Auxiliary Power Consumption, Variable cost of generation is reduced. |  |  |  |  | 0 |  | 5.5874 | [17 empty] | 0 |  |  | 5.5874 | [8 empty] | #REF! | #REF! | 0.022564 | Cooling Towers and Circulating Water Systems | E
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | Non-DPR |  |  |  |  | 9.09 | [11 empty] | 0 |  | 8.2283 | 0.86172 | [16 empty] | 0 |  |  | 9.09 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | Non-DPR |  |  |  |  | 9.95 | [6 empty] | Heat Rate improvement of 58 KCal/Kwh expected after replacement of module in Unit-6 during proposed COH |  |  |  |  | 0 |  |  | 9.95 | [16 empty] | 0 |  |  | 9.95 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | Non-DPR |  |  |  |  | 4.9 | [11 empty] | 0 |  | 0.4838 | 4.4162 | [16 empty] | 0 |  |  | 4.9 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | Non-DPR |  |  |  |  | 3.66 | [11 empty] | 0 |  | 2.8573 | 0.80267 | [16 empty] | 0 |  |  | 3.66 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | Non-DPR |  |  |  |  | 4.37 | [11 empty] | 0 |  |  | 4.37 | [16 empty] | 0 |  |  | 4.37 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | Non-DPR |  |  |  |  | 2.24 | [11 empty] | 0 |  |  |  | 2.24 | [15 empty] | 0 |  |  |  | 2.24 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | Non-DPR |  |  |  |  | 1.6 | [11 empty] | 0 |  |  |  | 1.6 | [15 empty] | 0 |  |  |  | 1.6 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | Non-DPR |  |  |  |  | 9.01 | [11 empty] | 0 |  |  | 9.01 | [16 empty] | 0 |  |  | 9.01 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | Non-DPR |  |  |  |  | 2.57 | [6 empty] | Benefits in quantified terms cannot be calculated as spares shall be procured as Insurance spares for emergency replacement thus reducing down time of auxiliary. However, Feed water system improvement & enhancement can be ascertained. As on date, 8.5MW of APC can be saved for each day of reduction in Auxiliary outage. |  |  |  |  | 0 |  |  | 0.55 | 2.02 | [15 empty] | 0 |  |  | 0.55 | 2.02 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | Non-DPR |  |  |  |  | 4.2 | [11 empty] | 0 |  |  |  | 4.2 | [15 empty] | 0 |  |  |  | 4.2 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | Non-DPR |  |  |  |  | 2.1 | [11 empty] | 0 |  |  | 2.1 | [16 empty] | 0 |  |  | 2.1 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | Non-DPR |  |  |  |  | 4.55 | [11 empty] | 0 |  |  |  | 4.55 | [15 empty] | 0 |  |  |  | 4.55 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | Non-DPR |  |  |  |  | 0.97 | [11 empty] | 0 |  |  |  | 0.97 | [15 empty] | 0 |  |  |  | 0.97 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | Non-DPR |  |  |  |  | 7.89 | [11 empty] | 0 |  |  |  | 7.89 | [15 empty] | 0 |  |  |  | 7.89 | [7 empty] | #REF! | #REF! | 0 | Other & Civil work | N
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | Non-DPR |  |  |  |  | 5.44 | [11 empty] | 0 |  |  |  | 5.44 | [15 empty] | 0 |  |  |  | 5.44 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
31 | Replacement of LTSH assemblies in U- 5 | Non-DPR |  |  |  |  | 1.3757 | [11 empty] | 0 |  | 1.3757 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 1.3757 | 0 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
32 | Replacement of complete Z-panels in unit- 5 | Non-DPR |  |  |  |  | 0.82546 | [11 empty] | 0 |  | 0.82546 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0.82546 | 0 | [8 empty] | #REF! | #REF! | 0 | Plant & Machinery | E
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | Non-DPR |  |  |  |  | 10.3 | [11 empty] | 0 |  |  | 7.5 | 2.8 | [15 empty] | 0 |  |  | 7.5 | 2.8 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | Non-DPR |  |  |  |  | 5.62 | [6 empty] | • By installing online Dissolved gas analyser, incipient transformer faults can be detected which helps to prevent further damage to GTR. • By replacing OIP Condenser Bushings by Resin Impregnated Polymer (RIP) bushing, bushing oil leakages will be vanish permanently. |  |  |  |  | 0 |  |  |  | 5.62 | [15 empty] | 0 |  |  |  | 5.62 | [7 empty] | #REF! | #REF! | 0 | Plant & Machinery | N
| Total | [13 empty] | 380.6384 | 70.4402 | 55.0078 | 372.4974 | 878.5837 | 131.0561 | 127.604 | 591.3531 | 3042.2372 | 2211.6905 | 814.964 | 879.1599 | 211.02 | [7 empty] | 337.7359 | 54.1196 | 59.8915 | 397.5792 | 849.3262 | 117.3226 | 110.7942 | 638.3779 | 2974.7857 | 2260.8135 | 789.964 | 879.1599 | 211.02 | 2.5426
[40 empty] | 19.5493 | 18.4657 | 64.5157
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Note on G18: USER: (Cost included in Scheme of pressure drop across APH)
Note on G52: RCD-SSP: 29.51 As per financial model. 26.20 as per BR & initial submission.
Note on G146: RCD-SSP: Initial submission: Rs. 171.51 Cr
Note on G157: RCD-SSP: Initial submission Rs. 16.52 with 2.15 IDC
Note on G206: RCD-SSP: Total DPR Cost Rs. 32 Cr. 9.6 is for C'pur only
Note on G207: RCD-SSP: Total DPR Cost Rs. 32 Cr. 9.6 is for C'pur only
Note on G227: SSP-RCD: Need to split between nasik, parli & chandrapur
Note on G228: SSP-RCD: Including 18% GST & 2% P&F Charges
Note on M1: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on AP238: Prasanna kumar: take correct figures from account

## F4.3
MSPGCL: Chandrapur U # 3-7
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 3.9205 | 3.9205 | 0 | 0.32828 | 0.32828 |  |  | 0.32828 | 0 | 0 | 0.32828
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 3.9e-08 | 3.9e-08 |  |  | 3.9e-08 | -3.2584e-16 | 3.9e-08 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 5.0972 | 5.0973 | -5.4e-05 | 0.64944 | 0.64939 |  |  | 0.64939 | 0 | 0.64939 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 5.0497 | 4.9279 | 0.12178 | 1.1781 | 1.2999 |  |  | 1.2999 | 0 | 1.2999 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 4.5201 | 4.4155 | 0.10458 | 0.66977 | 0.66977 |  |  | 0.66977 | 0.10458 | 0.66977 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 5.4267 | 4.0159 | 1.4107 | 0 | 0 |  |  | 0 | 1.4107 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.1444 | 2.1444 | 0 | 0.16888 | 0.16888 |  |  | 0.16888 | 0 | 0.16888 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 1.3517 | 1.3517 | 0 | 4.0368 | 4.0368 |  |  | 4.0368 | 0 | 4.0368 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 0 | 0 | 0 | 2.347 | 2.347 |  |  | 2.347 | 0 | 2.347 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.1298 | 3.1298 | 0 | 0.19438 | 0.19438 |  |  | 0.19438 | 0 | 0 | 0.19438
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.8049 | 3.8049 | 0 | 0.10731 | 0.10731 |  |  | 0.10731 | 0 | 0.10731 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.4976 | 0 | 4.4976 | 0.07524 | 4.5728 |  |  | 4.5728 | 0 | 4.5728 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 12.1667 | 9.418 | 2.7487 | 0 | 2.5941 |  |  | 2.5941 | 0.15468 | 2.5941 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 254.5851 | 254.5851 | 0 | 1.8582 | 1.8582 |  |  | 1.8582 | -8.8818e-15 | 0 | 1.8582
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 81.733 | 74.3189 | 7.4142 | -4.8009 | 3.2833 |  |  | 3.2833 | -0.67003 | 3.2833 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.7981 | 5.837 | 1.9612 | -1.4528 | 0.5084 |  |  | 0.5084 | 0 | 0.5084 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 0.48954 | 0 | 0.48954 | 1.1378 | 1.6273 |  |  | 1.6273 | 0 | 1.6273 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 0 | 0 | 0 | 5.4274 | 5.4274 |  |  | 5.4274 | 0 | 5.4274 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 0 | 0 | 0 | 29.2133 | 0 |  |  | 0 | 29.2133 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 1.0992 | 0.826 | 0.27324 | 41.0903 | 41.3636 |  |  | 41.3636 | 0 | 39.5331 | 1.8305
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | #REF! | #REF!
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 8.8348 | 8.8348 | 0 | 7.3896 | 7.3896 |  |  | 7.3896 | 0 | 7.3896 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0 | 0 | 0 | 0.26772 | 0.26772 |  |  | 0.26772 | 0 | 0.26772 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0 | 0 | 0 | 2.1847 | 2.1847 |  |  | 2.1847 | 0 | 1.25 | 0.93465
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 7.737 | 6.1289 | 1.6082 | 1.214 | 2.8222 |  |  | 2.8222 | 0 | 2.8222 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 0 | 0 | 0 | 2.8883 | 2.8883 |  |  | 2.8883 | 0 | 2.8883 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0 | 0 | 0 | 0.84252 | 0.84252 |  |  | 0.84252 | 0 | 0.84252 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 0 | 0 | 0 | 6.0121 | 6.0121 |  |  | 6.0121 | 0 | 6.0121 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 0 | 0 | 0 | 4.3294 | 4.3294 |  |  | 4.3294 | 0 | 4.3294 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 0 | 0 | 0 | 1.7287 | 0 |  |  | 0 | 1.7287 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 4.073 | 4.073 | 0 | 1.3032 | 1.3032 |  |  | 1.3032 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0 | 0.68824 | 0 | 0.68824 |  |  | 0.68824 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 3.1822 | 0 | 3.1822 | -3.1822 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 0 | 0 | 0 | 4.8622 | 4.8622 |  |  | 4.8622 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 0 | 0 | 0 | 4.742 | 4.742 |  |  | 4.742 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 2.2543 | 0 | 2.2543 | 2.2543 | 4.5085 |  |  | 4.5085 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 0 | 0 | 0 | 3.4451 | 3.4451 |  |  | 3.4451 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 0 | 0 | 0 | 0.81084 | 0 |  |  | 0 | 0.81084
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 2.5033 | 0 | 2.5033 | 4.52 | 0 |  |  | 0 | 7.0232
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 0 | 0 | 0 | 0.91373 | 0 |  |  | 0 | 0.91373
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 0 | 0 | 0 | 2.3014 | 0 |  |  | 0 | 2.3014
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 878.5837 | 849.3262 | 29.2576 | 131.0561 | 117.3226 | 0 | 0 | 117.3226 | 42.9911
FY 2023-24
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 5.7467 | 5.7467 | 0 | 2.8735 | 2.8735 |  |  | 2.8735 | 0 | 2.8735 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 6.2278 | 6.2278 | 0 | 0.32741 | 0.32741 |  |  | 0.32741 | 0 | 0.32741 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 5.1899 | 5.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0 | 0 | 0 | 0.03865 | 0.03865 |  |  | 0.03865 | 0 | 0.03865 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 5.4267 | 4.0159 | 1.4107 | 0 | 0 |  |  | 0 | 1.4107 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.3133 | 2.3133 | 0 | 0.16907 | 0.16907 |  |  | 0.16907 | 0 | 0.16907 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 2.347 | 2.347 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 12.1667 | 12.0121 | 0.15468 | 0.23363 | 0.3883 |  |  | 0.3883 | 0 | 0.3883 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.4433 | 256.4433 | 0 | 0.37193 | 0.37193 |  |  | 0.37193 | 2.0317e-14 | 0 | 0.37193
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 76.9321 | 77.6022 | -0.67003 | 5.3179 | 4.6478 |  |  | 4.6478 | 0 | 4.6478 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 6.3454 | 6.3454 | 0 | 0.034842 | 0.034842 |  |  | 0.034842 | 3.0531e-16 | 0.034842 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 0 | 0 | 0 | 4.1941 | 4.1941 |  |  | 4.1941 | 0 | 4.1941 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 1.6273 | 1.6273 | 0 | 3.6196 | 3.0375 |  |  | 3.0375 | 0.5821 | 3.0375 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 5.4274 | 5.4274 | 0 | 5.513 | 5.513 |  |  | 5.513 | 0 | 2.4026 | 3.1103
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 29.2133 | 0 | 29.2133 | -0.010019 | 1.7134 |  |  | 1.7134 | 27.4899 | 1.7134 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 0 | 0 | 0 | 1.4649 | 0 |  |  | 0 | 1.4649 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 16.2244 | 16.2244 | 0 | 0.54562 | 0 |  |  | 0 | 0.54562 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 0 | 0 | 0 | 9.3999 | 9.3999 |  |  | 9.3999 | 0 | 9.3999 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 0 | 0 | 0 | 9.9521 | 9.9521 |  |  | 9.9521 | 0 | 9.9521 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 8.9511 | 8.9511 | 0 | 0.66117 | 0.66117 |  |  | 0.66117 | 0 | 0.12312 | 0.53805
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 0 | 0 | 0 | 3.607 | 3.607 |  |  | 3.607 | 0 | 3.607 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 0 | 0 | 0 | 2.709 | 2.3456 |  |  | 2.3456 | 0.36343 | 2.3456 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.7287 | 0 | 1.7287 | 0 | 0 |  |  | 0 | 1.7287 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | 0 | 0 | 0 | 0 | 19.22 |  |  | 19.22 | -19.22 | 19.22 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 0 | 0 | 0 | 40.1338 | 40.1338 |  |  | 40.1338 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 0 | 0 | 0 | 2.9194 | 2.9194 |  |  | 2.9194 | 0 | 2.9194 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 5.3762 | 5.3762 | 0 | 0 | 0 |  |  | 0 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 0.81084 | 0 | 0.81084 | 1.1201 | 0 |  |  | 0 | 1.9309
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.0232 | 0 | 7.0232 | 0 | 0 |  |  | 0 | 7.0232
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 0.91373 | 0 | 0.91373 | 0.91373 | 1.8275 |  |  | 1.8275 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 2.3014 | 0 | 2.3014 | 2.301 | 4.6024 |  |  | 4.6024 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 0 | 0 | 0 | 7.2509 | 7.2509 |  |  | 7.2509 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 0 | 0 | 0 | 2.5838 | 2.5838 |  |  | 2.5838 | -1e-07
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 0 | 0 | 0 | 5.5874 | 0 |  |  | 0 | 5.5874
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 0 | 0 | 0 | 8.2283 | 0 |  |  | 0 | 8.2283
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 0 | 0 | 0 | 0.4838 | 0 |  |  | 0 | 0.4838
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 0 | 0 | 0 | 2.8573 | 0 |  |  | 0 | 2.8573
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 0 | 0 | 0 | 1.3757 | 1.3757 |  |  | 1.3757 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0 | 0 | 0 | 0.82546 | 0.82546 |  |  | 0.82546 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1009.6399 | 966.6487 | 42.9911 | 127.604 | 130.0142 | 0 | 0 | 130.0142 | 40.5809
FY 2024-25
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 6.5553 | 6.5553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 5.1899 | 5.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 26.1 | 26.1 |  |  | 26.1 | 0 | 26.1 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 5.4267 | 4.0159 | 1.4107 | 0 | 0 |  |  | 0 | 1.4107 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 2.347 | 2.347 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0 | 2.204 | 1.296
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 12.4004 | 12.4004 | 0 | 2.29 | 2.29 |  |  | 2.29 | 0 | 2.2856 | 0.0043744
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.25 | 82.25 | 0 | 0.35 | 0.35 |  |  | 0.35 | 0 | 0.35 | 5.6621e-15
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 6.3802 | 6.3802 | 0 | 0.6998 | 0.6998 |  |  | 0.6998 | 0 | 0.6998 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.1941 | 4.1941 | 0 | 0.52593 | 0.52593 |  |  | 0.52593 | 0 | 0.52593 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 5.247 | 4.6649 | 0.5821 | 2.1 | 2.1 |  |  | 2.1 | 0.5821 | 2.1 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 29.2032 | 1.7134 | 27.4899 | 3.3568 | 30.8466 |  |  | 30.8466 | 0 | 30.8466 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 1.4649 | 0 | 1.4649 | 15.4351 | 16.9 |  |  | 16.9 | 0 | 14.2003 | 2.6997
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 16.77 | 16.2244 | 0.54562 | 1.55 | 1.0956 |  |  | 1.0956 | 1 | 1.0956 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 0 | 0 | 0 | 179.49 | 179.49 |  |  | 179.49 | 0 | 179.49 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 3.607 | 3.607 | 0 | 2.47 | 2.47 |  |  | 2.47 | 0 | 2.47 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 2.709 | 2.3456 | 0.36343 | 0 | 0.36343 |  |  | 0.36343 | 0 | 0.36343 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.7287 | 0 | 1.7287 | 0 | 0 |  |  | 0 | 1.7287 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 0 | 0 | 0 | 116.38 | 116.38 |  |  | 116.38 | 0 | 116.38 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | 0 | 19.22 | -19.22 | #VALUE! | 108.94 |  |  | 108.94 | #VALUE! | 90.18 | 18.76
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 0 | 0 | 0 | 39 | 39 |  |  | 39 | 0 | 32.568 | 6.432
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 40.1338 | 40.1338 | 0 | 26.8099 | 26.8099 |  |  | 26.8099 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 0 | 0 | 0 | 1.1231 | 1.1231 |  |  | 1.1231 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 0 | 0 | 0 | 2.8072 | 2.8072 |  |  | 2.8072 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 0 | 0 | 0 | 16.8707 | 16.8707 |  |  | 16.8707 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 0 | 0 | 0 | 5.66 | 5.66 |  |  | 5.66 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 0 | 0 | 0 | 8.17 | 8.17 |  |  | 8.17 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 0 | 0 | 0 | 4.12 | 4.12 |  |  | 4.12 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 0 | 0 | 0 | 3.72 | 3.72 |  |  | 3.72 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 0 | 0 | 0 | 3.45 | 3.45 |  |  | 3.45 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 0 | 0 | 0 | 4.6 | 4.6 |  |  | 4.6 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 0 | 0 | 0 | 8.14 | 8.14 |  |  | 8.14 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 0 | 0 | 0 | 4.18 | 4.18 |  |  | 4.18 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 0 | 0 | 0 | 17.46 | 17.46 |  |  | 17.46 | 0 | 17.46 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 25.42 | 25.42 |  |  | 25.42 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 5.3762 | 5.3762 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 1.9309 | 0 | 1.9309 | 1.6811 | 3.612 |  |  | 3.612 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.0232 | 0 | 7.0232 | 0.92678 | 0 |  |  | 0 | 7.95
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 2.5838 | 2.5838 | -1e-07 | 2.6862 | 2.6862 |  |  | 2.6862 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 0 | 5.5874 | 0 | 5.5874 |  |  | 5.5874 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 8.2283 | 0 | 8.2283 | 0.86172 | 9.09 |  |  | 9.09 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 0 | 0 | 0 | 9.95 | 9.95 |  |  | 9.95 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 0.4838 | 0 | 0.4838 | 4.4162 | 4.9 |  |  | 4.9 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 2.8573 | 0 | 2.8573 | 0.80267 | 3.66 |  |  | 3.66 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 0 | 0 | 0 | 4.37 | 4.37 |  |  | 4.37 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 0 | 0 | 0 | 9.01 | 9.01 |  |  | 9.01 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 0 | 0 | 0 | 0.55 | 0.55 |  |  | 0.55 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 0 | 0 | 0 | 2.1 | 2.1 |  |  | 2.1 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1137.2438 | 1096.6629 | 40.5809 | #VALUE! | 728.0979 | 0 | 0 | 728.0979 | #VALUE!
FY 2025-26
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 6.5553 | 6.5553 | 0 | 6 | 6 |  |  | 6 | 0 | 6 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 5.1899 | 5.0853 | 0.10458 | 8 | 8 |  |  | 8 | 0.10458 | 8 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 0 | 0 | 0 | 26.1 | 26.1 |  |  | 26.1 | 0 | 26.1 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 5.4267 | 4.0159 | 1.4107 | 11.3433 | 12.7541 |  |  | 12.7541 | 0 | 12.7541 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0 | 5 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 5.847 | 5.847 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0 | 0 | 1.4
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 0 | 0 | 0 | 4.61 | 4.61 |  |  | 4.61 | 0 | 4.61 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 14.6904 | 14.6904 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.6 | 82.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.08 | 7.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 7.347 | 6.7649 | 0.5821 | 7.993 | 8.5751 |  |  | 8.5751 | 0 | 8.5751 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 0 | 0 | 0 | 24.03 | 24.03 |  |  | 24.03 | 0 | 24.03 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 0 | 0 | 0 | 4.33 | 4.33 |  |  | 4.33 | 0 | 4.33 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0 | 0 | 0 | 0.48 | 0.48 |  |  | 0.48 | 0 | 0.48 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 0 | 0 | 0 | 1.93 | 1.93 |  |  | 1.93 | 0 | 1.93 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 0 | 0 | 0 | 1.76 | 1.76 |  |  | 1.76 | 0 | 1.76 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 0 | 0 | 0 | 1.25 | 1.25 |  |  | 1.25 | 0 | 1.25 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 0 | 0 | 0 | 9.35 | 9.35 |  |  | 9.35 | 0 | 9.35 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0 | 0 | 0 | 0.31 | 0.31 |  |  | 0.31 | 0 | 0.31 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 0 | 0 | 0 | 2.74 | 2.74 |  |  | 2.74 | 0 | 2.74 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 0 | 0 | 0 | 7.63 | 7.63 |  |  | 7.63 | 0 | 7.63 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 0 | 0 | 0 | 18.67 | 18.67 |  |  | 18.67 | 0 | 18.67 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 0 | 0 | 0 | 3.93 | 3.93 |  |  | 3.93 | 0 | 3.93 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 32.56 | 32.56 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 16.9 | 16.9 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 18.32 | 17.32 | 1 | 0 | 1 |  |  | 1 | 0 | 1 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 179.49 | 179.49 | 0 | 658.11 | 658.11 |  |  | 658.11 | 0 | 423.09 | 235.02
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 7.0966 | 7.0966 |  |  | 7.0966 | 0 | 7.0966 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 6.077 | 6.077 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 2.709 | 2.709 | 0 | 2.571 | 2.571 |  |  | 2.571 | 0 | 2.571 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.7287 | 0 | 1.7287 | 0.2513 | 1.98 |  |  | 1.98 | 0 | 1.98 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 116.38 | 116.38 | 0 | 116.38 | 116.38 |  |  | 116.38 | 0 | 91.08 | 25.3
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | #VALUE! | 128.16 | #VALUE! | 19.22 | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 66.9437 | 66.9437 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 1.1231 | 1.1231 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 2.8072 | 2.8072 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 16.8707 | 16.8707 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 35.944 | 35.944 |  |  | 35.944 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 5.66 | 5.66 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 8.17 | 8.17 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 4.12 | 4.12 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 8.14 | 8.14 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 4.18 | 4.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 27.12 | 0 |  |  | 0 | 27.12
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 22.003 | 0 |  |  | 0 | 22.003
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 0 | 0 | 0 | 40.075 | 40.075 |  |  | 40.075 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 4.43 | 4.43 |  |  | 4.43 | 0 | 0 | 4.43
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 4.54 | 4.54 |  |  | 4.54 | 0 | 0 | 4.54
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 5.25 | 5.25 |  |  | 5.25 | 0 | 0 | 5.25
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 4.61 | 4.61 |  |  | 4.61 | 0 | 0 | 4.61
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 3.83 | 3.83 |  |  | 3.83 | 0 | 0 | 3.83
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 3.83 | 3.83 |  |  | 3.83 | 0 | 0 | 3.83
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 5.31 | 5.31 |  |  | 5.31 | 0 | 0 | 5.31
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 0 | 0 | 0 | 9.58 | 9.58 |  |  | 9.58 | 0 | 9.58 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 0 | 0 | 0 | 2.95 | 2.95 |  |  | 2.95 | 0 | 2.95 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 0 | 0 | 0 | 7.95 | 7.95 |  |  | 7.95 | 0 | 7.95 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 17.46 | 17.46 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 11.9 | 11.9 |  |  | 11.9 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 18.49 | 18.49 |  |  | 18.49 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 16.5 | 16.5 |  |  | 16.5 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 3.05 | 3.05 |  |  | 3.05 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 2.21 | 2.21 |  |  | 2.21 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 1.39 | 1.39 |  |  | 1.39 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 1.95 | 1.95 |  |  | 1.95 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 4.15 | 4.15 |  |  | 4.15 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 6.07 | 6.07 |  |  | 6.07 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 9.01 | 9.01 |  |  | 9.01 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 9.86 | 9.86 |  |  | 9.86 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 24.96 | 24.96 |  |  | 24.96 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 0 | 0 | 0 | 5.42 | 5.42 |  |  | 5.42 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 0 | 0 | 0 | 35.82 | 35.82 |  |  | 35.82 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 15.5 | 15.5 |  |  | 15.5 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 0 | 0 | 0 | 18.74 | 18.74 |  |  | 18.74 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 0 | 0 | 0 | 4.94 | 4.94 |  |  | 4.94 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 0 | 0 | 0 | 19 | 19 |  |  | 19 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 0 | 0 | 0 | 7.3 | 7.3 |  |  | 7.3 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 0 | 0 | 0 | 12.52 | 12.52 |  |  | 12.52 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0 | 0 | 0 | 0.81 | 0.81 |  |  | 0.81 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 0 | 0 | 0 | 1.1 | 1.1 |  |  | 1.1 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 0 | 0 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 0 | 0 | 0 | 38 | 38 |  |  | 38 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 0 | 0 | 0 | 28.56 | 28.56 |  |  | 28.56 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 32.28 | 32.28 |  |  | 32.28 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 52 | 52 |  |  | 52 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 52.62 | 52.62 |  |  | 52.62 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 25.42 | 25.42 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 0 | 0 | 0 | 9.81 | 9.81 |  |  | 9.81 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 0 | 0 | 0 | 15.07 | 15.07 |  |  | 15.07 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 44.31 | 44.31 |  |  | 44.31 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 28 | 28 |  |  | 28 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 0 | 0 | 0 | 20.19 | 20.19 |  |  | 20.19 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 0 | 0 | 0 | 18.81 | 18.81 |  |  | 18.81 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 17.55 | 17.55 |  |  | 17.55 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 0 | 0 | 0 | 39 | 39 |  |  | 39 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 25 | 0 |  |  | 0 | 25
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 6 | 0 |  |  | 0 | 6
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 0 | 0 | 0 | 3.78 | 3.78 |  |  | 3.78 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 0 | 0 | 0 | 4.05 | 4.05 |  |  | 4.05 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 0 | 0 | 0 | 7.01 | 7.01 |  |  | 7.01 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 0 | 0 | 0 | 6.34 | 6.34 |  |  | 6.34 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 0 | 0 | 0 | 8.43 | 8.43 |  |  | 8.43 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 0 | 0 | 0 | 14.905 | 14.905 |  |  | 14.905 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 0 | 0 | 0 | 3.755 | 3.755 |  |  | 3.755 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 0 | 0 | 0 | 6.11 | 6.11 |  |  | 6.11 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 0 | 0 | 0 | 3.325 | 3.325 |  |  | 3.325 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 0 | 0 | 0 | 1.785 | 1.785 |  |  | 1.785 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 200 | 200 |  |  | 200 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 42 | 42 |  |  | 42 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 0 | 0 | 0 | 200 | 200 |  |  | 200 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 6.8762 | 6.8762 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 3.612 | 3.612 | 0 | 0 | 0 |  |  | 0 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.95 | 0 | 7.95 | 0 | 7.95 |  |  | 7.95 | 0
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 5.27 | 5.27 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 5.5874 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 9.09 | 9.09 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 9.95 | 9.95 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 4.9 | 4.9 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 0 | 0 | 0 | 2.24 | 2.24 |  |  | 2.24 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 0.55 | 0.55 | 0 | 2.02 | 2.02 |  |  | 2.02 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 0 | 0 | 0 | 4.2 | 4.2 |  |  | 4.2 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 0 | 0 | 0 | 4.55 | 4.55 |  |  | 4.55 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0 | 0 | 0 | 0.97 | 0.97 |  |  | 0.97 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 0 | 0 | 0 | 7.89 | 7.89 |  |  | 7.89 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 0 | 0 | 0 | 5.44 | 5.44 |  |  | 5.44 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 7.5 | 7.5 | 0 | 2.8 | 2.8 |  |  | 2.8 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 0 | 0 | 0 | 5.62 | 5.62 |  |  | 5.62 | 0
| Total |  |  |  | #VALUE! | 1824.7608 | #VALUE! | 2952.5172 | #VALUE! | 0 | 0 | #VALUE! | #VALUE!
FY 2026-27
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 12.5553 | 12.5553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 13.1899 | 13.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 16.77 | 16.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 7.247 | 7.247 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 14.6904 | 14.6904 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.6 | 82.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.08 | 7.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 15.34 | 15.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 24.03 | 24.03 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 4.33 | 4.33 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0.48 | 0.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 1.93 | 1.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 1.76 | 1.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0.31 | 0.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 2.74 | 2.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 7.63 | 7.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 18.67 | 18.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 32.56 | 32.56 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0 | 4.91 | 3.09
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 16.9 | 16.9 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 18.32 | 18.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 837.6 | 837.6 | 0 | 358.97 | 358.97 |  |  | 358.97 | 0 | 0 | 358.97
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 7.0966 | 7.0966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 6.077 | 6.077 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.98 | 1.98 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 232.76 | 232.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | #VALUE! | #VALUE! | #VALUE! | 108.94 | 0 |  |  | 0 | #VALUE! | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 66.9437 | 66.9437 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 1.1231 | 1.1231 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 2.8072 | 2.8072 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 16.8707 | 16.8707 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 35.944 | 35.944 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 5.66 | 5.66 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 8.17 | 8.17 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 4.12 | 4.12 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 8.14 | 8.14 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 4.18 | 4.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 0 | 27.12 | 0 | 27.12 |  |  | 27.12 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 22.003 | 0 | 22.003 | 44.006 | 66.009 |  |  | 66.009 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 40.075 | 40.075 | 0 | 40.075 | 40.075 |  |  | 40.075 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 0 | 0 | 0 | 7.19 | 7.19 |  |  | 7.19 | 0 | 7.19 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0 | 0.8 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 0 | 0 | 0 | 10.48 | 10.48 |  |  | 10.48 | 0 | 10.48 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 0 | 0 | 0 | 3.66 | 3.66 |  |  | 3.66 | 0 | 3.66 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 78.3255 | 78.3255 |  |  | 78.3255 | 0 | 0 | 78.3255
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.43 | 4.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.54 | 4.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.25 | 5.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.31 | 5.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 17.46 | 17.46 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 0 | 0 | 0 | 17.61 | 17.61 |  |  | 17.61 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 0 | 0 | 0 | 14.65 | 14.65 |  |  | 14.65 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0 | 0 | 0 | 0.29 | 0.29 |  |  | 0.29 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 13.8 | 13.8 |  |  | 13.8 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 10.19 | 10.19 |  |  | 10.19 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 2.55 | 2.55 |  |  | 2.55 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 8.35 | 8.35 |  |  | 8.35 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 17 | 17 |  |  | 17 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 11.9 | 11.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 18.49 | 18.49 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.39 | 1.39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.95 | 1.95 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 6.07 | 6.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 9.86 | 9.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 24.96 | 24.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 118.75 | 118.75 |  |  | 118.75 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 31.56 | 31.56 |  |  | 31.56 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 5.42 | 5.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 35.82 | 35.82 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 5 | 5 | 0 | 28.47 | 28.47 |  |  | 28.47 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 15.5 | 15.5 | 0 | 56 | 56 |  |  | 56 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 18.74 | 18.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 12 | 12 | 0 | 12 | 12 |  |  | 12 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 4.94 | 4.94 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 0 | 0 | 0 | 24 | 24 |  |  | 24 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 19 | 19 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 7.3 | 7.3 | 0 | 10 | 10 |  |  | 10 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 12.52 | 12.52 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 2 | 2 | 0 | 4.35 | 4.35 |  |  | 4.35 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 1.1 | 1.1 | 0 | 5.7 | 5.7 |  |  | 5.7 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 0 | 0 | 0 | 1.8 | 1.8 |  |  | 1.8 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 1.4 | 1.4 | 0 | 5 | 5 |  |  | 5 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 24.304 | 24.304 |  |  | 24.304 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 0 | 0 | 0 | 3.89 | 3.89 |  |  | 3.89 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 28.56 | 28.56 | 0 | 28.56 | 28.56 |  |  | 28.56 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 32.28 | 32.28 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 52 | 52 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 52.62 | 52.62 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 25.42 | 25.42 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 0 | 0 | 0 | 3.2 | 3.2 |  |  | 3.2 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 0 | 0 | 0 | 5.2 | 5.2 |  |  | 5.2 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0 | 0 | 0 | 0.75 | 0.75 |  |  | 0.75 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 0 | 0 | 0 | 24 | 24 |  |  | 24 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 9.81 | 9.81 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 44.31 | 44.31 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 26 | 26 |  |  | 26 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 0 | 0 | 0 | 8.1 | 8.1 |  |  | 8.1 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 15 | 15 | 0 | 15 | 15 |  |  | 15 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 0 | 0 | 0 | 23.5 | 23.5 |  |  | 23.5 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 20 | 20 | 0 | 20 | 20 |  |  | 20 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 5.5 | 5.5 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 5 | 5 | 0 | 3 | 3 |  |  | 3 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 28 | 28 | 0 | 28 | 28 |  |  | 28 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 20.19 | 20.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 18.81 | 18.81 | 0 | 19.37 | 19.37 |  |  | 19.37 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 17.55 | 17.55 | 0 | 10 | 10 |  |  | 10 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 18.81 | 18.81 |  |  | 18.81 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 25 | 0 | 25 | 0 | 0 |  |  | 0 | 25
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 6 | 0 | 6 | 0 | 0 |  |  | 0 | 6
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 10 | 10 | 0 | 27.57 | 27.57 |  |  | 27.57 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 15 | 15 | 0 | 32.15 | 32.15 |  |  | 32.15 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 15 | 15 | 0 | 12.05 | 12.05 |  |  | 12.05 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 15 | 15 | 0 | 15 | 15 |  |  | 15 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 15 | 15 | 0 | 15 | 15 |  |  | 15 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 6 | 6 | 0 | 4 | 4 |  |  | 4 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 4.05 | 4.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 6.34 | 6.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 8.43 | 8.43 | 0 | 8.43 | 8.43 |  |  | 8.43 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 14.905 | 14.905 | 0 | 14.905 | 14.905 |  |  | 14.905 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 0 | 0 | 0 | 44 | 44 |  |  | 44 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 3.755 | 3.755 | 0 | 3.755 | 3.755 |  |  | 3.755 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 6.11 | 6.11 | 0 | 6.11 | 6.11 |  |  | 6.11 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 3.325 | 3.325 | 0 | 3.325 | 3.325 |  |  | 3.325 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 1.785 | 1.785 | 0 | 1.785 | 1.785 |  |  | 1.785 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 0 | 0 | 0 | 293 | 293 |  |  | 293 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 0 | 0 | 0 | 100 | 100 |  |  | 100 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 200 | 200 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 42 | 42 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 200 | 200 | 0 | 68 | 68 |  |  | 68 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 0 | 0 | 0 | 8.9 | 8.9 |  |  | 8.9 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 0 | 0 | 0 | 10.82 | 10.82 |  |  | 10.82 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 0 | 0 | 0 | 7.88 | 7.88 |  |  | 7.88 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 8.3762 | 8.3762 | 0 | 0 | 0 |  |  | 0 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 3.612 | 3.612 | 0 | 0 | 0 |  |  | 0 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 5.27 | 5.27 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 5.5874 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 9.09 | 9.09 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 9.95 | 9.95 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 4.9 | 4.9 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 2.57 | 2.57 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 4.2 | 4.2 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 4.55 | 4.55 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0.97 | 0.97 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 7.89 | 7.89 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 5.44 | 5.44 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 5.62 | 5.62 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | 2320.6305 | 2260.8135 | 0 | 0 | 2260.8135 | #VALUE!
FY 2027-28
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 12.5553 | 12.5553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 13.1899 | 13.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 16.77 | 16.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 7.247 | 7.247 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 14.6904 | 14.6904 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.6 | 82.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.08 | 7.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 15.34 | 15.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 24.03 | 24.03 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 4.33 | 4.33 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0.48 | 0.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 1.93 | 1.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 1.76 | 1.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0.31 | 0.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 2.74 | 2.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 7.63 | 7.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 18.67 | 18.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 32.56 | 32.56 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 16.9 | 16.9 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 18.32 | 18.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 1196.57 | 1196.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 7.0966 | 7.0966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 6.077 | 6.077 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.98 | 1.98 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 232.76 | 232.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 |  |  | 0 | #VALUE! | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 66.9437 | 66.9437 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 1.1231 | 1.1231 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 2.8072 | 2.8072 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 16.8707 | 16.8707 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 35.944 | 35.944 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 5.66 | 5.66 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 8.17 | 8.17 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 4.12 | 4.12 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 8.14 | 8.14 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 4.18 | 4.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 66.009 | 66.009 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 80.15 | 80.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 7.19 | 7.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 10.48 | 10.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 78.3255 | 78.3255 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.43 | 4.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.54 | 4.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.25 | 5.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.31 | 5.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 17.46 | 17.46 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 17.61 | 17.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 14.65 | 14.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0.29 | 0.29 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 13.8 | 13.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 10.19 | 10.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 8.35 | 8.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 11.9 | 11.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 18.49 | 18.49 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.39 | 1.39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.95 | 1.95 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 6.07 | 6.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 9.86 | 9.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 24.96 | 24.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 118.75 | 118.75 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 31.56 | 31.56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 5.42 | 5.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 35.82 | 35.82 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 33.47 | 33.47 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 71.5 | 71.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 18.74 | 18.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 24 | 24 | 0 | 12 | 12 |  |  | 12 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 4.94 | 4.94 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 19 | 19 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 17.3 | 17.3 | 0 | 10 | 10 |  |  | 10 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 12.52 | 12.52 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 6.35 | 6.35 | 0 | 1 | 1 |  |  | 1 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 6.8 | 6.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 6.4 | 6.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 24.304 | 24.304 | 0 | 24.304 | 24.304 |  |  | 24.304 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 57.12 | 57.12 | 0 | 28.56 | 28.56 |  |  | 28.56 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 32.28 | 32.28 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 52 | 52 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 52.62 | 52.62 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 25.42 | 25.42 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 6.25 | 6.25 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 0 | 0 | 0 | 15.85 | 15.85 |  |  | 15.85 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 0.75 | 0.75 | 0 | 0.75 | 0.75 |  |  | 0.75 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 9.81 | 9.81 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 1.5 | 1.5 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 0 | 0 | 0 | 35 | 35 |  |  | 35 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 44.31 | 44.31 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 40 | 40 |  |  | 40 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 30 | 30 | 0 | 15 | 15 |  |  | 15 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 23.5 | 23.5 | 0 | 23.5 | 23.5 |  |  | 23.5 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 40 | 40 | 0 | 20 | 20 |  |  | 20 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 56 | 56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 20.19 | 20.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 38.18 | 38.18 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 27.55 | 27.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 18.81 | 18.81 | 0 | 19.75 | 19.75 |  |  | 19.75 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 0 | 0 | 0 | 16 | 16 |  |  | 16 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 5 | 5 | 0 | 3 | 3 |  |  | 3 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 100 | 100 |  |  | 100 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 25 | 0 | 25 | 0 | 0 |  |  | 0 | 25
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 15 | 0 |  |  | 0 | 15
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 6 | 0 | 6 | 0 | 0 |  |  | 0 | 6
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 10 | 0 |  |  | 0 | 10
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 37.57 | 37.57 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 47.15 | 47.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 27.05 | 27.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 4.05 | 4.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 6.34 | 6.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 16.86 | 16.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 29.81 | 29.81 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 44 | 44 | 0 | 44 | 44 |  |  | 44 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 0 | 0 | 0 | 27.5 | 27.5 |  |  | 27.5 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 0 | 0 | 0 | 15 | 15 |  |  | 15 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 7.51 | 7.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 12.22 | 12.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 6.65 | 6.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 3.57 | 3.57 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 293 | 293 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 200 | 200 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 42 | 42 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 268 | 268 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 12.5 | 12.5 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 8.9 | 8.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 10.82 | 10.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 7.88 | 7.88 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 60 | 60 |  |  | 60 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 55 | 55 |  |  | 55 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 8.3762 | 8.3762 | 0 | 0 | 0 |  |  | 0 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 3.612 | 3.612 | 0 | 0 | 0 |  |  | 0 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 5.27 | 5.27 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 5.5874 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 9.09 | 9.09 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 9.95 | 9.95 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 4.9 | 4.9 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 2.57 | 2.57 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 4.2 | 4.2 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 4.55 | 4.55 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0.97 | 0.97 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 7.89 | 7.89 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 5.44 | 5.44 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 5.62 | 5.62 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | 814.964 | 789.964 | 0 | 0 | 789.964 | #VALUE!
FY 2028-29
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 12.5553 | 12.5553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 13.1899 | 13.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 16.77 | 16.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 7.247 | 7.247 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 14.6904 | 14.6904 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.6 | 82.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.08 | 7.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 15.34 | 15.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 24.03 | 24.03 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 4.33 | 4.33 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0.48 | 0.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 1.93 | 1.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 1.76 | 1.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0.31 | 0.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 2.74 | 2.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 7.63 | 7.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 18.67 | 18.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 32.56 | 32.56 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 16.9 | 16.9 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 18.32 | 18.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 1196.57 | 1196.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 7.0966 | 7.0966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 6.077 | 6.077 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.98 | 1.98 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 232.76 | 232.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 |  |  | 0 | #VALUE! | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 66.9437 | 66.9437 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 1.1231 | 1.1231 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 2.8072 | 2.8072 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 16.8707 | 16.8707 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 35.944 | 35.944 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 5.66 | 5.66 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 8.17 | 8.17 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 4.12 | 4.12 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 8.14 | 8.14 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 4.18 | 4.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 66.009 | 66.009 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 80.15 | 80.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 7.19 | 7.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 10.48 | 10.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 78.3255 | 78.3255 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.43 | 4.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.54 | 4.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.25 | 5.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.31 | 5.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 17.46 | 17.46 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 17.61 | 17.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 14.65 | 14.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0.29 | 0.29 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 13.8 | 13.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 10.19 | 10.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 8.35 | 8.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 11.9 | 11.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 18.49 | 18.49 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.39 | 1.39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.95 | 1.95 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 6.07 | 6.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 9.86 | 9.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 24.96 | 24.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 118.75 | 118.75 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 31.56 | 31.56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 5.42 | 5.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 35.82 | 35.82 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 33.47 | 33.47 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 71.5 | 71.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 18.74 | 18.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 36 | 36 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 4.94 | 4.94 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 19 | 19 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 27.3 | 27.3 | 0 | 10 | 10 |  |  | 10 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 12.52 | 12.52 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 7.35 | 7.35 | 0 | 5 | 5 |  |  | 5 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 6.8 | 6.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 6.4 | 6.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 48.608 | 48.608 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 0 | 0 | 0 | 8.2 | 8.2 |  |  | 8.2 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 0 | 0 | 0 | 2.45 | 2.45 |  |  | 2.45 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 0 | 0 | 0 | 15.75 | 15.75 |  |  | 15.75 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 85.68 | 85.68 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 32.28 | 32.28 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 52 | 52 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 52.62 | 52.62 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 25.42 | 25.42 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 12.5 | 12.5 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 3.2 | 3.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 15.85 | 15.85 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 0 | 0 | 0 | 8.5 | 8.5 |  |  | 8.5 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 9.81 | 9.81 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 44.31 | 44.31 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 47 | 47 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 60 | 60 | 0 | 20 | 20 |  |  | 20 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 56 | 56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 20.19 | 20.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 38.18 | 38.18 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 27.55 | 27.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 38.56 | 38.56 | 0 | 20.73 | 20.73 |  |  | 20.73 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 0 | 0 | 0 | 85.5299 | 85.5299 |  |  | 85.5299 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 25 | 0 | 25 | 0 | 0 |  |  | 0 | 25
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 15 | 0 | 15 | 0 | 0 |  |  | 0 | 15
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 6 | 0 | 6 | 0 | 0 |  |  | 0 | 6
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 10 | 0 | 10 | 0 | 0 |  |  | 0 | 10
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 37.57 | 37.57 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 47.15 | 47.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 27.05 | 27.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 4.05 | 4.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 6.34 | 6.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 16.86 | 16.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 29.81 | 29.81 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 88 | 88 | 0 | 44 | 44 |  |  | 44 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 27.5 | 27.5 | 0 | 27.5 | 27.5 |  |  | 27.5 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 30 | 30 | 0 | 30 | 30 |  |  | 30 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0 | 0 | 0 | 0.75 | 0.75 |  |  | 0.75 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 7.51 | 7.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 12.22 | 12.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 6.65 | 6.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 3.57 | 3.57 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 293 | 293 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 0 | 0 | 0 | 300 | 300 |  |  | 300 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 200 | 200 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 42 | 42 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 268 | 268 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 8.9 | 8.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 10.82 | 10.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 7.88 | 7.88 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 60 | 60 | 0 | 60 | 60 |  |  | 60 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 50 | 50 | 0 | 50 | 50 |  |  | 50 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 55 | 55 | 0 | 55 | 55 |  |  | 55 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 25 | 25 | 0 | 25 | 25 |  |  | 25 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 8.3762 | 8.3762 | 0 | 0 | 0 |  |  | 0 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 3.612 | 3.612 | 0 | 0 | 0 |  |  | 0 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 5.27 | 5.27 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 5.5874 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 9.09 | 9.09 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 9.95 | 9.95 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 4.9 | 4.9 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 2.57 | 2.57 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 4.2 | 4.2 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 4.55 | 4.55 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0.97 | 0.97 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 7.89 | 7.89 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 5.44 | 5.44 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 5.62 | 5.62 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | 879.1599 | 879.1599 | 0 | 0 | 879.1599 | #VALUE!
FY 2029-30
a) DPR Schemes
(i) In Principally Approved By MERC
1 | Boiler & Turbine Improvement | MERC/CAPEX/20102011/01755 | 2010-11-25 | 181.827 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Installation of Sonic soot blowers for unit 5, 6 and 7 - Sonic soot blowers will be installed in LTSH and Eco zones (48 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.06 | 0.44763 | 0.44763 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.2 | Installation of smart soot blower system for unit 5 and 6 boiler (Smart cannons- 8 nos, sealing and cooling air fans – 8 nos, heat flux sensors- 32 nos, HP pump – 1 no | MERC/CAPEX/20102011/01755 | 2010-11-25 | 11.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.3 | Total Replacement of boiler skin and air duct insulation of unit 3 to 7 (Ribbed aluminium cladding – 2000 m2, GI cladding, U bonded rock wool mattresses 100 mm thick )(consists of two schemes) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 12.3 | 10.0166 | 10.0166 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.4 | Redesign of the burner equipment with superior grade steel alloys and hardened with weld overlays of tungsten carbide or chromium carbides ( Coal tips-104 nos, coal nozzle-104 nos, weld overlay on coal tip by tungsten carbide – 104 nos, weld overlay on coal nozzle by tungsten carbide- 104 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 7.52 | 3.8602 | 3.8602 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.5 | Replacement of ECO coils with gas velocity profiles and erosion control devices for Unit 1 to 6 (U7 middle eco- 69 assemblies, U5&6 middle and lower eco- 65 assemblies each) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 43.2 | 56.1594 | 56.1594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.6 | Replacement of LTSH coils with improved tube materials, gas velocity profiles and erosion control devices for unit 3 to 7 (U5&6 LTSH terminal tubes – 58 assemblies) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 23.4 | 12.9173 | 12.9173 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.7 | Replacement of RH platens for Unit 5 & 6 (unit 5- 46 coils, unit 6- 28 coils) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 27.6 | 11.3681 | 11.3681 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.8 | Gas proportioning dampers, flue gas, primary and secondary air dampers should be retrofitted with cold hardened material (SAH dampers- 4 nos) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 1.43 | 1.8769 | 1.8769 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.9 | Replacement of flue gas ducting zones prone to erosion with 6 to 8 mm high grade material and insulation of the flue gas ducts may be replaced (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 5, 6 and 7 (Straight wear plates – 440 m2, curved wear plates – 400 m2) | MERC/CAPEX/20102011/01755 | 2010-11-25 | 3.5 | 4.2488 | 4.2488 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.10 | Reducing the pressure drop across APH in Unit 5, 6 and 7 (CFD analysis and design modification in APH inlet duct, Manufacture and supply and erection of carbide overlay divertet plates – 600 m2 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2 | 2.0468 | 2.0468 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.11 | Reducing the pressure drop across ESP | MERC/CAPEX/20102011/01755 | 2010-11-25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.12 | Replacement of CT fan blades from GRP to FRP and resizing the motor to 75 kw | MERC/CAPEX/20102011/01755 | 2010-11-25 | 2.913 | 1.6187 | 1.6187 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.13 | Improving the BFP efficiency by overhauling of pump and motors for unit 3 &4 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 15 | 14.8516 | 14.8516 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.14 | During the next capital overhaul, restoration of the steam paths through steam path audits for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.604 | 0.089776 | 0.089776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.15 | Continuous monitoring system for CO in the furnace and flue gas ducting zone for Unit 3 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.16 | Oxygen measurement must be introduced at APH inlet and after ID fan outlet for unit 1 to 7 | MERC/CAPEX/20102011/01755 | 2010-11-25 | 4.91 | 3.5436 | 3.5436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20102011/01755 | 2010-11-25 | 10.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Input source Measurement | MERC/CAPEX/20112012/00925 | 2011-07-06 | 20.9901 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Installation of Guided wave radar type level indicators for all fuel oil tanks of unit-1 to 7 DTFA 15 tanks and MTFA 15 tanks (total 30 tanks) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0398 | 0.707 | 0.707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Installation of mass based oil flow meters with provision for continuous digital transfer (20 transmitters) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.138 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of 54 Nos. of ultrasonic type Flow measurement transmitters for water consumption monitoring | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.0657 | 1.7643 | 1.7643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Trivector Meters for Auxiliary power measurement of GT (7 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.0211 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Standard Meters for Auxiliary power measurement for sp. Consumption of Auxiliary transformer, Limbs and auxiliaries. | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.4954 | 0.29784 | 0.29784 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Belt weighers (28 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 3.3196 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | In motion weigh bridge (10 Nos). | MERC/CAPEX/20112012/00925 | 2011-07-06 | 4.5396 | 0.19084 | 0.19084 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Bunker level transmitters (50 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 2.5285 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Flap Gate sensors (120 Nos.) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.1225 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.10 | PLC (20 Nos) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 0.5333 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.11 | Cables (20,000 meters estimated) | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.0216 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00925 | 2011-07-06 | 1.165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | ESP Restoration/Refurbishment | MERC/CAPEX/20112012/00939 | 2011-07-07 | 53.99 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Replacement of all emitting coils and collecting plates of U#5 ESP of all four pass of field 2nd, 3rd & 4th | MERC/CAPEX/20112012/00939 | 2011-07-07 | 11.7 | 8.6202 | 8.6202 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.2 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#6 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 15.6 | 12.5553 | 12.5553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.3 | Replacement of all emitting coils and collecting plates of all four pass of field 1 to 4, U#7 ESP | MERC/CAPEX/20112012/00939 | 2011-07-07 | 16.02 | 13.1899 | 13.0853 | 0.10458 | 0 | 0 |  |  | 0 | 0.10458 | 0 | 0
3.4 | Ash evacuation system on existing dummy hoppers of Flue gas duct from APH outlet to ESP inlet of U#5 & 6. | MERC/CAPEX/20112012/00939 | 2011-07-07 | 0.95 | 0.92199 | 0.92199 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/00939 | 2011-07-07 | 9.72 | 0.03865 | 0.03865 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Control & Instrumentation up-gradation of CSTPS Unit 5 & 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 57.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Control & Instrumentation up-gradation of CSTPS Unit 5 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Control & Instrumentation up-gradation of CSTPS Unit 6 | MERC/CAPEX/20112012/01908 | 2011-11-03 | 26.1 | 26.1 | 26.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20112012/01908 | 2011-11-03 | 5.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Alternate water supply Scheme for Chandrapur T.P.S as a crisis management scheme | MERC/CAPEX/20112012/02443 | 2012-01-03 | 229.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Complete Track Renovation (CTR) work of rail track from Chandrapur Vivekanand Nagar railway stations to exchange yard and bulb line of BOBR at CSTPS siding maintained by railway authority | MERC/CAPEX/20122013/00818 | 2012-07-10 | 16.77 | 16.77 | 16.77 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of additional IDCT to improve performance of existing condenser cooling system of CSTPS Unit 5 & 6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 29.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction for U#5 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 11.2318 | 19.3782 | 19.3782 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.2 | Construction for U#6 | MERC/CAPEX/20122013/00827 | 2012-07-10 | 14.968 | 23.1899 | 23.1899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00827 | 2012-07-10 | 3.0802 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Upgradation of IDCT Unit 5 | MERC/CAPEX/20122013/00914 | 2012-07-18 | 18.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Cooling Tower IDCT for Unit-5A | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.2 | Cooling Tower IDCT for Unit-5B | MERC/CAPEX/20122013/00914 | 2012-07-18 | 8.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/00914 | 2012-07-18 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | LPT Retrofit at Chandrapur TPS Units 3 & 4 | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 107.8364 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Design, Engineering, Supply and Retrofitting of LP Cylinder with Modified Bladed rotor without Bauman’s Stages, diaphragms, liners, Gland sealing and exhaust hood spray. (total 2 units) | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 101.8526 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00823 | 2013-07-09 | 5.9838 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Modification in Ash Handling Plant at Chandrapur TPS unit 5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 15.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | Complete series replacement in U-5 & 6 | MERC/CAPEX/20122013/02104 | 2013-01-07 | 7.12 | 1.408 | 1.408 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | Extension of ash lines inside ash bund (9000 Rmt) | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.03 | 2.4824 | 2.4824 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | Replacement ash line worn out pipes | MERC/CAPEX/20122013/02104 | 2013-01-07 | 3.6 | 4.4211 | 4.4211 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20122013/02104 | 2013-01-07 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Fully Integrated Security Surveillance System | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 54.1979 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Long range cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 12.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Laser fence sensors/buried cable | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 6.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.3 | PTZ/fixed cameras | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 8.075 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.4 | Command & control /video wall | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.5 | Communication | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.4595 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.6 | RFID | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.83 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.7 | LPR | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.8 | Electricals/networking | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 2.8674 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.9 | Infrastructure | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.896 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20122013/00190 | 2013-04-18 | 3.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Revamping of existing SWAS installed at U#1 to 4 and commissioning of new (AFGC) System of U#5&7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 10.0839 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | AFGC U 5,7 | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 2.08 | 2.037 | 2.037 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Dismantling and revamping of Sample panels of Unit 1 to 4. (4 Nos.) | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 7.1339 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01366 | 2013-10-04 | 0.87 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Replacements Platen Super Heater & Eco Additional of U-5 & U-6 and Upper & Lower LTSH & Eco Bottom assemblies of U-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 76.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Platen super heater assemblies – 24 nos each for Unit-5 & 6(2 sets) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 32.76 | 11.6609 | 11.6609 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2 | Economizer additional Assemblies along with cassette baffles – 65 Nos. each for unit- 5 & 6 (2Set ) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 3.88 | 3.5012 | 3.5012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | Upper LTSH Assemblies along with cassette baffles – 62 Nos. each for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 9.81 | 4.9253 | 4.9253 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Lower LTSH Assemblies along with cassette baffles – 62Nos. for unit – 7 (1 Set) | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 4.76 | 2.7668 | 2.7668 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | Lower Eco + Eco additional along with cassette baffles for Unit-7 | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 13.41 | 6.3206 | 6.3206 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | Work Cost for Replacement of above Assemblies. | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 5.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01936 | 2014-01-08 | 6.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Complete IPT Module for 500MW Unit-7 and Fully Bladed Rotor for LP Turbine of 500 MW Unit-5, 6, & 7 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 83.8237 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | IPT Module complete Type-M30-63 with advance class blading suitable for 500 MW Chandrapur Unit-7, Khaperkheda 1x500, Bhusawal 2x500 | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 48.0394 | 48.0394 | 48.0394 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Fully bladed dynamically balanced LP Rotor for 500 MW Units-5,6 &7 at Chandrapur STPS | MERC/TECH 1/CAPEX/20132014/01334 | 2013-10-01 | 35.7843 | 35.7843 | 35.7843 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Performance Improvement of Air Preheater Unit 1 & 2 CSTPS Chandrapur | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 11.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | supply of MSERW / high frequency induction welding tubes for Air pre-heater in Unit 1&2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 8.8554 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Compete Replacement of the air heater tubes in top ,intermediate and bottom bank(LHS and RHS) of unit 1 & 2 | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 2.1445 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/01431 | 2013-10-18 | 0.1701 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Procurement & Replacement of heating elements (baskets) of primary and secondary air pre-heaters of unit # 5 & 6 | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 11.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-5 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.2319 | 4.2319 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Primary & Secondary Air Pre-heater baskets hot end, intermediate & cold end (2 sets) for U-6 (Including works cost) | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 5.5023 | 4.5024 | 4.5024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00432 | 2014-06-02 | 0.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Procurement of moving blades for LP Turbine, Control Fluid Pumps & AOP of 500MW Unit 5,6 &7 | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 19.3102 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Moving blades for LPT—2L Moving blades for LPT—2R Moving blades for LPT—3L Moving blades for LPT—3R | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 13.5092 | 5.3885 | 5.3885 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | 1. Control Fluid Pump for 500 MW Unit-5&6_KSB Make- Type : WKVM 100/1+4 2. Control Fluid Pump for 500 MW Unit-7_KSB Make- Type : WKVM 80/1+3 3. Aux. Oil Pump for Main Turbine of 500 MW Unit-5,6& 7 KSB Make- Type : ETA 150-50VL | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 4.551 | 7.247 | 7.247 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/0010 | 2014-10-16 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Procurement of Gear Box & Wear Resistance liners for coal mills of Unit#5&6 & Supply of Gear Box for Coal Mills of Unit#7 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 11.9145 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Complete bevel gear stage consisting of pinion with part nos 100, 106, 107, 109, 110, 158, 159 and gear with part nos 102, 401, 402, 12 X 403 of Flender make Bocholt KMS 850 Gear Boxes of XRP-1043 Coal Mill in Unit#5&6. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4388 | 1.6219 | 1.6219 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Manufacturing, Supply and Application of Wear Resistance Liners inside the mill body of XRP 1043 Coal Mill in unit-5&6 | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 2.2757 | 2.2757 | 2.2757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Complete Gear Box type H2C630 without coupling, without lubrication unit. As per order CMD ref: 20/0900212-GA Dwg No 524932 and as per attached list for main reducer gear box of coal mill BBD 4772 in Unit#7. | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 4.4665 | 2.2258 | 2.2258 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/01220 | 2014-11-25 | 0.7335 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 & BFP cartridge for Unit 5, 6 & 7 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 13.1637 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Procurement of Cartridge Assembly for Boiler Feed Pump type FK 4E 36 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 4.87 | 2.8937 | 2.8937 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement & Replacement of Condenser tubes for 500MW Unit-6 | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 7.0937 | 6.1698 | 6.1698 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20142015/00950 | 2014-09-11 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | 210/500 MW CHP performance improvement | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 16.303 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Provision of over band suspended magnets for CHP-C. | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 1.077 | 0.90834 | 0.90834 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.2 | 1. Procurement of HT contactor for bunkering side auxiliary at CHP B 2. Procurement of HT contactor for unloading side Critical Auxiliary at CHP-B | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.759 | 2.8943 | 2.8943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.3 | Bulldozer BD-155 | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 5.12 | 7.9707 | 7.9707 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.4 | Modification of wagon tippler CHP-A | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 3.897 | 4.4884 | 4.4884 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/Cell No. 1/CAPEX/ 20152016/00634 | 2015-09-09 | 0.45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Improvement in Electrical Systems | MERC/CAPEX/20162017/00192 | 2016-05-10 | 10.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.1 | Station Battery set 1 & 2 of 220V, 2190 AH Capacity (2V X 110 Cells) New type Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.71 | 3.7131 | 3.7131 | 1e-07 | 0 | 0 |  |  | 0 | 1e-07 | 0 | 0
21.2 | The G1 & G2 Battery sets of 24V, 1825AH Capacity (13 Nos. cells X 2= 26 Nos. cells) plantetype Make- Exide | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.55 | 0.53016 | 0.53016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.3 | Replacement of 6.6 KV HT breakers at Ash Handling Plant by 6.6 KV SF6 contactors suitable for frequent ON/OFFs. | MERC/CAPEX/20162017/00192 | 2016-05-10 | 3.12 | 3.5539 | 3.5539 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.4 | Micro-processor based flame scanners at Unit#3&4 (210 MW) | MERC/CAPEX/20162017/00192 | 2016-05-10 | 2.34 | 3.3241 | 3.3241 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.5 | Supply, erection and commissioning of Generator Protection scheme as per enclosed material schedule and scope of work for Unit-6 | MERC/CAPEX/20162017/00192 | 2016-05-10 | 1.03 | 1.1916 | 1.1916 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/00192 | 2016-05-10 | 0.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22 | Implementation of MPCB related ESP performance Improvement schemes at Chandrapur STPS Unit 3 to 7 | MERC/CAPEX/20152016/00420 | 2016-08-02 | 18.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.1 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #3 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 3.9122 | 3.9122 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.2 | Supply of internals of ESP. ( model-2FAA-5 X 32-13290-2) 1st & 2nd fields in Unit #4 & Works | MERC/CAPEX/20152016/00420 | 2016-08-02 | 4.61 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.3 | Installation of SOx/ NOx analyzers for unit-3 to 7 along with all required hardware and software (Statutory requirement). | MERC/CAPEX/20152016/00420 | 2016-08-02 | 2.98 | 1.3773 | 1.3773 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
22.4 | Design, Engineering, Supply, Erection and Commissioning of High pressure MIST/FOG Generating System at Track hopper, WT 1 & 2 of 500MW, Crusher House, Transfer Points & Bunker house of 500MW | MERC/CAPEX/20152016/00420 | 2016-08-02 | 5.37 | 4.5728 | 4.5728 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20152016/00420 | 2016-08-02 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Performance Improvement & Life enhancement of 500MW CHP-B | MERC/CAPEX/20162017/01067 | 2016-11-28 | 18.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Life Enhancement of Stacker reclaimer of CHP-B. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 5.76 | 5.295 | 5.295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Renovation including replacement of hydraulic system of paddle feeder with up gradations at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 2.19 | 2.3148 | 2.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.3 | Renovation of hydraulic system of wagon tippler and side arm charger with procurement of its essential spares at CHPB. | MERC/CAPEX/20162017/01067 | 2016-11-28 | 10.33 | 11.7941 | 11.7941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01067 | 2016-11-28 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24 | Retrofitting of existing circuit breakers at Chandrapur STPS Unit-3, 4, 5, 6 and ODP-II | MERC/CAPEX/20162017/01475 | 2017-02-06 | 13.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.1 | Retrofitting of existing Circuit breakers of AHP motor feeders at Unit # 5 & 6 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.25 | 3.8744 | 3.8744 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.2 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –5 & Aundha Pump House (ODP-II) | MERC/CAPEX/20162017/01475 | 2017-02-06 | 3.46 | 3.5523 | 3.5523 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
24.3 | Retrofitting of existing Circuit breakers installed at Unit Boards at Unit –3&4 | MERC/CAPEX/20162017/01475 | 2017-02-06 | 6.19 | 4.5767 | 4.5767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01475 | 2017-02-06 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
25.1 | Construction of Quarter Guard, Bachelor Accomodation & Allied Structures in Phase I & II for Induction of CISF Security | MERC/CAPEX/20162017/01269 | 2017-01-02 | 14.686 | 14.6904 | 14.6904 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
26.1 | Pipe Conveyor System for Transporting Coal from Bhatadi Coal Mine to Chandrapur STPS. | MERC/CAPEX/20172018/4171 | 2017-09-08 | 196.26 | 256.8153 | 256.8153 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Procurement & replacement of Economizer upper assemblies of Unit-5,6 & hot Reheater coil complete set of Unit-3 of CSTPS | MERC/CAPEX/20172018/4071 | 2017-08-18 | 25.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | supply & replacement of Economizer Upper Assemblies of unit no.5 & 6 | MERC/CAPEX/20172018/4071 | 2017-08-18 | 18.25 | 8.283 | 8.283 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.2 | Supply & replacement of hot reheater coil complete set of Unit-3. | MERC/CAPEX/20172018/4071 | 2017-08-18 | 6.72 | 6.0757 | 6.0757 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4071 | 2017-08-18 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28 | Replacement of H2 Generator with new Hydrogen Generator (Non Asbestos Design), procurement of 3-phase TR sets for stage II & other electrical items for ORC at Chandrapur STPS.” | MERC/CAPEX/20172018/4686 | 2017-11-15 | 12.456 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.1 | Supply, Installation & Commissioning of Hydrogen Generator Model : HMXT 200 (Non Asbestos Design) | MERC/CAPEX/20172018/4686 | 2017-11-15 | 10.36 | 11.5758 | 11.5758 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.2 | Supply of 3 phase high frequency T-R sets for replacement of T-R sets of ESP Stg-II | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
28.3 | Replacement of HPSV High Mast Towers by Stadium LED High Mast at ORC ground CSTPS Chandrapur | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.536 | 0.51656 | 0.51656 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4686 | 2017-11-15 | 0.93 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29 | Procurement of Boiler Feed Booster Pumps to improve availability & performance of feed system, moving blades for LPT & Condenser Tubes of (3 x 500 MW) Units at Chandrapur STPS | MERC/CAPEX/20172018/0272 | 2018-02-23 | 15.49 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.1 | Procurement of Boiler Feed Booster pumps to improve availability and performance of Feed system of 500 MW Unit-5, 6 & 7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 2.01 | 2.115 | 2.115 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.2 | Procurement of moving blades for 500 MW Unit-5, 6 & 7 LPT at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 3.34 | 1.9274 | 1.9274 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
29.3 | Procurement & Replacement of Condenser Tubes in 500MW, Unit-7 at CSTPS, Chandrapur | MERC/CAPEX/20172018/0272 | 2018-02-23 | 9.02 | 8.8302 | 8.8302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0272 | 2018-02-23 | 1.12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30 | Renovation & Beautification of Colony at Chandrapur STPS | MERC/CAPEX/20182019/0644 | 2018-05-18 | 117.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.1 | Face- lifting and Renovation of staff quarters & related work at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 82.6 | 82.6 | 82.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.2 | Colony Internal Roads at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.08 | 7.08 | 7.08 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.3 | Development of existing open spaces and Garden at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 4.72 | 4.72 | 4.72 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
30.4 | Renovation of club building /community building and providing new swimming pool and other misc works including Architectural and Consultancy Charges at CSTPS, Chandrapur | MERC/CAPEX/20182019/0644 | 2018-05-18 | 15.34 | 15.34 | 15.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/0644 | 2018-05-18 | 7.83 | 10.9403 | 10.9403 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Fully Integrated Security Surveillance System | MERC/CAPEX/2018-19/066 | 2019-03-05 | 76.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | CLOSE CIRCUIT TELEVISION SYSTEM (CCTV), MOBILE DVR | MERC/CAPEX/2018-19/066 | 2019-03-05 | 24.03 | 24.03 | 24.03 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | FIRE ALARM SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 4.33 | 4.33 | 4.33 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | ACCESS CONTROL SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.48 | 0.48 | 0.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.4 | EPABX | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.93 | 1.93 | 1.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.5 | RADIO COMMUNICATION AND CONNECTIVITY (Wireless) | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.76 | 1.76 | 1.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.6 | ENTRY MANAGEMENT SYSTEM, TRUCK TRACKING SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.7 | NETWORKING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 9.35 | 9.35 | 9.35 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.8 | MESSAGE DISPLAY SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 0.31 | 0.31 | 0.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.9 | IP PA SYSTEM | MERC/CAPEX/2018-19/066 | 2019-03-05 | 2.74 | 2.74 | 2.74 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.10 | TOWERS, EARTHING /POLES, CONDUITING, DIGGING | MERC/CAPEX/2018-19/066 | 2019-03-05 | 7.63 | 7.63 | 7.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.11 | RDBMS, SERVER, WORKSTATIONS, IN CON. ROOM WITH FURINITURE DOCUMENTATION, CAMERA & ANALYTICS LICENSES | MERC/CAPEX/2018-19/066 | 2019-03-05 | 18.67 | 18.67 | 18.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.12 | ADDITIONAL CIVIL WORK | MERC/CAPEX/2018-19/066 | 2019-03-05 | 3.93 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32 | Provision of VFD panel along with bypasses arrangement for HT/LT conveyors & automation of control room at Coal Handling Plant-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 38.63 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.1 | Procurement, Installation and commissioning of MV/LT VFD panel along with bypass arrangement for HT/LT Conveyors of CHP-B | MERC/CAPEX/20182019/1240 | 2018-09-20 | 32.56 | 32.56 | 32.56 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
32.2 | Automation of Control Room of CHP-B Using PLC System | MERC/CAPEX/20182019/1240 | 2018-09-20 | 4.91 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20182019/1240 | 2018-09-20 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 15.2203 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
33.1 | Complete Track Renewal (CTR)/Renovation of existing Broad Gauge Railway Siding of 500MW Yard in CSTPS | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 14.2003 | 16.9 | 16.9 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/362 | 2019-07-11 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34 | Procurement of Spare Generator Rotor along with one set of Bearings for Unit # 5, 6 & 7 CSTPS, Chandrapur | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 41.4691 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
34.1 | Generator Rotor suitable for THDF 115/59 One Set of Bearings (Comprising of 2 nos. of bearings) | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 40.3591 | 42.1896 | 42.1896 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/129 | 2019-05-03 | 1.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 22.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
35.1 | Procurement of 2 NOS. OF 3100 HP, WDG-3A Locomotives for CSTPS, Chandrapur | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 21.66 | 22.8548 | 22.8548 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/1214 | 2019-12-23 | 0.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
36.1 | Replacement of 220 V Station Battery Sets & UPS Battery Sets of Unit# 5 & 6 and 24 V G1 G2 Battery sets of Unit# 5, 6 & 7 for 500MW Stage-III, CSTPS. | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 18.32 | 18.32 | 18.32 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/32 | 2020-09-30 | 0.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 656.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
37.1 | Flue Gas Desulphurization (FGD) System for 500 MW UnitS (Total 8 Nos) of MSPGCL (Chandrapur Unit # 5-7) | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 602.58 | 1196.57 | 1196.57 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/43 | 2020-12-14 | 53.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
38 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur (Parli DPR) | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | Replacement of ECO and LTSH coils to Unit-4 Chandrapur | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 9.4 | 9.3999 | 9.3999 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH1/CAPEX/20142015/01526 | 2015-01-29 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39 | Supply of complete gear box assembly for XRP-1043 coal mill at U-5 & U-6 for FY 2019-20 & FY 20-21 at CSTPS, Chandrapur | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.53 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
39.1 | Supply of complete gear box assembly for XRP-1043coal mill unit 5&6and complete lub oil system of XRP-1043Coal Mill in Unit-5&6. (Qty. 02 nos. one for each unit) | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 21.02 | 9.9521 | 9.9521 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/05 | 2021-05-19 | 0.51 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1 | AFGC/DFGC SYSTEM 210MW | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 1.1 | CSTPS U-1,2&4 | MERC/CAP/DPR/10/07/1149 | 2007-05-30 | 9.6 | 4.9831 | 4.9831 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4 | Construction of coal platform for Chandrapur TPS, Khaperkheda TPS & Parli TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 4.1 | Chandrapur TPS | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 10.36 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/CAPEX/20132014/00827 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5 | Procurement of energy efficient HT motors at Bhusawal TPS, Koradi TPS, Chandrapur TPS, khaperkheda TPS, Parli TPS & Paras TPS as insurance spares | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 16.956 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3a | CSTPS (U-3/4, 210 MW, 7Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 5.706 | 0.90661 | 0.90661 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 5.3b | CSTPS (U-5/6/7, 500 MW, 11Nos) | MERC/TECH 1/CAPEX/20142015/01218 | 2014-11-25 | 11.25 | 5.7542 | 5.7542 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.1 | CSTPS (U-1 to 7) ( 1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 1.3258 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.1 | Chandrapur STPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 7.0966 | 7.0966 | 7.0966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 4.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.9 | 0.26772 | 0.26772 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender for CSTPS | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.1847 | 2.1847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.1 | CSTPS Chandrapur | MERC/CAPEX/20172018/0177 | 2018-02-06 | 9.0742 | 9.6123 | 9.6123 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 11.13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.2 | Procurement of Complete set of assembly of baskets for air preheater of type tri-sector APH in27 VI(T) 80”CSTPS unit No-4 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 1.73 | 1.696 | 1.696 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.4 | Procurement of Complete set of assembly of baskets for air preheater of type bi-sector APH “BI-SECTOR 27VI 1250(1400)”in CSTPS unit no. 5 & 6 (500MW). (4 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 9.4 | 8.9105 | 8.9105 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.7552 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.1 | Electromagnetic Flow meters at various lines & Locations of CSTPS unit-3 to 7 | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 2.9127 | 2.8883 | 2.8883 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16.2 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & Operation & Maintenance for 1 Year & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84252 | 0.84252 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7 And Supply & Replacement of complete PVC Fills of cell of cooling tower of Unit-7 in ODP-II at CSTPS, Chandrapur | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 10.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.1 | Procurement of Condensate Extraction Pump for 500MW Unit-5, 6 & 7, CSTPS, Chandrapur as insurance spare | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 6.2 | 6.0121 | 6.0121 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
40.2 | Supply and replacement of complete PVC Fills of cell of cooling tower in Unit- 7 | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 4.39 | 4.3294 | 4.3294 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/ WFH/SBR/ 10 | 2021-06-10 | 0.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41 | Supply & Commissioning of Advanced Microprocessor based Fast Bus Transfer panels; Up-gradation of Thyristor based 24V & 220V DC battery chargers by SMPS Microprocessor based Battery Chargers at U-5,6 &7 and Generator Protection scheme at U-7, at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 14.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.1 | Supply & commissioning of Advanced Microprocessor based Fast Bus Transfer Panels for Unit#5,6,7, Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 6.08 | 6.077 | 6.077 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.2 | Up-gradation of thyristor based 24V & 220V DC Battery Chargers by SMPS Microprocessor based Battery Chargers at Stage-III, CSTPS, Chandrapur. | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 5.28 | 5.28 | 5.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
41.3 | Generator Protection Scheme U-7 | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 1.98 | 1.98 | 1.98 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0321 | 2022-07-18 | 0.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42 | ESP Upgradation of 5 Nos. of 210/500MW Units at Khaperkheda, Koradi & Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 219.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
42.1 | ESP Upgradation at Unit # 5 & 6, Chandrapur TPS | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 207.46 | 232.76 | 232.76 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0453 | 2022-09-29 | 11.98 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 115.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
43.1 | Flue Gas Desulphurization (FGD) System at Unit 3 & 4, Chandrapur | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 109.4 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 |  |  | 0 | #VALUE! | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0459 | 2023-09-05 | 5.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of 3 nos. of new 200MVA. 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS, Chandrapur | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 33.268 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
44.1 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 200MVA, 21/400/√3KV, Single phase Generator Transformers, BHEL make for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur including Erection & Commissioning of GTs and Freight & Transit Insurance charges | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 32.568 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/0409 | 2022-09-02 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
45 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M with construction of concrete dam (Waste Weir & Non overflow structure), construction of drain wells, approach to drain wells and raising of ash compartment for ash bund along with renewal of Ash Disposal Pipe Line Service Road with WBM treatment at CSTPS, Chandrapur | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 145.055 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
45.1 | Construction of 4th raising of existing Ash Bund from T.B.L. 198.00 M to T.B.L 201.00 M | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 101.8102 | 66.9437 | 66.9437 | 0 | 0 | 0 |  |  | 0 | 0
45.2 | Construction of New Drain Wells (12 Nos.) along with necessary connection to existing drain wells at CSTPS | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 1.708 | 1.1231 | 1.1231 | 0 | 0 | 0 |  |  | 0 | 0
45.3 | Construction of waste weir for raising of ash bund (Waste Weir & Non overflow structure) | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 4.2692 | 2.8072 | 2.8072 | 0 | 0 | 0 |  |  | 0 | 0
45.4 | Raising of Ash Compartment i.e. Lagoon in Ash Bund | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 25.6575 | 16.8707 | 16.8707 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2022-2023/MSPGCL/0458 | 2023-09-05 | 11.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 37.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
46.1 | Procurement of 03 Nos. of complete assembly of 3.3 KV, 300 KW Boiler Circulation Water Pump - Motors along with Impeller for Unit#5&6, 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 35.944 | 35.944 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0308 | 2024-05-17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47 | Performance Improvement & Life Extension Schemes for CHP of Unit 3 to 7 of CSTPS, Chandrapur | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 43.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
47.1 | Work of Renovation/Upgradation/Modification of Crusher House of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 5.66 | 5.66 | 5.66 | 0 | 0 | 0 |  |  | 0 | 0
47.2 | Work of Renovation/Upgradation/Modification of Belt Conveyor 10A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.17 | 8.17 | 8.17 | 0 | 0 | 0 |  |  | 0 | 0
47.3 | Work of Modification/Modernization of conveyor cable of 10 A/B/C of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.12 | 4.12 | 4.12 | 0 | 0 | 0 |  |  | 0 | 0
47.4 | Design, Engineering, Supply, Erection and commissioning of bypass chute with hydraulic cylinder & modification/renovation at JT-06 of CHPA of Unit 3&4 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 |  |  | 0 | 0
47.5 | Design, Engineering, Supply, Erection and Installation of Wear Resistance Chutes for Belt Conveyor System at CHPA/B of Unit 3to9 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 3.45 | 3.45 | 3.45 | 0 | 0 | 0 |  |  | 0 | 0
47.6 | Work of Modification/Renovation/Upgradation of Ventilation System of Track Hopper of CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.6 | 4.6 | 4.6 | 0 | 0 | 0 |  |  | 0 | 0
47.7 | Work of Renovation /Upgradation of Hydraulic System of Paddle Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 8.14 | 8.14 | 8.14 | 0 | 0 | 0 |  |  | 0 | 0
47.8 | Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPB of Unit 5,6&7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 4.18 | 4.18 | 4.18 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0560 | 2023-10-31 | 0.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 27.12 | 27.12 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 18.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 66.009 | 66.009 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y2 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 81.35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Procurement & replacement of 400 NB Cast Basalt Pipelines with the existing MSERW pipe of ash disposal system of Unit #5,6 & 7 at CSTPS, Chandrapur” under capital expenditure during the FY 2023-24. | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 80.15 | 80.15 | 80.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0475 Dt 06.08.2024 | 2024-08-06 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y3 | 4 Nos. of Capex Schemes at Urjanagar Colony & Provision of 11kV Supply to Urjanagar Colony from station board of Stage-III; Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit # 5, 6 &7 of CSTPS, Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 25.78 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Scheme-1: Upgradation of 11KV Sub-stations of Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 7.19 | 7.19 | 7.19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-3: Replacement of old energy meters by electronics energy meters at Urjanagar colony, CSTPS, Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-5 : Provision of 11KV supply to Urjanagar colony from station board of Stage-III, CSTPS Chandrapur. | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 2.97 | 2.9194 | 2.9194 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-6: Design, Supply, Erection, Installation, Testing and Commissioning of new lifts in place of existing lifts installed at Unit#5,6&7 3X500MW CSTPS Chandrapur (500MW Service Bldg Front & Rear, Turbine House Lift Unit#6 &7, Boiler Passenger lifts Unit#5&7 & Boiler Goods lifts Unit#5) | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 10.48 | 10.48 | 10.48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Scheme-7: Design, supply, erection, installation, testing and commissioning of the boiler goods lifts in place of the existing old lifts installed at Unit#6&7 500MW Stage-III CSTPS Chandrapur | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-25/MSPGCL/0473 Dt 06.08.2024 | 2024-08-06 | 0.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y4 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Providing 1600 mm pipeline from Erdai Dam to CSTPS, Chandrapur | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 78.3255 | 78.3255 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/MSPGCL/0476 Dt 06.08.2024 | 2024-08-06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Y5 | Performance Improvement & Life Extension Schemes for CHP of Unit 5 to 7 of CSTPS, Chandrapur. -Part-2 | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Scheme-1: Upgradation/Renovation of Deck Module of Under Ground Conveyor stream of CHPB of Unit-5,6&7 Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.43 | 4.43 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Scheme-2: Renovation & Upgradation of Transfer Point of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.54 | 4.54 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Scheme-3: Renovation & Upgradation of Walkway Platform of CHPB of Unit 5 to 7 of CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.25 | 5.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Scheme-4: Work of Renovation & Modernization of Bunker Shuttle Conveyor of CHPB of Unit 5, 6 & 7 in CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 4.61 | 4.61 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Scheme-5: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-B of Unit 5,6&7 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Scheme-6: Renovation & Modernization of Wagon Tippler Concrete Hopper of Coal Handling Plant-D of Unit 8&9 at CSTPS Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 3.83 | 3.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Scheme-7: Design, supply, installation & commissioning of LED based energy efficient illumination system at CHP-A, B & C, C.S.T.P.S., Chandrapur. | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 5.31 | 5.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-2024/0466 Dt 02.08.2024 | 2024-08-02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
63 | Procurement of Equipment’s for Stack yard management at Coal Handling Plant & Upgradation of existing ash disposal pump system by installing higher efficiency pump system in Ash Handling Plant of Unit- 5 & 6 at CSTPS, Chandrapur. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 38.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Scheme-1: Procurement of 04 Nos Bulldozers. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 9.58 | 9.58 | 9.58 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Scheme-2: Procurement of 01 No Wheel Dozer | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Scheme-3: Procurement 02 Nos. 800 HP Diesel Hydraulic Locomotives. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Scheme-4: Upgradation of existing ash disposal pump assembly by higher efficiency pump assembly in ash handling plant. | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 17.46 | 17.46 | 17.46 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/496 Dt 08.08.2024 | 2024-08-08 | 0.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
64 | Stacker Reclaimer, Impact Crusher and Conveyor Drive reliability & availability improvement scheme for CHP of Unit 5,6&7 CSTPS Chandrapur.- Elecon | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 32.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Reliability & availability improvement for Stacker Reclaimer by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS Chandrapur. | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 17.61 | 17.61 | 17.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Reliability & availability improvement for Conveyor Drive by supply & commissioning of essential equipment at CHPB of Unit 5,6&7 CSTPS | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 14.65 | 14.65 | 14.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC approved MERC/CAPEX/MSPGCL/2023-24/566 Dt 09.09.2024 | 2024-09-09 | 0.29 | 0.29 | 0.29 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet To Receive Approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y8, Y9 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. & Supply of Combine Fire fighting & Rescue vehicle, quick response vehicle and High capacity machine for providing services of debris, dust, coal partials etc cleaning, lifting and transporting by mechanized way along with dedicated manpower for operation and maintenance for three years. | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BOXN-HL Wagons for C.S.T.P.S., Chandrapur. | Yet To Receive Approval | - | 0 | 13.8 | 13.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Combined Fire and Rescue vehicle with Hydraulic Platform (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 10.19 | 10.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Quick Response Vehicle (Multipurpose Fire Tender) | Yet To Receive Approval | - | 0 | 2.55 | 2.55 | 0 | 0 | 0 |  |  | 0 | 0
0 | High capacity Machine for debris transporting by Mechanized way (Vehicle) along with jetting machine | Yet To Receive Approval | - | 0 | 8.35 | 8.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y10 | Retrofitting of existing SF6 HT Circuit Breakers installed at Unit # 7 & EM-II (Outdoor plant) of 3X500MW CSTPS Chandrapur by latest technology HT Contactor/ Vacuum Circuit breakers along with Supply, Installation & Commissioning | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB make SF6 Circuit Breakers installed at AHP Unit#7 by latest technology SF6 HT Contactor/ Vacuum Circuit Breaker | Yet To Receive Approval | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of existing ABB/Voltas make SF6 Circuit Breakers installed at CCW Board of Unit#5,6&7 ODP-II, WTP- II Board of ODP-II, Raw water RWS Board of ODP-II by latest technology Vacuum Circuit Breaker: | Yet To Receive Approval | - | 0 | 17 | 17 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y11 | Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for wagon Tippler & Portable Reclaim Feeder for CHP of Unit 5 to 9 of CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Design, Engineering, Manufacturing, Supply, Erection, Commissioning and testing of Wagon Locking System for Wagon Tippler of CHP of Unit 5 to 9 of CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 11.9 | 11.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Manufacturing, Supply, Erection, Commissioning, and testing of Portable Reclaim Feeder for CHP of Unit 5 to 9 in CSTPS Chandrapur. | Yet To Receive Approval | - | 0 | 18.49 | 18.49 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y12 | Efficiency and Reliability improvement of PRDS, HP Heaters & Boiler pressure part system by rejuvenation of control valves, CSTPS Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Procurement of Sub body assembly & Actuator for control & motorized valves for U#3 & U#4 (210MW). | Yet To Receive Approval | - | 0 | 16.5 | 16.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Procurement of HC & LC Feed and Soot Blower Drain Control sub body assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 3.05 | 3.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Procurement of actuator assembly for control valves for boiler Unit- 5, 6 & 7 (500MW). | Yet To Receive Approval | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Procurement of HP heaters drip sub body assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.39 | 1.39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-5: Procurement of actuator assembly for control valve of 500MW Unit-5,6&7. | Yet To Receive Approval | - | 0 | 1.95 | 1.95 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y13 | Supply & installation of Advanced ESP Controller & Numerical relay at U-7 and DAVR & Up-gradation of Servo valves (ST) for HP-Bypass system at U-5,6,7, CSTPS | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme1: Supply and installation of advanced ESP Controllers for retrofitting in place of existing Alstom make EPIC-II controllers at ESP U-7 | Yet To Receive Approval | - | 0 | 4.15 | 4.15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Supply and installation of DAVR at U-5,6,7 | Yet To Receive Approval | - | 0 | 6.07 | 6.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 3: Supply, installation and commissioning of numerical protection relays with set of auxiliary relays for HT switchgear, Unit-7 | Yet To Receive Approval | - | 0 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme 4: Up-gradation of Servo valves (ST) by Proportional valves (PV) & oil unitOV to HV for HP- Bypass system in U-5,6,7 | Yet To Receive Approval | - | 0 | 9.86 | 9.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Y14 | Improvement in Reliability and Life Enhancement of Coal Mill by Refurbishment of Flender make KMS 850 Gear Box of XRP-1043 Coal Mill Unit 5 & 6 at CSTPS, Chandrapur | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Coal Mill Life Enhancement by Refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill in Unit-5&6 | Yet To Receive Approval | - | 0 | 24.96 | 24.96 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet To Receive Approval | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | ‘Supply, installation, restoration, up-gradation and revamping of Fire Protection Systems viz Fire Hydrant System, Passive Fire Protection System, DV House Construction & Fire Water Spray System at plant & ODP area of Unit-3to9 and CHPs (CHP-A,B,C,&D) of CSTPS, Chandrapur’ | 0 | - | 118.75 | 118.75 | 118.75 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Fire Detection & Alarm and Protection System from Fire and Providing Rapid Extinguishing Clean Agent (CA) System at Unit -7, Outdoor Plants, CHPs, Service building & Admin Building at CSTPS | 0 | - | 31.56 | 31.56 | 31.56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation of various component of bottom opening bogie frame at CSTPS Chandrapur & Provision of Wagon Tippler Safety System in Coal Handling Plant at CSTPS | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
5 | Construction of road from CHP Weighbridge to Railway Crossing & provision of Road Under Bridge (RUB) at CSTPS, Chandrapur | 0 | - | 41.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete pavement road connecting to CHP weighbridge to Railway crossing at CSTPS, Chandrapur. | 0 | - | 5.42 | 5.42 | 5.42 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of Road Under Bridge at Vivekanand Nagar Tukum At CSTPS, Chandrapur. | 0 | - | 35.82 | 35.82 | 35.82 | 0 | 0 | 0 |  |  | 0 | 0
6 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of UCR wall and bed of Neri Nallah at CSTPS, Chandrapur. | 0 | - | 33.47 | 33.47 | 33.47 | 0 | 0 | 0 |  |  | 0 | 0
7 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Concrete Pavement Road Connecting to Reject Coal Gate & F point upto Ash water recovery pump house & F point to CP No- 635 at CSTPS Chandrapur | 0 | - | 71.5 | 71.5 | 71.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Coal mill improvement | 0 | - | 54.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | The performance improvement & availability enhancement of coal millsXRP-803 at U#3&4(210MW)CSTPS, Chandrapur | 0 | - | 18.74 | 18.74 | 18.74 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Existing Volumetric coal feeders by Rotary Gravimetric coal feeders | 0 | - | 36 | 36 | 36 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for APH basket, HRH coil and Valves | 0 | - | 28.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of APH Basket assemblies at U#3&4,CSTPS, Chandrapur | 0 | - | 4.94 | 4.94 | 4.94 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of complete HRH coils assembly in U#4 | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for ESP internal and CRH coil | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of complete internals of ESP U#3&4 | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of CRH coil assemblies in U#3 | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement & replacement of LTSH & Economiser coil assemblies in U#3 | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for Vaccuum system improvement and procurment of BFP cartridge | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Condenser vaccuum system improvement | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP main pump cartridges for 200 KHI/s BHEL pump & Procurment of Voith Hydraulic Coupling R17K for BFP | 0 | - | 19 | 19 | 19 | 0 | 0 | 0 |  |  | 0 | 0
2 | WTP-I improvement schemes | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of instrument air an service air compressors in Unit 3 & 4, WTP-I with screw type compressors including refrigerant type air dryer system | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of hydrogen compressors at Hydrogen plant WTP-I | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Circulating water pumps in Unit 3 & 4 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurment of HP valves, CEP Cartridge, GS pump | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP valves for Unit 3 & 4 | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement cartridges for Condensate extraction pump ( Make KSB WKT 150/7) | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of WPIL make GS pump JTC 24E with pipelines and valves for Unit 3 & 4 | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrical maintenance -I | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | DPR for colony electrical renovation, switchgear, Energy meter, breaker | 0 | - | 47.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Colony electrical renovation | 0 | - | 47.3 | 37.3 | 37.3 | 0 | 10 | 10 |  |  | 10 | 0
2 | Electrification and illumination of perimeter wall CSTPS, Chandapur as per IB recomm | 0 | - | 25.68 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Electrification and illumination of perimeter wall CSTPS, Chandapur | 0 | - | 12.52 | 12.52 | 12.52 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Distibution board, and switchgear at different areas of plant, colony, Dam | 0 | - | 12.35 | 12.35 | 12.35 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Energy meter | 0 | - | 0.81 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, Breakers, VFDs at compressor, Watch Tower | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of 400V, 220V, 50V, 26V batteries and its battery chargers at 210MW, CSTPS. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting of Breakers | 0 | - | 6.8 | 6.8 | 6.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | supply, installation and commissioning of VFDs at compressor and of soft starters for clear water pump at 210MW, CSTPS. | 0 | - | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of Watch Tower along periphery compound wall as per IB recommendation at CSTPS, Chandrapur | 0 | - | 6.4 | 6.4 | 6.4 | 0 | 0 | 0 |  |  | 0 | 0
0 | TIC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation of complete Instrumentation System including FSSS System , Soot Blower System, Station C &I System ,Turbine protection system, Turbovisory, HP/LP and PRDS at CSTPS Unit # 3&4 (210 MW) | 0 | - | 48.608 | 48.608 | 48.608 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4, Upgradation of old ACS, PLC, SCADA WTP, FBTS, WTP measuring and instrumentation & other WTP improvement schemes | 0 | - | 25.39 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Retrofitting/Upgradation of critical control loops by multiloop programmable controllers at Unit #3 & 4 CSTPS,Chandrapur. | 0 | - | 6 | 3 | 3 | 0 | 3 | 3 |  |  | 3 | 0
0 | Upgradation of Old control system with PLC and SCADA at WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.89 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & commissioning of advanced Microprocessor based Fast Bus Transfer Scheme for Stage-II Unit 3&4, CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring & Instrumentation of WTP Stg-I of U# 3,4, 8 and 9, CSTPS, Chandrapur. | 0 | - | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Ash Level Monitoring System at ESP/Eco / AHP Ash Hoppers at U# 3,4 CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Obsolete Electromechanical Protection Relays to advanced Numeric Relays Installed at WTP - I | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgardation of BPF Scoop with electrical actuators at U#3 & 4 CSTPS, Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Measuring Instruments, Final Control Elements and Control System for Unit #3/4, WTP, AHP CSTPS Chandrapur | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
4 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation Errection and commissioning of Solar System for Electrical Suppy to CSTPS Colony. | 0 | - | 60 | 0 | 0 | 0 | 60 | 60 |  |  | 60 | 0
5 | Rejuvenation of WTP-I | 0 | - | 26.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing rejuvenation with upgradation of rapid gravity sand filters under drain system. | 0 | - | 8.2 | 8.2 | 8.2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of NDM clarifier of 27 Mtr dia & DM clarifier of 15 mtr dia. | 0 | - | 2.45 | 2.45 | 2.45 | 0 | 0 | 0 |  |  | 0 | 0
0 | Repairing & reconditioning of ion exchanger vessels of DM plant stream (PF,ACF,SAC,WBA,SBA,MB &Degassor) | 0 | - | 15.75 | 15.75 | 15.75 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-A | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Proc of Loco, Bulldozer, & upgradation of Wagon Tippler, Stacker, Wing Tripper & installation of Dust Extraction system | 0 | - | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 numbers WDG-3A Locomotives and 4 numbers Bulldozers | 0 | - | 38 | 38 | 38 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Wagon Tipplers, Stacker Reclaimer Machine and Wing Tripper at CHP-A | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Installation of Dust Extraction system at Bunker and SCR buildings | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation of BC-9A & BC-9C, Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3, Upgradation of Junction Tower-1 Hopper and Bunkering Trippers, Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of BC-9A & BC-9C for converting 1000 mm to 1200 mm along with Gantry structure replacement | 0 | - | 12 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Aerial Ropeway System 1 & 2 & BC-L1,L2 & L3 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Junction Tower-1 Hopper and Bunkering Trippers | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Providing and Installation of Hopper Grills of Wagon Tippler-169 & 170, Road Hopper, DT Ho[pper and DRCC Grills | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Bulldozer, Locomotives, Tunnel conveyors, Augur machines | 0 | - | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Bulldozers | 0 | - | 12 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 2 Numbers 800 HP Locomotives | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Tunnel conveyors BC-1AB, BC-4AB, BC-3, BC-5AB & BC-21B | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of 4 Numbers Mobile Coal sampling Equipments (Augur Machines) | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
0 | Boiler Maintenance -II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up Gradation of existing volumetric belt type coal feeders to gravimetric rotary weigh coal feeder of U-5 & 6 at CSTPS | 0 | - | 85.68 | 85.68 | 85.68 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Work of Modification of existing coal bunker and commissioning of bunker chute assembly with vibrating motor to avoid bunker mouth coal choke up for Unit 5 &6 at CSTPS, Chandrapur. | 0 | - | 32.28 | 32.28 | 32.28 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacment of Boiler Thermal Insulation Unit 5 &6, 7 at CSTPS, Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
4 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for Manufacturing, supply and application of wear resistance liners for Coal Mill XRP-1043 and Procurement of Complete Gear box for Coal Mill XRP-1043, ID Fan impeller and sub assembly for Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Modification and Restoration of Eco. outlet to ESP inlet duct of Unit -6 (500MW) CSTPS, Chandrapur . | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
6 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Detailed Project Report for the “Schemes for the Reliability Improvement of coal mill performance by replacing of Conveyor Body, Complete Classifier assembly, Outlet Connecting Duct, Refusal Duct, Girth Gear and Drive Shaft Assembly with Bearing housing and Mill Shell Body and Foundation Deck Spring, Main Speed Reducer Gear box for BBD 4772 coal mill unit-7 for 2024-25 at CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for Supply & Replacement of Divisional Panels in Boiler Unit 5,6 & 7 and Economizer upper coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
8 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Platen Superheater, Front Reheater in Unit-7 and Economizer middle & Economizer lower coil assembly in Unit 5 & 6 CSTPS, Chandrapur. | 0 | - | 52 | 52 | 52 | 0 | 0 | 0 |  |  | 0 | 0
9 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for the Supply & Replacement of Front & Rear Reheater coil assemblies and LTSH terminal tube assembly in Boiler Unit 5 & 6 . | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
10 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR For Coal Mill Performance Improvement and Life Enhancement of BHEL Make XRP-1043 Coal Mills in Unit 5 & 6 At CSTPS, Chandrapur. | 0 | - | 52.62 | 52.62 | 52.62 | 0 | 0 | 0 |  |  | 0 | 0
0 | Turbine Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Post facto DPR for "Urgent restoration and Life Enhancement of Unit#5 500 MW BHEL make Turbo Generator for prolonged efficient operation at Stage-III CSTPS Chandrapur" | 0 | - | 25.42 | 25.42 | 25.42 | 0 | 0 | 0 |  |  | 0 | 0
2 | Upgradation and modernization scheme for Air Washer system installed in U-5 & 6, CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Supply, Installation, Testing & commissioning of Energy Efficient Air Washer System for Unit -5 & 6, 500MW, CSTPS, Chandrapur | 0 | - | 25 | 18.75 | 18.75 | 0 | 6.25 | 6.25 |  |  | 6.25 | 0
3 | Schemes for Improvement in availability & performance of feed system for U-5, 6 & 7, CSTPS, Chandrapur | 0 | - | 44.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of BFP Booster Pump assembly for Unit-5, 6 & 7 CSTPS Chandrapur | 0 | - | 7.2 | 3.2 | 3.2 | 0 | 4 | 4 |  |  | 4 | 0
0 | Procurement of Boiler Feed Pump catridge with CI sealing for Unit- 5 & 6 CSTPS Chandrapur | 0 | - | 11.2 | 5.2 | 5.2 | 0 | 6 | 6 |  |  | 6 | 0
0 | Procurement of Modulating type Boiler Feed Pump Recirculation valve assembly for 500 MW, U-5, 6 & 7 | 0 | - | 15.85 | 15.85 | 15.85 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully bladed dynamically balanced Rotor (along with both side coupling hub) for TDBFP Turbine | 0 | - | 8.5 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 TDBFP Lub System | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
4 | Life enhancement and Reliability improvement schemes of 500MW Main Turbine Assests | 0 | - | 36.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability improvement of Low pressure Turbine by maintaining one set of LP free standing blades as insurance spare | 0 | - | 24 | 24 | 24 | 0 | 0 | 0 |  |  | 0 | 0
0 | Performance and efficiency improvement of 500MW U-5 & 6 High Pressure Turbine module | 0 | - | 9.81 | 9.81 | 9.81 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and efficiency improvement of 500MW U-5 & 6 Main TG Lub System | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
5 | Reliability improvement of Main Turbine | 0 | - | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Brief Scope of Work; Procurement of critical spares for Main TG U-5, 6 & 7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of HP turbine Module along with breach nuts and pipe spool pieces (Type:H30-100-2) for Unit-7, CSTPS, Chandrapur | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
6 | Reliability improvement of IP Turbine for 500 MW Main TG U-5 & 6 | 0 | - | 35 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of Fully Bladed & Dynamically Balanced IP Rotor (M 30-50) for 500MW Unit-5 & 6, CSTPS, Chandrapur under Capital Nature items. | 0 | - | 35 | 35 | 35 | 0 | 0 | 0 |  |  | 0 | 0
7 | Energy saving in Air compressors | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Air Compressor Unit-7 to be replaced in a phased manner with energy efficient compressor | 0 | - | 30 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
8 | Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Manufacture, Supply, Erection & Commissioning,environment friendly, Efficiency Upgrade of AC Plant of Unit-5 & 6 | 0 | - | 50 | 25 | 25 | 0 | 25 | 25 |  |  | 25 | 0
0 | Electrical Maintenance-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. & DPR for “Design, engineering, manufacturing, testing, unloading at site, E&C of 80 MVA 420/11/6.9 kV Three phase Station Transformer and 25 MVA 21/6.9 kV Three phase Unit Auxiliary Transformer as common pool spares for Bhusawal U#4&5, Chandrapur U#8&9 and Khaperkheda U#5”. | 0 | - | 25.07 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 500MW Stage-III CSTPS Chandrapur. | 0 | - | 15.07 | 15.07 | 15.07 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, Manufacturing, Transportation to CSTPS site, unloading, Erection, Testing & Commissioning of new 12.5MVA, 21/3.45 KV, 3 phase, Unit Auxiliary Transformer and 90/45/45 MVA, Rated Voltage: HV-400 KV, LV1-11.5KV, LV2-11.5KV, 3 phase, Station Transformer, complete with all fittings and accessories along with insulating oil for first filling for 500MW Stage-III CSTPS Chandrapur”. | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR for Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Life enhancement and Energy efficiency of Critical HT Auxiliaries of Unit#3 to 7, CSTPS, Chandrapur | 0 | - | 44.31 | 44.31 | 44.31 | 0 | 0 | 0 |  |  | 0 | 0
3 | DPR for “Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur.” | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply & Installation of energy saving plates for Energy Conservation at 3X500MW, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
4 | DPR for "Complete renovation of Chimney elevator ) of Unit-5,6,7" & Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. & DPR for “Provision of 11KV supply to Aundha pump house from Unit 5,6&7.” | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete renovation of Chimney elevator of Unit-5,6,7 | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete revamping of chimney aviation obstruction lights (AOL) & other associated spares installed at unit#5,6&7 CSTPS Chandrapur. | 0 | - | 3 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision of 11KV supply to Aundha pump house from U 5,6&7 Station boards. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
5 | DPR for Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for CEP motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 26 | 26 | 26 | 0 | 0 | 0 |  |  | 0 | 0
6 | DPR for Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy saving by installation of VFD for PA Fan & ID Fan motors at Unit#5 to 9, CSTPS, Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
7 | DPR for refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of Critical HT & LT board installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
8 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Refurbishment of LV bus duct Bus duct of UAT, SAT, station transformer installed at Unit#5,6,&7, CSTPS Chandrapur. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Instrumentation & Control-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete Supply ,Erection and Commissioning DDCMIS system of Unit 7 at CSTPS | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
2 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions for Unit5,6 &7, CSTPS, Chandrapur | 0 | - | 40 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of sub-assy for ID Fan VFD System& Energy Management System (EMS) at Stage-III, CSTPS, & Procurement of numerical motor/feeder protection relay | 0 | - | 26.1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply of sub-assy for ID Fan VFD System | 0 | - | 4.5 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Energy Management System (EMS) at Stage-III, CSTPS, Chandrapur. | 0 | - | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of numerical motor/feeder protection relays | 0 | - | 8.1 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of portable multi function test kit, Microprocessot based CB TIM, CRM & MVDT, CBO analyser, Vacuum cleaner bottle HV tester | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of various motorised control actuators at Unit 5, 6 CSTPS,Chandrapur. | 0 | - | 6 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network & Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and commissioning of Energy Optimization & Real Time Analysis system software for Auxiliary Power management of power network | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply and installation of advanced Microprocessor based Pump performance monitoring system for water pumping stations for Unit#5,6&7, CSTPS, Chandrapur | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of Online Connectivity and Environmental Monitoring (OCEMS) System at Unit-5,6&7 | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement of I&C Testing Labouratory Instruments | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of various motorised control actuators at Unit-7, CSTPS,Chandrapur. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | ODP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete reconditioning of Condensate cooling water system, Ash raw water system & fire fightning system of U-5,6 & 7 | 0 | - | 92 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of cooling tower 5A & 5B of Unit -5. | 0 | - | 45 | 45 | 45 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of induced draft Cooling tower - 6A & 6B internals with supply & replacement to improve the performance of Cooling tower of Unit -6 (500MW), CSTPS, Chandrapur | 0 | - | 47 | 47 | 47 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Complete pump assembly of CCW pump, ACW pump and other schemes | 0 | - | 121 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Replacement of Complete pump assembly of CCW pump installed at U-5,6,7. | 0 | - | 100 | 80 | 80 | 0 | 20 | 20 |  |  | 20 | 0
0 | Replacement of Complete pump assembly of ACW pump installed at U-5,6,7. | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Ash Raw water system & DM/NDM system of U- 7. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Complete reconditioning of Fire fightning system of Stage -I, II, III. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
3 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgradation of existing DM water system along with supply, erection & Commissioning of PLC panel, Instrumentation, CPVC Pipes & fittings, installed at WTP–500MW, CSTPS, Chandrapur. | 0 | - | 56 | 56 | 56 | 0 | 0 | 0 |  |  | 0 | 0
4 | Various work for renovation & improvement of ash disposal pipeline system of Unit # 5 & 6 at CSTPS, Chandrapur. | 0 | - | 58.37 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection & commissioning of third 400 NB ash slurry disposal pipeline for Unit #5 at CSTPS, Chandrapur | 0 | - | 20.19 | 20.19 | 20.19 | 0 | 0 | 0 |  |  | 0 | 0
0 | Supply, Erection, Replacement of 400 NB MSERW pipes of existing Ash disposal pipelines of Unit # 5 & 6 in ‘B’ & ‘C’ zone at CSTPS, Chandrapur. | 0 | - | 38.18 | 38.18 | 38.18 | 0 | 0 | 0 |  |  | 0 | 0
5 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, engineering, supply, installation and commissioning of disposal of bottom ash in under ground mines at Chandrapur area WCL at CSTPS, Chandrapur | 0 | - | 27.55 | 27.55 | 27.55 | 0 | 0 | 0 |  |  | 0 | 0
6 | Supply and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Procurement and replacement of 400 NB MSERW pipe lines of ash disposal system in Ash Handling Plant at CSTPS, Chandrapur. | 0 | - | 81.06 | 59.29 | 59.29 | 0 | 21.77 | 21.77 |  |  | 21.77 | 0
0 | WTP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | SWAS system & STREAM FILTRATION FOR COOLING WATER SYSTEM | 0 | - | 95.65 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Revamping of SWAS system at 3 x 500 MW at WTP-II of CSTPS, Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | STREAM FILTRATION FOR COOLING WATER SYSTEM OF UNIT 5,6,7,8 and 9 OF CSTPS CHANDRAPUR | 0 | - | 85.5299 | 85.5299 | 85.5299 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-B | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Bunker Hopper of Unit 5&6 along with coal flow system & Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC | 0 | - | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Modification,Upgradation & renovation of Bunker Hopper of Unit 5&6 along with coal flow system at CSTPS Chandrapur | 0 | - | 16 | 16 | 16 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 :- Renovation & up gradation of conveyor gantries & Travelling Tripper of CHPB. | 0 | - | 7 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 :- Design, Engineering, Manufacturing, Fabrication, Erection and commissioning of Modified Wobbler Feeder at CHPC of Unit 6&7 of CSTPS Chandrapur | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
2 | installation & commissioning of various LV and MV drives at CHPA & Automation of Control Room of CHPA/B | 0 | - | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Design, Engineering, supply, installation & commissioning of various LV and MV drives at CHPA | 0 | - | 39 | 39 | 39 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2 Automation of Control Room of CHPA/B | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3 Design, Engineering, supply, installation & commissioning of various MV VFD for Crusher 1,2,3&4 at CHPB | 0 | - | 11 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4:- Renovation modernization of 11 KV PMCC Board at Sub-Station-2 of CHPB | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
3 | Renovation & Upgrdation of Bunker lift & Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Renovation & Upgrdation of Bunker lift of Unit 5,6&7 of CHPB | 0 | - | 9 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2:- Desgin, Engineering, supply, installation & commissioning of Energy chain system at various locations of CHPB & CHPC | 0 | - | 20 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
4 | Upgradation of old ropeway, BC-108 A/B, installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1 Work of Renovation & upgradation of Ventilation system of CHPA&CHPB. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-2: Design, Engineering, Supply, fabrication, Erection, installation & commissioning of modified take up arrangement for BC 108A/B of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of coal pile thermal monitoring system for stack pile of CHPA/B. | 0 | - | 8 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-3: Design, Engineering, supply & installation of Belt Tear Detector system for belt conveyor system of CHPB. | 0 | - | 4 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-4: Capacity Enhancement of Belt Conveyor Drives of CHPB by upgrdation of conveyor drvie system. | 0 | - | 5 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
5 | Modification & upgradation in Railway Track network of CSTPS | 0 | - | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Provision of additional take off & cutoff point for CHPD and empty formation at WT outhaul in CSTPS Railway Siding. | 0 | - | 14 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Work of Modification & upgradation in Railway Track network of CSTPS by Complete Track Renewal of old BG rail with other allied works in CSTPS Railway Siding. | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
6 | extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Scheme-1: Augmentation of extension of Pipe Conveyor System from Padmapur Loading Station to Coal Handling Plant-C of Unit 5,6&7 at CSTPS Chandrapur. | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP-C | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, Engineering, supply, Erection and commissioning of new fire fighting system at Pipe conveyor of CSTPS, Chandrapur | 0 | - | 25 | 25 | 0 | 25 | 0 | 0 |  |  | 0 | 25
2 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement of coal transportation by Procurement of UTS (BOBR) Wagons for CHP | 0 | - | 15 | 15 | 0 | 15 | 0 | 0 |  |  | 0 | 15
3 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of set of internals for Paddle feeders | 0 | - | 6 | 6 | 0 | 6 | 0 | 0 |  |  | 0 | 6
4 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Reliability & availability improvement by replacement of transfer chutes at CHP-C | 0 | - | 10 | 10 | 0 | 10 | 0 | 0 |  |  | 0 | 10
0 | Civil U#3 to U#7 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Provision for Scientific storage of coal reject and leachate collection system at CSTPS, Chandrapur | 0 | - | 37.57 | 37.57 | 37.57 | 0 | 0 | 0 |  |  | 0 | 0
2 | Infrastructure development scheme for improvement of CHP at CSTPS, Chandrapur | 0 | - | 47.15 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of RCC platform facility for Coal storage & transportation in CHP-B STACKER I & II area (500MW) at CSTPS, Chandrapur | 0 | - | 47.15 | 47.15 | 47.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Contruction of cement concrete roads in CHP area at CSTPS, Chandrapur | 0 | - | 27.05 | 27.05 | 27.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Arresting Leakages by water proofing treatment in main Plant & ancillary buildings at CSTPS, Chandrapur. | 0 | - | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | A)- water proofing treatment in Control room of WTP-I area. (B)- water proofing treatment inControl room of WTP-II area. (C)- water proofing treatment in Control room of CT Fan area (D)- water proofing treatment in Main Plant area. | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of Unit 3& 4 at CSTPS, Chandrapur | 0 | - | 30 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | Structural strengthening of CHP-A buildings | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
6 | Infrastructure Deveolpment of CSTPS colony at CSTPS Chandrapur . | 0 | - | 67.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new ESR (Elevated Storage Reservoir) at CSTPS Chandrapur | 0 | - | 3.78 | 3.78 | 3.78 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii- Providing & Rerouting of existing water supply pipe line at CSTPS Chandrapur | 0 | - | 4.05 | 4.05 | 4.05 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii- Providing & Rerouting of esiting sewer line at CSTPS colony Chandrapur | 0 | - | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv- Providing water proofing treatment to terrace slab of residential building aaat CSTPS colony Chandrapur | 0 | - | 6.34 | 6.34 | 6.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Construction of storm water drain along major and internal road of CSTPS colony at Chnadrapur | 0 | - | 16.86 | 16.86 | 16.86 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi-Improvement of existing major and internal Bitumen road of CSTPS colony by Bituminous treatment at CSTPS Chandrapur | 0 | - | 29.81 | 29.81 | 29.81 | 0 | 0 | 0 |  |  | 0 | 0
7 | Renovation of residential buildings , Public building , Road and other allied civil works in CSTPS colony at Chandrapur | 0 | - | 209 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Renovation and Beautification of residential building ( Type A, B, C, D, E and F) Phase -II at CSTPS Chnadrapur | 0 | - | 132 | 132 | 132 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Renovation of old and new market at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Improvement of exsiting Main road by Cement Concrte road in colony at CSTPS Chandrapur | 0 | - | 55 | 55 | 55 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Renovation of Civil and Electrical Maint office building at CSTPS Chandrapur. | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | v- Renoavtion of Post office building and Bank Building at CSTPS Chandrapur | 0 | - | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | vi- Renovation fo Erai Dam guest House at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii- Improvement of Erai dam approch road by Bituminous treatment at CSTPS Chnadrapur | 0 | - | 15 | 15 | 15 | 0 | 0 | 0 |  |  | 0 | 0
8 | Construction of new residential building ,Hospital Building ,Chemmary Building,security office building and allied civil work infrastructure in colony at CSTPS Chandrapur | 0 | - | 76.25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | i- Construction of new residential staff quarter of A, B ,C D and E type building in colony at CSTPS Chandrapur | 0 | - | 60 | 60 | 60 | 0 | 0 | 0 |  |  | 0 | 0
0 | ii-Construction of New Hospital Building at CSTSP Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | iii-Construction of new Chummary Building at CSTPS Chandrapur | 0 | - | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
0 | iv-Construction of new security office and check post at various location in colony at CSTPS Chandrapur | 0 | - | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 |  |  | 0 | 0
0 | v-Construction of swimming pool in colony at CSTPS Chandrapur | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | vii-Providing new drinking water supply DI- pipe line 300 mm dia .for domestic water supply to rsidential colony at CSTPS Chandrapur. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
0 | viii-Rain water Harvesting system to residential building at CSTPS Chandrapur. | 0 | - | 2 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
9 | Renovation of public utility building of CSTPS, Chandrapur | 0 | - | 29.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of Hirai guest house | 0 | - | 7.51 | 7.51 | 7.51 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing chummery guest house | 0 | - | 12.22 | 12.22 | 12.22 | 0 | 0 | 0 |  |  | 0 | 0
0 | Renovation and interior decoration of existing Erai dam guest house | 0 | - | 6.65 | 6.65 | 6.65 | 0 | 0 | 0 |  |  | 0 | 0
0 | Work of interior decoration by proding stop cabin arrangement and other internal architechture decorative work for RP section of admin building | 0 | - | 3.57 | 3.57 | 3.57 | 0 | 0 | 0 |  |  | 0 | 0
10 | R&M/LE for Identified Thermal units of MSPGCL | 0 | - | 400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-3 | 0 | - | 293 | 293 | 293 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL, CSTPS U-4 | 0 | - | 300 | 300 | 300 | 0 | 0 | 0 |  |  | 0 | 0
11 | CHP Improvement Schemes | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at CHP-A, B, C | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
12 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Developlment & Upgradation of SAP for MSPGCL | 0 | - | 200 | 200 | 200 | 0 | 0 | 0 |  |  | 0 | 0
13 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation and commissioning of Smart Energy Efficienient Illumination System for safety precautions and proving suitable working conditions at stg-II & III, CSTPS, Chandrapur | 0 | - | 42 | 42 | 42 | 0 | 0 | 0 |  |  | 0 | 0
14 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Flexible Operation Solutions (U-3,4) | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
15 | DPR for ash utilisation cell- infrastructure development | 0 | - | 278.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | DPR for development of infrastructure for loading and dispatch of fly ash through Railway Wagons, CSTPS, Chandrapur | 0 | - | 268 | 268 | 268 | 0 | 0 | 0 |  |  | 0 | 0
0 | Disposal of bottom ash for stowing of u/g mines of Chandrapur Area by installing direct pipeline from CSTPS to WCL | 0 | - | 10 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
0 | Design, supply, installation, testing and commissioning of 100 MT 16X3 Mtr. electronic weigh bridge system, for weighment and dispatch of Pond Ash from Ash bund, CSTPS, Chandrapur | 0 | - | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Up-gradation Schemes for CAAQM Stations & NABL Laboratory | 0 | - | 25 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
17 | Comprehensive Strategies for Environmental Sustainability at CSTPS: Implementing Zero Discharge Policies and Pollution Control Measures for Effective Water Body Management and Hazard Prevention | 0 | - | 27.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Upgrading Settling tank near the Coal Reject Area: Installation of Settling Tank Liners and Enhanced Upgraded Pump House Systems to Prevent Acidic Water Seepage into the Ranvendli Nallah which connected to the ERAI River. | 0 | - | 8.9 | 8.9 | 8.9 | 0 | 0 | 0 |  |  | 0 | 0
0 | Implementation of Zero Water Discharge Solutions: Design, Construction, and Commissioning of New Pump Houses for ETP 1 and ETP 2 to Enhance Capacity for Effective Water Recovery | 0 | - | 10.82 | 10.82 | 10.82 | 0 | 0 | 0 |  |  | 0 | 0
0 | Underground Ash Disposal Pipeline Management: Design, Construction, and Installation of Filter Beds Along Ash Disposal Pipelines for Improved Environmental Protection of Water Bodies from Ingress into the Erai River | 0 | - | 7.88 | 7.88 | 7.88 | 0 | 0 | 0 |  |  | 0 | 0
18 | Ash bund peripheral road | 0 | - | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Ash bund peripheral road | 0 | - | 120 | 120 | 120 | 0 | 0 | 0 |  |  | 0 | 0
19 | Construction of peripheral nallah | 0 | - | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of peripheral nallah | 0 | - | 100 | 100 | 100 | 0 | 0 | 0 |  |  | 0 | 0
20 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Construction of concrete Roads with drains at colony | 0 | - | 110 | 110 | 110 | 0 | 0 | 0 |  |  | 0 | 0
21 | Fugitive emisson reduction techniques | 0 | - | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Fugitive emisson reduction schemes | 0 | - | 50 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | GENERAL ASSET | 0 | - | 20 | 8.3762 | 8.3762 | 0 | 0 | 0 |  |  | 0 | 0
2 | M/S GEO-MILLER arbitration amount | 0 | - | 1.3765 | 0.68824 | 0.68824 | 0 | 0 | 0 |  |  | 0 | 0
3 | CM Reject Handling Sys Macawber Breakey | 0 | - | 3.1822 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Work of Design, Engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt Elecon stack yard of CHPA of U-3 & U-4 to Belt Conveyor 105-A/B at CHP-B of Unit 5, 6 & 7 at CSTPS Chandrapur ((Non-DPR) | 0 | - | 4.8622 | 4.8622 | 4.8622 | 0 | 0 | 0 |  |  | 0 | 0
5 | Non Dpr The Work of Upgradation/Renovation of Track Hopper Unloading Conveyor system with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.742 | 4.742 | 4.742 | 0 | 0 | 0 |  |  | 0 | 0
6 | Non DPR scheme for “The Work of Upgradation of Belt Conveyor 107A/B by replacement of conveyor deck structure with allied works in CHPB of Unit-5, 6&7 at CSTPS Chandrapur | 0 | - | 4.51 | 4.5085 | 4.5085 | 0 | 0 | 0 |  |  | 0 | 0
7 | Non-DPR: Supply, installation & commissioning of oil cooled over band magnetic separators for various conveyor belts of CHP-B & CHP-C, CSTPS, Chandrapur | 0 | - | 3.45 | 3.4451 | 3.4451 | 0 | 0 | 0 |  |  | 0 | 0
8 | Various preventive works to avoid Tiger movement and animals in CSTPS colony premises Up-gradation od existing periphery compound wall by avoiding barbed wire and concertina fencing and allied works in the colony at CSTPS, Chandrapur | 0 | - | 6.41 | 3.612 | 3.612 | 0 | 0 | 0 |  |  | 0 | 0
9 | Repairing, revamping and modification of existing alarm and protection system from fire and providing rapid extinguishing CA system at 500 MW Unit # 5 & 6 CSTPS | 0 | - | 7.95 | 7.95 | 7.95 | 0 | 0 | 0 |  |  | 0 | 0
10 | NON-Detailed Project Report for the Work of Upgradation/Renovation of Crusher House of CHPB of Unit-5, 6&7 at CSTPS Chandrapur (benefit U-8,9 by short conveyor coal stacking in catering emergency) | 0 | - | 4.7 | 1.8275 | 1.8275 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of Up-gradation/Renovation of Bunkering Conveyor system with allied works in CHPA of Unit-3&4 at CSTPS Chandrapur | 0 | - | 4.6024 | 4.6024 | 4.6024 | 0 | 0 | 0 |  |  | 0 | 0
12 | Non-Detailed Project Report for the up-gradation of existing belt type gravimetric coal feeders to gravimetric rotary weigh coal feeders of unit- 7, at CSTPS, Chandrapur | 0 | - | 7.251 | 7.2509 | 7.2509 | 0 | 0 | 0 |  |  | 0 | 0
14 | Non DPR scheme for the procurement of Girth Gear Assembly for BBD-4772 coal mill unit-7 | 0 | - | 5.27 | 5.27 | 5.27 | 0 | 0 | 0 |  |  | 0 | 0
15 | Non DPR Supply of Sub-Assemblies for KBL -make Auxiliary cooling water pump, Model BHR-70 & BHR 60-30 deg. installed at Auxiliary cooling water system of U- 5 to 7 at ODP-II, CSTPS, Chandrapur. | 0 | - | 5.61 | 5.5874 | 5.5874 | 0 | 0 | 0 |  |  | 0 | 0
16 | Procurement of Primary and Secondary Air Pre-heater Baskets for Unit-5, Chandrapur STPS, 500MW through OEM basis from M/s. BHEL | 0 | - | 9.09 | 9.09 | 9.09 | 0 | 0 | 0 |  |  | 0 | 0
17 | Restoration of Operational efficiency and improvement in useful life of spare HP turbine Module of 500MW Unit-5,6 CSTPS chandrapur by Refurbishement | 0 | - | 9.95 | 9.95 | 9.95 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of Upgradation/Renovation of Crusher House & Track Hopper Unloading System of CHPC of Unit-6&7 CSTPS Chandrapur | 0 | - | 4.9 | 4.9 | 4.9 | 0 | 0 | 0 |  |  | 0 | 0
19 | Non – DPR: Design, supply, erection, installation, testing and commissioning of boiler goods lift in place of existing old lifts installed at Unit#6,7 500MW CSTPS, Chandrapur | 0 | - | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 |  |  | 0 | 0
20 | Work of refurbishment of Flender make KMS 850 gear box of XRP-1043 coal mill unit 5&6 at CSTPS, Chandrapur | 0 | - | 4.37 | 4.37 | 4.37 | 0 | 0 | 0 |  |  | 0 | 0
21 | Work of renovation of take up trestle structure of BC-105A2/BC-105B and trestle near TP-104, Modification of MS fixtures for the work of various auxiliary replacement at various sites and other allied works in CHP-B (M2) at CSTPS Chandrapur, as NonDPR Scheme. | 0 | - | 2.24 | 2.24 | 2.24 | 0 | 0 | 0 |  |  | 0 | 0
22 | Non DPR scheme for upgradation and life enhancements of BC-1AB_BC-4AB at CHP-A, CSTPS, Chandrapur | 0 | - | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
23 | THE PROCUREMENT AND REPLACEMENT OF AIR PREHEATER BASKETS ASSEMBLIES AT UNIT-6 AT CSTPS, CHANDRAPUR | 0 | - | 9.01 | 9.01 | 9.01 | 0 | 0 | 0 |  |  | 0 | 0
24 | NonDPR: Procurement of cartridge for boiler feed pump of 500MW U#7 and parallel shaft gear box for boiler feed pump of 500MW Unit-5 &6 CSTPS, Chandrapur | 0 | - | 2.57 | 2.57 | 2.57 | 0 | 0 | 0 |  |  | 0 | 0
25 | Replacement of FD & ID Fan IGV Actuators & Electronic Controllers in 500 MW Unit-5 & 6 at CSTPS, Chandrapur | 0 | - | 4.2 | 4.2 | 4.2 | 0 | 0 | 0 |  |  | 0 | 0
26 | Non DPR for Work of Repairing and Strengthening of Coal Mill structure, Replacement of MS grating and painting of structural supports, columns, and platform supports of at various locations Coal Mill, Boiler and ESP of Unit-5, 6 and 7 at CSTPS Chandrapur. | 0 | - | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 |  |  | 0 | 0
27 | Administrative approval under Non DPR scheme for“The Work of Up-gradation / Renovation and life enhancement of Conveyor system BC-6ABC with allied works in CHP-A of Unit-3&4 at CSTPS Chandrapur” | 0 | - | 4.55 | 4.55 | 4.55 | 0 | 0 | 0 |  |  | 0 | 0
28 | Supply Erection and commissioning of Institu type SOX, NOX Analyzer along with remote calibration facility and connectivity to CPCB and MPCB as per latest CPCB Guidelines for Unit-3&4, CSTPS. | 0 | - | 0.97 | 0.97 | 0.97 | 0 | 0 | 0 |  |  | 0 | 0
29 | Work of Renovation & Upgradation of Receipt & Dispatch Yard of Railway Siding of CSTPS by provision of Various Standard Infrastructure facilities at R&D yard in Coal Handling Plant of CSTPS Chandrapur | 0 | - | 7.89 | 7.89 | 7.89 | 0 | 0 | 0 |  |  | 0 | 0
30 | Supply, Installation and Commissioning of MV VFD panel along with integrated online cell redundancy technology with VFD bypass feature arrangement for conveyors 103 A & B of CHP-B. | 0 | - | 5.44 | 5.44 | 5.44 | 0 | 0 | 0 |  |  | 0 | 0
31 | Replacement of LTSH assemblies in U- 5 | 0 | - | 1.3757 | 1.3757 | 1.3757 | 0 | 0 | 0 |  |  | 0 | 0
32 | Replacement of complete Z-panels in unit- 5 | 0 | - | 0.82546 | 0.82546 | 0.82546 | 0 | 0 | 0 |  |  | 0 | 0
33 | MODIFICATION AND RESTORATION OF APH OUTLET TO ESP INLET DUCTS AT U#3 (210MW) | 0 | - | 10.3 | 10.3 | 10.3 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply, Installation, Testing, Commissioning for complete solution and comprehensive protection and monitoring package along with retrofit of allied accessories for Generator Transformers for 3 X 500 MW Unit#5,6&7 | 0 | - | 5.62 | 5.62 | 5.62 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | #VALUE! | #VALUE! | #VALUE! | 211.02 | 211.02 | 0 | 0 | 211.02 | #VALUE!